## Chapter 1
Ship name: |  | COTE D'ALBATRE
Case No.: |  | 231051
Currency: | DKK | Chapter 1 |  |  |  | Estimate | New/changes | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-03-31 | 2023-04-05 | 2023-04-11 | 2023-04-13 | 2025-05-06 | Total
1001 | 6866 + 6930 + 6932 | Dry docking
|  | Docking / undocking including first day | QUOTED | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 50000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each following day | QUOTED | 19 | 30000 | 600000 | 0 | 0 | -30000 | 0 | 570000
1005 | 6878 | Fire precautions
|  | Fire Line under pressure max. 5 bar, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000
|  | Maintenance per day incl. Electrical consumption | QUOTED | 20 | 350 | 7350 | 0 | 0 | -350 | 0 | 7000
1009 | 6888 | Garbage and refuse
|  | Garbage containers (4 m³) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Garbage container on the quay, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each time emptied, incl. disposal | QUOTED | 7 | 5000 | 35000 | 0 | 0 | 0 | 0 | 35000
1011 | 6916 | Supply of gangway
|  | Gangway, each | QUOTED | 2 | 4000 | 8000 | 0 | 0 | 0 | 0 | 8000
1012 | 6882 | Shore supply of cooling water
|  | Connection of cooling water, each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000
|  | Cooling out, each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000
|  | Supply of Cooling water SW, per day incl. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Electrical consumption | QUOTED | 42 | 750 | 31500 | 0 | 0 | 0 | 0 | 31500
1013 | 6884 | Supply of domestic fresh water
|  | Connection of FW hose, Each time | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000
|  | Supply of FW, per m³ | QUOTED | 500 | 40 | 20000 | 0 | 0 | 0 | 0 | 20000
1014 | 6910 | Sewage system
|  | Sewage connection/disconnection | QUOTED | 1 | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000
|  | Disposal during yard stay, each m³ | QUOTED | 58 | 95 | 9500 | 0 | -3990 | 0 | 0 | 5510
|  | Mud truck | QUOTED | 30 | 1150 | 0 | 0 | 34500 | 0 | 0 | 34500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Treated sewage connection incl. Disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | during yard stay | NA | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Grey/Black water connection on/off to Yard |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | facilities (mixed BW/GW) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Sewage connection, each time | NA | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal during yard stay, each m³ | NA | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Grey/Black water discharge to Yard facilities |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | (mixed BW/GW) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud truck per hour | NA | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on normal working hours |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal per m³ | NA | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0
1016 | 6894 | Office and communications
|  | Superintendents office: | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000
1017 | 6906 | Supply of ballast water
|  | Connection of Ballast water connection, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each hose | QUOTED | 1 | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000
|  | Supply of ballast water, each m³ | QUOTED | 400 | 8 | 3200 | 0 | 0 | 0 | 0 | 3200
|  | Further assistance with ballasting: As per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1043 | 6808 | Sacrificial anodes - Renew
|  | Change of owner supplied Bera Alu anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 43 (4,3 kg), each |  | 14 | 540 | 0 | 0 | 7560 | 0 | 0 | 7560
|  | AL 60 (6,0 kg), each |  | 40 | 645 | 14400 | 7200 | 330 | 3870 | 0 | 25800
|  | Incl. cherry picker, demounting of old, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | mounting of new, welded type |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1047 | 6860 | Sea chests and gratings
|  | Sea chests opened, cleaned and painted, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | minimum 1 m³/seachest: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 - 5 m³, each m³ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 pc. 1,7 x 0,7 x 2,8 = 3,3 m³ | QUOTED | 3 | 1940 | 6402 | 0 | 0 | 0 | 0 | 6402
|  | 1 pc. 2,1 x 1,2 x 0,7 = 1,8 m³ | QUOTED | 2 | 1940 | 3492 | 0 | 0 | 0 | 0 | 3492
|  | 1 pc. 2,2 x 0,9 x 2,5 = 4,9 m³ | QUOTED | 5 | 1940 | 9506 | 0 | 0 | 0 | 0 | 9506
|  | 1 pc. 1,8 x 1,3 x 1,5 = 3,5 m³ | QUOTED | 4 | 1940 | 6790 | 0 | 0 | 0 | 0 | 6790
|  | Excl. Possible staging |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal of barnacles per ton |  | 3 | 7500 | 22500 | 0 | 0 | 0 | 0 | 22500
1048 | 6862 | Paint jobs
|  | Flat bottom 2000 m² based Wj-2 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP washing with max 500 bar | QUOTED | 2000 | 20 | 40000 | 0 | 0 | 0 | 0 | 40000
|  | Wj-2 basis 100% | QUOTED | 2000 | 132 | 264000 | 0 | 0 | 0 | 0 | 264000
|  | HP washing with 500 bar for removal of new rust | QUOTED | 2000 | 20 | 40000 | 0 | 0 | 0 | 0 | 40000
|  | Fc 1 coat | QUOTED | 2000 | 6.25 | 12500 | 0 | 0 | 0 | 0 | 12500
|  | Fc 1 coat NEXUS ll (silicone) | QUOTED | 2000 | 12.5 | 25000 | 0 | 0 | 0 | 0 | 25000
|  | Fc 1 coat X-Tend (silicone) | QUOTED | 2000 | 12.5 | 25000 | 0 | 0 | 0 | 0 | 25000
|  | Fc 1 coat X8 (silicone) | QUOTED | 2000 | 12.5 | 25000 | 0 | 0 | 0 | 0 | 25000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom 1000 m² based Wj-2 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP washing with max 500 bar | QUOTED | 1000 | 22 | 22000 | 0 | 0 | 0 | 0 | 22000
|  | Wj-2 basis 100% | QUOTED | 1000 | 132 | 132000 | 0 | 0 | 0 | 0 | 132000
|  | WJ-2 of bilge keel with hand held gun | QUOTED | 1 | 35100 | 35100 | 0 | 0 | 0 | 0 | 35100
|  | HP washing with 500 bar for removal of new rust | QUOTED | 1000 | 22 | 22000 | 0 | 0 | 0 | 0 | 22000
|  | Fc 1 coat | QUOTED | 1000 | 9.5 | 9500 | 0 | 0 | 0 | 0 | 9500
|  | Fc 1 coat NEXUS ll (silicone) | QUOTED | 1000 | 19 | 19000 | 0 | 0 | 0 | 0 | 19000
|  | Fc 1 coat X-Tend (silicone) | QUOTED | 1000 | 19 | 19000 | 0 | 0 | 0 | 0 | 19000
|  | Fc 1 coat X8 (silicone) | QUOTED | 1000 | 19 | 19000 | 0 | 0 | 0 | 0 | 19000
|  | Painting of line | QUOTED | 1 | 4750 | 4750 | 0 | 0 | 0 | 0 | 4750
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Boottop 500 m² based Wj-2 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP washing with max 500 bar | QUOTED | 500 | 22 | 11000 | 0 | 0 | 0 | 0 | 11000
|  | Wj-2 basis 7% - 35 m² with hand held gun | QUOTED | 35 | 210 | 7350 | 0 | 0 | 0 | 0 | 7350
|  | HP washing with 500 bar for removal of new rust | QUOTED | 35 | 22 | 770 | 0 | 0 | 0 | 0 | 770
|  | Hosing down with FW, basis 93% | QUOTED | 465 | 3.5 | 1628 | 0 | 0 | 0 | 0 | 1628
|  | Tu 1 coat, based 12% | QUOTED | 60 | 21 | 1260 | 0 | 0 | 0 | 0 | 1260
|  | Tu 1 coat, based 12% | QUOTED | 60 | 21 | 1260 | 0 | 0 | 0 | 0 | 1260
|  | Fc 1 coat | QUOTED | 500 | 9.5 | 4750 | 0 | 0 | 0 | 0 | 4750
|  | Fc 1 coat | QUOTED | 500 | 9.5 | 4750 | 0 | 0 | 0 | 0 | 4750
|  | Painting of line | QUOTED | 1 | 4750 | 4750 | 0 | 0 | 0 | 0 | 4750
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Topside white, 1620 m²: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP washing with max 500 bar | QUOTED | 1620 | 22 | 35640 | 0 | 0 | 0 | 0 | 35640
|  | Mechanical cleaning, based 7% | QUOTED | 113 | 103 | 11680 | 0 | 0 | 0 | 0 | 11680
|  | Hosing down with FW | QUOTED | 1620 | 3.5 | 5670 | 0 | 0 | 0 | 0 | 5670
|  | Tu 1 coat, based 12% done with roll/brush | QUOTED | 194 | 42 | 8165 | 0 | 0 | 0 | 0 | 8165
|  | Tu 1 coat, based 12% done with roll/brush | QUOTED | 194 | 42 | 8165 | 0 | 0 | 0 | 0 | 8165
|  | Fc 1 coat done with roll/brush, based 25% | QUOTED | 405 | 28.5 | 46170 | -34628 | 0 | 0 | 0 | 11543
|  | Fc 1 coat, based 75% | QUOTED | 1215 | 14.25 | 0 | 17314 | 0 | 0 | 0 | 17314
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Topside Yellow, 2700 m²: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP washing with max 500 bar | QUOTED | 2700 | 22 | 59400 | 0 | 0 | 0 | 0 | 59400
|  | Mechanical cleaning, based 11% | QUOTED | 297 | 103 | 30591 | 0 | 0 | 0 | 0 | 30591
|  | Hosing down with FW | QUOTED | 2700 | 3.5 | 9450 | 0 | 0 | 0 | 0 | 9450
|  | Tu 1 coat, based 16% done with roll/brush | QUOTED | 432 | 42 | 18144 | 0 | 0 | 0 | 0 | 18144
|  | Tu 1 coat, based 16% done with roll/brush | QUOTED | 432 | 42 | 18144 | 0 | 0 | 0 | 0 | 18144
|  | Fc 1 coat | QUOTED | 2700 | 14.25 | 76950 | -38475 | 0 | 0 | 0 | 38475
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional costs due to application of Silicone |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | paint: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of dock before and after painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | (environmental reason), |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering against topside for silicone painting, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Renewal of damages paint hoses due to Silicone |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | paint | QUOTED | 1 | 145000 | 145000 | 0 | 0 | 0 | 0 | 145000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Marks etc.: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of existing Cargo, plimsol, thruster and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | bulb markings | QUOTED | 1 | 5665 | 5665 | 0 | 0 | 0 | 0 | 5665
|  | Name and homeport | QUOTED | 1 | 6170 | 6170 | 0 | 0 | 0 | 0 | 6170
|  | Bottom marks with silicone tape | QUOTED | 1 | 20900 | 20900 | 0 | 0 | 0 | 0 | 20900
|  | Painting of blue line and "T" logo |  | 1 | 37440 | 37440 | 0 | 0 | 0 | 0 | 37440
|  | Painting of "TRANSMANCHEFERRIES" logo |  | 1 | 70200 | 70200 | 0 | 0 | 0 | 0 | 70200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering of: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Anodes and sensors, each | QUOTED | 54 | 21 | 1134 | 0 | 0 | 0 | 0 | 1134
|  | ICCP anodes, each | QUOTED | 4 | 925 | 3700 | 0 | 0 | 0 | 0 | 3700
|  | Propellers, each | QUOTED | 4 | 580 | 2320 | 0 | 0 | 0 | 0 | 2320
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Drain plugs fitted/removed, each | QUOTED | 22 | 135 | 2970 | 0 | 0 | 0 | 0 | 2970
1062 |  | Covering of vessel bottom with staging and
|  | plastic cover for silicone paint incl. Winter |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | covering. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering of vessels bottom with staging and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | plastic cover | QUOTED | 1 | 1338875 | 1338875 | 0 | 0 | 0 | 0 | 1338875
|  | Mobilization and demobilization of heating | QUOTED | 1 | 230350 | 230350 | 0 | 0 | 0 | 0 | 230350
|  | Heating (excl. Supply of fuel) Based 10 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 185 KW blowers. | QUOTED | 1 | 245000 | 245000 | 0 | 0 | 0 | 0 | 245000
|  | Vessel is to supply fuel and make sure that |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | diesel tanks are filled for hearing the vessel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1063 | VOR 2 | Demounting and mounting ventilation
|  | grid SB and PS shell 10 pcs. incl. painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Pointed out by super intendent |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Demounting and mounting of ventilation grids |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | In total 10 pcs. | VOR 2 | 1 | 34474 | 34474 | 0 | 0 | 0 | 0 | 34474
|  | Cherry picker | VOR 2 | 1 | 29800 | 29800 | 0 | 0 | 0 | 0 | 29800
|  | Crane | VOR 2 | 1 | 8500 | 8500 | 0 | 0 | 0 | 0 | 8500
|  | Grinding and painting of frame, each | VOR 2 | 10 | 3900 | 39000 | 0 | 0 | 0 | 0 | 39000
|  | TU ventilation grids, each | VOR 2 | 10 | 1040 | 10400 | 0 | 0 | 0 | 0 | 10400
|  | Scaffolding inside ventilations duct | VOR 2 | 1 | 9500 | 9500 | 0 | 0 | 0 | 0 | 9500
|  | Owner will deliver paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1064 | VOR 4 | Cleaning Crossover T.M
|  | For Cleaning crossover: | VOR 4 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Manpower 3 Man 3 days 12 hour shift. | QUOTED | 1 | 65000 | 85500 | 0 | -20500 | 0 | 0 | 65000
|  | High pressure washing equipment 3 days rent | QUOTED | 1 | 12500 | 12500 | 0 | 0 | 0 | 0 | 12500
|  | Disposal | QUOTED | 1 | 16500 | 25000 | 0 | -8500 | 0 | 0 | 16500
|  | Mud truck. | QUOTED | 1 | 23000 | 29000 | 0 | -6000 | 0 | 0 | 23000
1065 | VOR 5 | Painting windows SB and PS
|  | Painting of all windows SB and PS | VOR 5 | 1 | 48034 | 48034 | 0 | 0 | 0 | 0 | 48034
|  | Owner will deliver paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1066 | VOR 7 | Bridge wings below SB and PS
|  | Mech. grinding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Emulsions cleaning incl. fluid |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu 2 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | VOR 7 | 1 | 25200 | 25200 | 0 | 0 | 0 | 0 | 25200
|  | Owner will deliver paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1067 | VOR 10 | Funnel incl. logo to be painted
|  | Emulsions cleaning incl. fluid |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mech. grinding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Washing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu 2 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of existing logo |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | VOR 10 | 1 | 151200 | 151200 | 0 | 0 | 0 | 0 | 151200
|  | Owner will deliver paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1068 | VOR 11 | Bow thruster tunnel 1+2
|  | HP-wash with 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SA 2 / WJ-2 min. 0,25 m²/spot, basis 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-wash with 500 bar, spot |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat SIGMA SHIELD | VOR 11 | 1 | 36400 | 36400 | 0 | 0 | 0 | 0 | 36400
|  | Owner will deliver paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1069 |  | Epoxy filler around echosounder
|  | Epoxy filler around echosounder |  | 1 | 10500 | 0 | 10500 | 0 | 0 | 0 | 10500
1070 |  | Cleaning and painting scrubber outlet
|  | Cleaning and painting scrubber outlet |  | 1 | 8500 | 0 | 8500 | 0 | 0 | 0 | 8500
1072 | VOR 9.1 | Front of accommodation to be painted
|  | except windows |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mech. Grinding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Emulsion cleaning incl. fluid |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu 2 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat | VOR 9.1 | 1 | 34300 | 34300 | 0 | 0 | 0 | 0 | 34300
|  | Job have to be done from a crane basket | QUOTED | 1 | 48000 | 60000 | 0 | -12000 | 0 | 0 | 48000
|  | Owner will deliver paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1075 |  | Sea filter Cleaning – grinding and painting
|  | Sea filter Cleaning – grinding and painting |  | 1 | 12000 | 0 | 12000 | 0 | 0 | 0 | 12000
1077 | VOR 18 | Pullert 2 pcs.
|  | Emulsion cleaning incl. fluid |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mech. grinding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | VOR 18 | 1 | 22400 | 0 | 22400 | 0 | 0 | 0 | 22400
1078 | VOR 19 + 19.1 | Painting crossover incl. Washing 250 bar
|  | Scrabing, Cleaning and 2x Fc | VOR 19 | 1 | 27160 | 0 | 27160 | 0 | 0 | 0 | 27160
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional to VOR 19 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | High pressure washing, cleaning and painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 coat epoxy | VOR 19.1 | 1 | 35000 | 0 | 35000 | 0 | 0 | 0 | 35000
|  | Mud truck | VOR 19.1 | 1 | 9000 | 0 | 9000 | 0 | 0 | 0 | 9000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Owner will deliver paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1080 | VOR 20 | Bulp + Down below Duck tail SB + PS on
|  | boottop after end paint removal. | VOR 20 | 1 | 37440 | 0 | 37440 | 0 | 0 | 0 | 37440
|  | WJ-2 pistol / Mech. cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
9993 |  | Discount according to agreement | 10% | 1 | -476404.1 | 0 | 0 | 0 | -476404 | 0 | -476404
|  |  | DKK |  |  | 4685709 | 113411 | -8600 | -502884 | 0 | 4287637 | 0