## Chapter 0
Ship name: |  | LUNA SEAWAYS
Case No.: |  | 231054
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-03-30 | 2023-04-13 | 2025-05-06 | Total
1000 |  | Sag
1001 | 200.01 | Drydocking
|  | Dock/undock and first day dues | QUOTED | 1 | 65000 | 65000 | 0 | 0 | 65000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Cost for subsequent days, each day | QUOTED | 22 | 30000 | 690000 | -30000 | 0 | 660000
1002 | 500.06 | Shore connection
|  | Connection/disconnection |  | 0 |  | 0 | 0 | 0 | 0
|  | Electric power supply: 400 V, 50Hz, 1000 Amp | QUOTED | 2 | 16000 | 32000 | 0 | 0 | 32000
|  | Maintenance per day | QUOTED | 46 | 750 | 36000 | -1500 | 0 | 34500
|  | Kw-hour, each | QUOTED | 202313 | 4.2 | 1260000 | -410285 | 0 | 849715
|  | Additional cost if shoreconnection is only used |  | 0 |  | 0 | 0 | 0 | 0
|  | as a stand-by connection | CANCELLED | 0 |  | 0 | 0 | 0 | 0
1003 | 200.01.3+500.25 | Earthing of vessel, included in docking.
|  | Earthing of vessel, included in docking. | INCL. | 0 |  | 0 | 0 | 0 | 0
1004 | 500.01 | Crane assistance
|  | Based yards rail cranes: |  | 0 |  | 0 | 0 | 0 | 0
|  | Each normal hour up to 45 t, each hour | QUOTED | 30 | 1500 | 45000 | 0 | 0 | 45000
|  | Based mobile cranes: |  | 0 |  | 0 | 0 | 0 | 0
|  | Each normal hour | N/A | 0 |  | 0 | 0 | 0 | 0
|  | Forklift 3/5 tons for Owner use, included driver: |  | 0 |  | 0 | 0 | 0 | 0
|  | Per normal hour | QUOTED | 30 | 1000 | 30000 | 0 | 0 | 30000
|  | Handling etc. | QUOTED | 1 | 15000 | 0 | 15000 | 0 | 15000
1005 | 500.10+500.28 | Temporary fire connections
|  | Fireline: Connecting of Fire Line, max 5 bar |  | 0 |  | 0 | 0 | 0 | 0
|  | Each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 23 | 1500 | 36000 | -1500 | 0 | 34500
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 23032 | 30000 | 0 | -6968 | 23032
|  | Hotel | QUOTED | 1 | 27512 | 25000 | 0 | 2512 | 27512
1008 |  | Isolation
|  | Stabilizer 1+1 | QUOTED | 2 | 3000 | 6000 | 0 | 0 | 6000
1009 | 500.23 | Garbage disposal
|  | Garbage containers (4 m³) |  | 0 |  | 0 | 0 | 0 | 0
|  | Garbage container on the quay. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each time emptied, incl. disposal | QUOTED | 12 | 5000 | 100000 | 0 | -40000 | 60000
|  | Pallet with rope |  | 1 | 6000 | 0 | 0 | 6000 | 6000
|  | 2 x oily rag |  | 2 | 3500 | 0 | 0 | 7000 | 7000
|  | Paint cans 1 x pallet |  | 1 | 2000 | 0 | 0 | 2000 | 2000
|  | Chemicals |  | 1 | 2000 | 0 | 0 | 2000 | 2000
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL. | 0 |  | 0 | 0 | 0 | 0
1011 | 500.02 | Gangways
|  | Per installation/removal | QUOTED | 5 | 4000 | 20000 | 0 | 0 | 20000
|  | Daily hire charge: Included |  | 0 |  | 0 | 0 | 0 | 0
1012 | 500.09 | Cooling water for auxilliary Engines
|  | Connection/disconnection, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Supply of Cooling water SW/maintenance, |  | 0 |  | 0 | 0 | 0 | 0
|  | per day | QUOTED | 23 | 1500 | 36000 | -1500 | 0 | 34500
1013 | 500.26 | Water supply
|  | Connection/disconnection of hose, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Supply of fresh water per m³ | QUOTED | 963 | 45 | 27000 | 9000 | 7335 | 43335
1014 | 500.16+500.18 | Grey water disposal
|  | Sewage connection/disconnection, each | QUOTED | 1 | 4000 | 0 | 4000 | 0 | 4000
|  | Disposal per m³ - per 4/4-23 | QUOTED | 28 | 95 | 0 | 2660 | 0 | 2660
|  | Possible use of mud truck, each hour - per 4/4-23 | QUOTED | 11 | 1150 | 0 | 12650 | 0 | 12650
1015 | 500.24 | Oily water disposal
|  | Mudtruck per hour - 23+24/3-23 | QUOTED | 30 | 1150 | 34500 | 0 | 0 | 34500
|  | Based on normal working hours |  | 0 |  | 0 | 0 | 0 | 0
|  | Disposal of oily water per m³ - per 23/3-23 | QUOTED | 33 | 1200 | 39600 | 0 | 0 | 39600
|  | Disposal of oily water per m³ - per 24/3-23 | QUOTED | 18 | 1200 | 21600 | 0 | 0 | 21600
|  | Mudtruck per hour - 27/3-23 | QUOTED | 25 | 1150 | 28750 | 0 | 0 | 28750
|  | Disposal of oily water per m³ - per 27/3-23 | QUOTED | 64 | 1200 | 76800 | 0 | 0 | 76800
|  | Disposal of oily water per m³ - per 30/3-23 | QUOTED | 119 | 1200 | 36000 | 106800 | 0 | 142800
|  | Mudtruck per hour - 30/3-23 | QUOTED | 50 | 1150 | 11500 | 46000 | 0 | 57500
|  | Disposal of oily water per m³ - per 31/3-23 | QUOTED | 18 | 1200 | 0 | 21600 | 0 | 21600
|  | Mudtruck per hour - 31/3-23 | QUOTED | 8 | 1150 | 0 | 9200 | 0 | 9200
|  | Disposal of oily water per m³ - per 11/4-23 | QUOTED | 20 | 1200 | 0 | 23400 | 0 | 23400
|  | Mudtruck per hour - 11/4-23 | QUOTED | 11 | 1150 | 0 | 12650 | 0 | 12650
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Empty void space 8+10: |  | 0 |  | 0 | 0 | 0 | 0
|  | Disposal of oily water per m³ - per 12/4-23 | QUOTED | 20 | 1200 | 0 | 24000 | 0 | 24000
|  | Mudtruck per hour - 12/4-23 | QUOTED | 16 | 1150 | 0 | 18400 | 0 | 18400
1016 |  | Internet Connection
|  | Internet Connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 23 | 350 | 8400 | -350 | 0 | 8050
1018 | 500.11 | Gas free certificates
|  | For initial visit - Gasfree certificate | QUOTED | 1 | 3500 | 3500 | 0 | 0 | 3500
1019 | 200.01.2 | Movement of vessel, See item 500.22
|  | Movement of vessel, See item 500.22 | INFO | 0 |  | 0 | 0 | 0 | 0
1020 | 300.01 | Paint Specification
|  | Painting done according to paint specification |  | 0 |  | 0 | 0 | 0 | 0
|  | and agreement. | INFO | 0 |  | 0 | 0 | 0 | 0
1022 | 500.04 | Bottom plugs
|  | Price pr. plug off and on | QUOTED | 12 | 200 | 2400 | 0 | 0 | 2400
|  | Vacum test per plug | QUOTED | 12 | 200 | 2400 | 0 | 0 | 2400
|  | Emptying of heeling tank by pump |  | 1 | 6000 | 6000 | 0 | 0 | 6000
|  | 2 pcs. plugs in rudder |  | 2 | 300 | 600 | 0 | 0 | 600
1031 | 500.22 | Movement of vessel
|  | A. Tugs for movement of vessel |  | 0 |  | 0 | 0 | 0 | 0
|  | B. Line handlers for movement of vessel |  | 0 |  | 0 | 0 | 0 | 0
|  | C. Pilot for movement of vessel |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Tugboat, pilotassistance and line handlers: |  | 0 |  | 0 | 0 | 0 | 0
|  | As per account according to valid harbour tariffs | VIA AGENT | 0 |  | 0 | 0 | 0 | 0
1032 | 500.27 | Cherry picker
|  | Rental each cherry picker per day | QUOTED | 1 | 3500 | 3500 | 0 | 0 | 3500
|  | Excl. possible driver |  | 0 |  | 0 | 0 | 0 | 0
|  | Rental per normal day including driver | CANCELLED | 0 |  | 0 | 0 | 0 | 0
|  | (if needed) |  | 0 |  | 0 | 0 | 0 | 0
|  | Rental of scissorlift, each per day | CANCELLED | 0 |  | 0 | 0 | 0 | 0
|  | Excl. driver |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Driver based on normal working hours |  | 0 |  | 0 | 0 | 0 | 0
1033 | 500.29 | Man hole covers
|  | Per manhole | BY CREW | 0 |  | 0 | 0 | 0 | 0
|  | Based on MAX size 600x800mm |  | 0 |  | 0 | 0 | 0 | 0
|  | Renew gasket, each | N/A | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Renovation of manhole studs: |  | 0 |  | 0 | 0 | 0 | 0
|  | By turning out, min. 5 pcs. per manhole, each | CANCELLED | 0 |  | 0 | 0 | 0 | 0
|  | By drilling out, min. 5 pcs. per manhole, each | CANCELLED | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Protection on opened manhole, per manhole |  | 0 |  | 0 | 0 | 0 | 0
|  | Installation of protection bars around manhole, |  | 0 |  | 0 | 0 | 0 | 0
|  | per location | CANCELLED | 0 |  | 0 | 0 | 0 | 0
|  | Supply of protection covers | CANCELLED | 0 |  | 0 | 0 | 0 | 0
1034 | 500.30 | Watch keeping
|  | To be agreed | INFO | 0 |  | 0 | 0 | 0 | 0
1035 | 500.32 | Wharfage fee
|  | Free of charge when yard works in progress |  | 0 |  | 0 | 0 | 0 | 0
|  | Subject to unsold capacity |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Rental of berth after drydocking |  | 1 | 112500 | 0 | 112500 | 0 | 112500
1036 | 500.33 | Hull preparation
|  | Painting of bottom area with spot blast and |  | 0 |  | 0 | 0 | 0 | 0
|  | silicone paint |  | 0 |  | 0 | 0 | 0 | 0
|  | Flat bottom area, 3.055 m²: |  | 0 |  | 0 | 0 | 0 | 0
|  | Hp wash with 500 bar, each m² | QUOTED | 3055 | 22 | 67210 | 0 | 0 | 67210
|  | Mechanical cleaning min. 0,25 m²/spot, each m² | QUOTED | 153 | 110 | 16803 | 0 | 0 | 16803
|  | Wash down with FW, each m² | QUOTED | 3055 | 3.75 | 11456 | 0 | 0 | 11456
|  | Tu coat, min. 0,25 m²/spot, Hempadur Quattro, |  | 0 |  | 0 | 0 | 0 | 0
|  | done with roll/brush, each m² | QUOTED | 306 | 23 | 7027 | 0 | 0 | 7027
|  | Tu coat, min. 0,25 m²/spot, Hempadur Tiecoat, |  | 0 |  | 0 | 0 | 0 | 0
|  | done with roll/brush, each m² | QUOTED | 306 | 23 | 7027 | 0 | 0 | 7027
|  | Full coat 100 µm - HEMPASIL NEXUS, II | QUOTED | 3055 | 14 | 42770 | 0 | 0 | 42770
|  | Full coat- HEMPASIL NEXUS,X-Tend | QUOTED | 3055 | 14 | 42770 | 0 | 0 | 42770
|  | Full coat - HEMPAGUARD X7 | QUOTED | 3055 | 14 | 42770 | 0 | 0 | 42770
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Lower Vertical bottom area, 2.838 m²: |  | 0 |  | 0 | 0 | 0 | 0
|  | Hp wash with 500 bar, each m² | QUOTED | 2838 | 24 | 68112 | 0 | 0 | 68112
|  | Mechanical cleaning min. 0,25 m²/spot, each m² | QUOTED | 142 | 119 | 16886 | 0 | 0 | 16886
|  | Wash down with FW, each m² | QUOTED | 2838 | 4 | 11352 | 0 | 0 | 11352
|  | Tu coat, min. 0,25 m²/spot, Hempadur Quattro, |  | 0 |  | 0 | 0 | 0 | 0
|  | done with roll/brush, each m² | QUOTED | 284 | 30.5 | 8656 | 0 | 0 | 8656
|  | Tu coat, min. 0,25 m²/spot, Hempadur Tiecoat, |  | 0 |  | 0 | 0 | 0 | 0
|  | done with roll/brush, each m² | QUOTED | 284 | 30.5 | 8656 | 0 | 0 | 8656
|  | Full coat 100 µm - Hempe´s NEXUS, II | QUOTED | 2838 | 21 | 59598 | 0 | 0 | 59598
|  | Full coat- HEMPASIL NEXUS,X-Tend | QUOTED | 2838 | 21 | 59598 | 0 | 0 | 59598
|  | Full coat - HEMPAGUARD X7 | QUOTED | 2838 | 21 | 59598 | 0 | 0 | 59598
|  | Marking up water line per meter | QUOTED | 492 | 12.75 | 6273 | 0 | 0 | 6273
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Upper Vertical Side bottom area, 1.967 m²: |  | 0 |  | 0 | 0 | 0 | 0
|  | Hp wash with 500 bar, each m² | QUOTED | 1967 | 24 | 47208 | 0 | 0 | 47208
|  | Mechanical cleaning min. 0,25 m²/spot, each m² | QUOTED | 98 | 119 | 11704 | 0 | 0 | 11704
|  | Wash down with FW, each m² | QUOTED | 1967 | 4 | 7868 | 0 | 0 | 7868
|  | Tu coat, min. 0,25 m²/spot, Hempadur Quattro, |  | 0 |  | 0 | 0 | 0 | 0
|  | done with roll/brush, each m² | QUOTED | 197 | 30.5 | 5999 | 0 | 0 | 5999
|  | Tu coat, min. 0,25 m²/spot, Hempadur Tiecoat, |  | 0 |  | 0 | 0 | 0 | 0
|  | done with roll/brush, each m² | QUOTED | 197 | 30.5 | 5999 | 0 | 0 | 5999
|  | FC coat | QUOTED | 1967 | 21 | 41307 | 0 | 0 | 41307
|  | Marking up line per meter | QUOTED | 492 | 12.75 | 6273 | 0 | 0 | 6273
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Stabilzator stb + ps - only cleaning | QUOTED | 1 | 31200 | 31200 | 0 | 0 | 31200
|  | Thruster, each | QUOTED | 2 | 6500 | 13000 | 0 | 0 | 13000
|  | Cleaning and painting of bilge keels as lower |  | 0 |  | 0 | 0 | 0 | 0
|  | vertical bottom area | CANCELLED | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Additional costs for silicone treatment: |  | 0 |  | 0 | 0 | 0 | 0
|  | Additional cleaning of dry dock for painting |  | 0 |  | 0 | 0 | 0 | 0
|  | with Silicone paint | QUOTED | 1 | 150000 | 150000 | 0 | 0 | 150000
|  | Destroyed paint hoses due to silicone paint | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 15000
|  | Covering of upper vertical side bottom for |  | 0 |  | 0 | 0 | 0 | 0
|  | silicone painting | QUOTED | 1 | 42778 | 42778 | 0 | 0 | 42778
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Covering of: |  | 0 |  | 0 | 0 | 0 | 0
|  | Anodes and sensors, each | QUOTED | 68 | 23 | 1564 | 0 | 0 | 1564
|  | Propellers, each | QUOTED | 4 | 638 | 2552 | 0 | 0 | 2552
|  | Drainplugs fitted/removed, each | QUOTED | 38 | 148.5 | 5643 | 0 | 0 | 5643
|  | ICCP anodes, each | QUOTED | 4 | 1018 | 0 | 0 | 4072 | 4072
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Painting - Diver stribes and markings |  | 0 |  | 0 | 0 | 0 | 0
|  | Painting existing Cargo and plimsol, thruster |  | 0 |  | 0 | 0 | 0 | 0
|  | and bulp markingsmarks | QUOTED | 1 | 6294 | 6294 | 0 | 0 | 6294
|  | Markings for in water survey to be painted, |  | 0 |  | 0 | 0 | 0 | 0
|  | special tape for silicone paint | QUOTED | 1 | 23894 | 23894 | 0 | 0 | 23894
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Painting of Sea Chests |  | 0 |  | 0 | 0 | 0 | 0
|  | Sea chests opened, cleaned and painted, |  | 0 |  | 0 | 0 | 0 | 0
|  | minimum 1 m³/seachest: |  | 0 |  | 0 | 0 | 0 | 0
|  | 2 pcs. x 13,4 m³ | QUOTED | 27 | 1529 | 40977 | 0 | 0 | 40977
|  | 1 pc. 20,6 m³ | QUOTED | 21 | 957 | 19714 | 0 | 0 | 19714
|  | 1 pc. 20,2 m³ | QUOTED | 20 | 957 | 19331 | 0 | 0 | 19331
|  | 1 pc. 51,4 m³ | QUOTED | 51 | 765 | 39321 | 0 | 0 | 39321
|  | Based on max 1 m³ disposal per sea chest |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Covering of bottom area for Silicon painting |  | 0 |  | 0 | 0 | 0 | 0
|  | Covering of vessel bottom by scaffoldings and |  | 0 |  | 0 | 0 | 0 | 0
|  | canvas for painting vessel bottom with Silicon |  | 0 |  | 0 | 0 | 0 | 0
|  | paint: |  | 0 |  | 0 | 0 | 0 | 0
|  | Covering of vessels bottom by scaffoldings and |  | 0 |  | 0 | 0 | 0 | 0
|  | canvas | NET PRICE | 1 | 2018311 | 2018311 | 0 | 0 | 2018311
|  | Mobilization and demobilization for heating | NET PRICE | 1 | 284222 | 284222 | 0 | 0 | 284222
|  | Heating excl. delivering of fuel for heating |  | 0 |  | 0 | 0 | 0 | 0
|  | Based on 10 pcs. of 185 KW heat blowers in |  | 0 |  | 0 | 0 | 0 | 0
|  | 7 days | NET PRICE | 1 | 250000 | 250000 | 0 | 0 | 250000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | The vessel to deliver DO fuel for heaters and do |  | 0 |  | 0 | 0 | 0 | 0
|  | the DO tank filling |  | 0 |  | 0 | 0 | 0 | 0
|  | Yard assistance to vessel with the DO tank filling | NET PRICE | 1 | 31400 | 31400 | 0 | 0 | 31400
1039 | 1121.01 | Hatch Coamings - shore connection room
|  | One new bolted hatch, WxD 2200 x 2500 mm, |  | 0 |  | 0 | 0 | 0 | 0
|  | to be fabricated and installed between Deck 3 |  | 0 |  | 0 | 0 | 0 | 0
|  | and Shore connection room, according to |  | 0 |  | 0 | 0 | 0 | 0
|  | drawing from owner. |  | 0 |  | 0 | 0 | 0 | 0
|  | Insulation to be removed and refitted for access |  | 0 |  | 0 | 0 | 0 | 0
|  | to new hatch. |  | 0 |  | 0 | 0 | 0 | 0
|  | Fabricating and installation of new hatch. | QUOTED | 1 | 280000 | 280000 | 0 | 0 | 280000
|  | Based on work done at Fayard |  | 0 |  | 0 | 0 | 0 | 0
1040 | 1302.01 | Mooring bollard - Auto mooring
|  | On Auto mooring bollards (3 pcs.) SB, the top |  | 0 |  | 0 | 0 | 0 | 0
|  | plate to be cut down in diameter to approx. |  | 0 |  | 0 | 0 | 0 | 0
|  | 5 mm from welding seam. | QUOTED | 1 | 31335 | 31335 | 0 | 0 | 31335
|  | Paint repair | QUOTED | 1 | 5500 | 5500 | 0 | 0 | 5500
1041 | 3320.01 | Shaft Generator renewal
|  | Both Shaft Generators PS and SB side to be |  | 0 |  | 0 | 0 | 0 | 0
|  | renewed according to spec. - only PS | QUOTED | 1 | 1284750 | 1284750 | 0 | 0 | 1284750
1042 | 3320.02 | Shaft Generator pre-check
|  | New Shaft Generators to be checked in advance |  | 0 |  | 0 | 0 | 0 | 0
|  | before mounting, in total 3 pcs: |  | 0 |  | 0 | 0 | 0 | 0
|  | Assistance to owners specialist from Leroy Somer |  | 0 |  | 0 | 0 | 0 | 0
|  | for checking the new Shaft Generators before |  | 0 |  | 0 | 0 | 0 | 0
|  | mounting, in total 3 pcs. of generators: |  | 0 |  | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | QUOTED | 4 | 8500 | 34000 | 0 | 0 | 34000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Shaft Generators to be stored and mounted |  | 0 |  | 0 | 0 | 0 | 0
|  | with power on electrical heating resistor |  | 0 |  | 0 | 0 | 0 | 0
|  | according to instruction from owners specialist. | QUOTED | 1 | 9950 | 9950 | 0 | 0 | 9950
|  | Power consumption according to KWH counter | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 15000
1043 | 3338.01 | Ship side pipe outlets cleaning
|  | 80 pcs. of ship side pipe outlets (47 scupper |  | 0 |  | 0 | 0 | 0 | 0
|  | outlets and 33 ship side valves) to be inspected |  | 0 |  | 0 | 0 | 0 | 0
|  | and cleaned for hard marine fouling by scraping, |  | 0 |  | 0 | 0 | 0 | 0
|  | pipes to be coated internally the hole way to |  | 0 |  | 0 | 0 | 0 | 0
|  | the valves with 2 coats of paint | CANCELLED | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Inspection, cherry picker, cleaning/painting of |  | 0 |  | 0 | 0 | 0 | 0
|  | 4 pcs. outlets | QUOTED | 1 | 24000 | 24000 | 0 | 0 | 24000
1044 | 3435.01 | Dumping condenser - stop valve
|  | Delivering and installation of 1 pcs. of DN 200 mm |  | 0 |  | 0 | 0 | 0 | 0
|  | seat stop valve with mechanical remute operation |  | 0 |  | 0 | 0 | 0 | 0
|  | on each steam inlet line. (total 2 pcs. of valves) | QUOTED | 1 | 185200 | 185200 | 0 | 0 | 185200
|  | Delivering time on DN 200 mm seat stop valve, |  | 0 |  | 0 | 0 | 0 | 0
|  | 4 weeks. |  | 0 |  | 0 | 0 | 0 | 0
1045 | 3435.02 | Hot well - recoat.
|  | 2 pcs. of Hotwells to be emptied, cleaned and |  | 0 |  | 0 | 0 | 0 | 0
|  | recoated. Size of Hotwell tanks approx. |  | 0 |  | 0 | 0 | 0 | 0
|  | WxBxH 2,5x2,0x1,0 meter (5 m³), each: |  | 0 |  | 0 | 0 | 0 | 0
|  | Hotwell tank to be opened washed down with |  | 0 |  | 0 | 0 | 0 | 0
|  | fresh water and emptied by sludge truck, |  | 0 |  | 0 | 0 | 0 | 0
|  | for inspection of tank. Each tank | QUOTED | 2 | 25100 | 50200 | 0 | 0 | 50200
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Repair of coating in Hot well tanks to be priced |  | 0 |  | 0 | 0 | 0 | 0
|  | after wash down and inspection of tanks |  | 0 |  | 0 | 0 | 0 | 0
|  | Prices based on empty tanks. |  | 0 |  | 0 | 0 | 0 | 0
|  | Price for cleaning and repair of coating Hotwell |  | 0 |  | 0 | 0 | 0 | 0
|  | tank as on Humbria Seaways. Each Tank | QUOTED | 2 | 60350 | 120700 | 0 | 0 | 120700
1046 | 3801.01 | Propeller - polish
|  | Main propeller blades to be normal polished, |  | 0 |  | 0 | 0 | 0 | 0
|  | each blade | QUOTED | 8 | 8200 | 65600 | 0 | 0 | 65600
|  | Edges and blade roots to be checked by Dye - |  | 0 |  | 0 | 0 | 0 | 0
|  | check. Each | QUOTED | 8 | 4100 | 32800 | 0 | 0 | 32800
|  | Dye-check of bolts, each | QUOTED | 64 | 300 | 19200 | 0 | 0 | 19200
|  | Based on work done after propeller blades are |  | 0 |  | 0 | 0 | 0 | 0
|  | dismantled. |  | 0 |  | 0 | 0 | 0 | 0
1047 | 3802.01 | Tail shaft wear down
|  | Staging by rope guards, each | QUOTED | 2 | 11200 | 22400 | 0 | 0 | 22400
|  | Dismantling of rope guards, each | QUOTED | 2 | 46900 | 93800 | 0 | 0 | 93800
|  | Draining and refilling of oil in measure camber, |  | 0 |  | 0 | 0 | 0 | 0
|  | each | QUOTED | 2 | 4450 | 8900 | 0 | 0 | 8900
|  | Measuring of wear down using vessels poker |  | 0 |  | 0 | 0 | 0 | 0
|  | guage, each time | OWNER | 0 |  | 0 | 0 | 0 | 0
|  | Disposal of oil, each m³ | QUOTED | 14 | 1200 | 16800 | 0 | 0 | 16800
1049 | 3805.01 | Propeller shaft withdrawal
|  | Scaffolding by rudder blade for dismantling |  | 0 |  | 0 | 0 | 0 | 0
|  | and fitting of rudder blade. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each rudder (cherry picker) | QUOTED | 2 | 22300 | 44600 | 0 | 0 | 44600
|  | Cut-out and re-weld access plates (2 pcs.) on |  | 0 |  | 0 | 0 | 0 | 0
|  | rudder blade for dismantling and refitting of |  | 0 |  | 0 | 0 | 0 | 0
|  | rudder stock nut. Each rudder blade | QUOTED | 2 | 55600 | 111200 | 0 | 0 | 111200
|  | Dismantling and refitting of rudder blade. |  | 0 |  | 0 | 0 | 0 | 0
|  | Weigh: 26882 kg. Each rudder blade: | QUOTED | 2 | 96500 | 193000 | 0 | 0 | 193000
|  | Welding up pad eyes for dismantling and |  | 0 |  | 0 | 0 | 0 | 0
|  | refitting of rudder blade. Each pad eye | QUOTED | 24 | 11200 | 268800 | 0 | 0 | 268800
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Draining of sterntupe oil done by crew, refilling |  | 0 |  | 0 | 0 | 0 | 0
|  | by crew. Each Sterntupe | QUOTED | 2 | 17800 | 35600 | 0 | 0 | 35600
|  | Disposal of oil. Each m³ - see job 1047 |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Dismantling and refitting of Promas hubcap. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each Promas hubcap | N/A | 0 |  | 0 | 0 | 0 | 0
|  | Dismantling and refitting of propeller shaft SKF |  | 0 |  | 0 | 0 | 0 | 0
|  | coupling. Each coupling | QUOTED | 2 | 62500 | 125000 | 0 | 0 | 125000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Dismantling and refitting of propeller blades: |  | 0 |  | 0 | 0 | 0 | 0
|  | Each propeller blade | QUOTED | 8 | 18300 | 146400 | 0 | 0 | 146400
|  | Hydraulic tools for propeller blade | QUOTED | 2 | 27800 | 55600 | 0 | 0 | 55600
|  | Transport of propeller blades from dry dock to |  | 0 |  | 0 | 0 | 0 | 0
|  | yard work shop and return to dry dock. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each propeller blade | QUOTED | 8 | 2950 | 23600 | 0 | 0 | 23600
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Withdrawal of propeller shaft. Each shaft | QUOTED | 2 | 214000 | 428000 | 0 | 0 | 428000
|  | Cleaning and NDT by magnaflux of area by hdr |  | 0 |  | 0 | 0 | 0 | 0
|  | coupling and flange coupling. | QUOTED | 2 | 11500 | 23000 | 0 | 0 | 23000
|  | Propeller shaft transported to work shop and |  | 0 |  | 0 | 0 | 0 | 0
|  | back. Each shaft | QUOTED | 2 | 55600 | 111200 | 0 | 0 | 111200
|  | Dismantling of inner and outer stern tupe seal, |  | 0 |  | 0 | 0 | 0 | 0
|  | bringing to yard work shop, dismantling in work |  | 0 |  | 0 | 0 | 0 | 0
|  | shop, cleaning and re-asampling with owners |  | 0 |  | 0 | 0 | 0 | 0
|  | delivered sealings. Each Stern tube seal | QUOTED | 4 | 47500 | 190000 | 0 | 0 | 190000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Possible repairs and/or machining of stern tupe |  | 0 |  | 0 | 0 | 0 | 0
|  | seals to be agreed and priced after agreement |  | 0 |  | 0 | 0 | 0 | 0
|  | of work scope. | QUOTED | 4 | 35000 | 140000 | 0 | 0 | 140000
|  | Cleaning of stern tubes. Each stern tube: | QUOTED | 4 | 27800 | 111200 | 0 | 0 | 111200
|  | Measuring of stern tube bearings. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each stern tupe, each time | N/A | 0 |  | 0 | 0 | 0 | 0
|  | Assistance to owners specialist with alignment |  | 0 |  | 0 | 0 | 0 | 0
|  | control of stern tupes. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each person per 12 hours shift - see job 1061 |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Standby time | N/A | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Possible change of stern tube bearings to be |  | 0 |  | 0 | 0 | 0 | 0
|  | priced after inspection and measuring of stern |  | 0 |  | 0 | 0 | 0 | 0
|  | tubes. | QUOTED | 2 | 40000 | 80000 | 0 | 0 | 80000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Specialist for, sterntube sealings, propeller shaft |  | 0 |  | 0 | 0 | 0 | 0
|  | withdraw, alignment control, to be ordered and |  | 0 |  | 0 | 0 | 0 | 0
|  | paid directly by owner |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Machining and delivery of new guide pins, |  | 0 |  | 0 | 0 | 0 | 0
|  | 8 pcs. - already paid on Aura | CANCELLED | 0 |  | 35000 | 0 | -35000 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Dismantling of cover plates and opening of |  | 0 |  | 0 | 0 | 0 | 0
|  | covers to midt bearings, 4 pcs. | N/A | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | UT - MPI rudder and cover plates | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Transport of sterntube bearings to Frederikshavn | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Ass. from Vestergaard Marine, measure/machining |  | 0 |  | 0 | 0 | 0 | 0
|  | and possible transport of aft sterntube bearings. | NET PRICE | 1 | 171066 | 150000 | 0 | 21066 | 171066
1050 | 3805.02 | Intermediate bearing inspection/renewal
|  | Following Intermediate bearings to be inspected: |  | 0 |  | 0 | 0 | 0 | 0
|  | PS: bearing no.: 1 and 2. |  | 0 |  | 0 | 0 | 0 | 0
|  | SB: Bearing no.: 1 and 2 and 3. |  | 0 |  | 0 | 0 | 0 | 0
|  | Bearings to be opened up and inspected by LR, |  | 0 |  | 0 | 0 | 0 | 0
|  | Wärtsila and owner, both upper and lower |  | 0 |  | 0 | 0 | 0 | 0
|  | bearing shell to be inspected. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each bearing: | QUOTED | 5 | 14500 | 72500 | 0 | 0 | 72500
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Supply of distance rings, 6 pcs. | N/A | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Measurement/clearness/alignment check | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning, further assistance and machining | QUOTED | 1 | 80000 | 50000 | 30000 | 0 | 80000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Possible repair/change of bearing shells or repairs |  | 0 |  | 0 | 0 | 0 | 0
|  | to be priced after agreement of work scope | N/A | 0 |  | 0 | 0 | 0 | 0
1052 | 3811.02 | Bow thruster grid
|  | Bow thruster grids to be examined for cracks |  | 0 |  | 0 | 0 | 0 | 0
|  | when dry docked. | QUOTED | 1 | 6200 | 6200 | 0 | 0 | 6200
|  | Possible repairs to be priced after agreement of |  | 0 |  | 0 | 0 | 0 | 0
|  | work scope | QUOTED | 1 | 156000 | 156000 | 0 | 0 | 156000
1055 |  | Sea chests to be opened and cleaned for
|  | inspection. |  | 0 |  | 0 | 0 | 0 | 0
|  | HP wash sea chest (20,6+13,4+20,2+13,4+ |  | 0 |  | 0 | 0 | 0 | 0
|  | 51,4m³) | QUOTED | 1 | 31941 | 31941 | 0 | 0 | 31941
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Securing of bolts |  | 1 | 5000 | 0 | 5000 | 0 | 5000
1056 |  | Anchors to be painted.
|  | Anchors to be painted. | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 20000
1059 |  | Temperary closing of scrupper outlet for
|  | painting | QUOTED | 18 | 800 | 14400 | 0 | 0 | 14400
1060 |  | Dis- and reinstallation of sensors and pipes
|  | in stern tubes | QUOTED | 1 | 100000 | 100000 | 0 | 0 | 100000
|  | Incl. pressure test |  | 0 |  | 0 | 0 | 0 | 0
1061 |  | Ass. to Wärtsilä/Munkholm related to
|  | measurements in stern tubes |  | 0 |  | 0 | 0 | 0 | 0
|  | Scaffolding, tent, heat and steel plates + pipes | QUOTED | 1 | 90000 | 90000 | 0 | 0 | 90000
1065 |  | Cleaning of stern tubes.
|  | Mudtruck each hour | QUOTED | 20 | 1150 | 23000 | 0 | 0 | 23000
|  | Manpower | QUOTED | 1 | 41000 | 0 | 41000 | 0 | 41000
|  | Disposal per m³ | QUOTED | 4 | 1200 | 0 | 4800 | 0 | 4800
1067 |  | Propeller shafts to be rolled for check of
|  | alignment. | QUOTED | 1 | 45500 | 60000 | 0 | -14500 | 45500
1068 |  | Pressure testing of rudder nuts
|  | Pressure testing of rudder nuts and cleaning | QUOTED | 2 | 15000 | 15000 | 15000 | 0 | 30000
1069 |  | Painting of topside as agreed on inspection.
|  | Wash down with FW, based on 10.500 m² | QUOTED | 10500 | 4 | 42000 | 0 | 0 | 42000
|  | Mechanical cleaning min. 0,25 m²/spot basis 4% | QUOTED | 420 | 119 | 49980 | 0 | 0 | 49980
|  | Emulsion cleaning min. 0,25 m²/spot basis 4% | QUOTED | 420 | 27.5 | 11550 | 0 | 0 | 11550
|  | 1 TU coat with brush/roller, basis 4% | QUOTED | 420 | 46 | 19320 | 0 | 0 | 19320
|  | 1 TU coat with brush/roller, basis 4% | QUOTED | 420 | 46 | 19320 | 0 | 0 | 19320
|  | 1 TU coat with brush/roller, basis 4% | QUOTED | 420 | 46 | 19320 | 0 | 0 | 19320
1070 |  | Delivery and installation of wibercon for
|  | alignment of shaft generators | QUOTED | 1 | 85000 | 85000 | 0 | 0 | 85000
1071 |  | Installation of 2 pcs scupper in front on deck
|  | 7 PS+STB | QUOTED | 2 | 38000 | 76000 | 0 | 0 | 76000
1074 |  | Opening/cleaning and new gaskets in
|  | manholdes to mittle bearings in stern tubes | BY CREW | 0 |  | 0 | 0 | 0 | 0
1075 |  | Jackup test for shaft intremediate bearings
|  | Jackup test for shaft intremediate bearings | QUOTED | 1 | 150000 | 150000 | 0 | 0 | 150000
1076 |  | Cooling system on sterntube
|  | Cooling system on sterntube | QUOTED | 1 | 267810 | 267810 | 0 | 0 | 267810
|  | Opening of 4 pcs. oil pumps , visual inspection | N/A | 0 |  | 9802 | 0 | -9802 | 0
1077 |  | New ceilings in way of life bats on deck 7
|  | Ceiling panels above lifeboats: |  | 0 |  | 0 | 0 | 0 | 0
|  | Change of panels above lifeboats in PS and Stb |  | 0 |  | 0 | 0 | 0 | 0
|  | side according to below: | QUOTED | 1 | 1410000 | 1410000 | 0 | 0 | 1410000
|  | Demount ceiling plates and sub-structure, |  | 0 |  | 0 | 0 | 0 | 0
|  | Delivery and installation new ceiling panels. |  | 0 |  | 0 | 0 | 0 | 0
|  | Made with 40x275x40mm u-profile panels in |  | 0 |  | 0 | 0 | 0 | 0
|  | 1,5mm galvanized plate, mounted on top of |  | 0 |  | 0 | 0 | 0 | 0
|  | existing T-beams so no substructure is needed. |  | 0 |  | 0 | 0 | 0 | 0
|  | A Z-profile will be mounted below panels around |  | 0 |  | 0 | 0 | 0 | 0
|  | T-beams to fixate panels, total amount of 14 |  | 0 |  | 0 | 0 | 0 | 0
|  | sections in PS and 14 sections in STBD side, |  | 0 |  | 0 | 0 | 0 | 0
|  | each section is 2500x4200mm. |  | 0 |  | 0 | 0 | 0 | 0
|  | Measuring up for pre-fabricating of panels |  | 0 |  | 0 | 0 | 0 | 0
|  | Scaffoldings for access |  | 0 |  | 0 | 0 | 0 | 0
|  | Electrical demount and remount of cables and |  | 0 |  | 0 | 0 | 0 | 0
|  | ilumination for access |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning and painting of new panels |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning and painting of T-bars and spot point |  | 0 |  | 0 | 0 | 0 | 0
|  | from old panel supports |  | 0 |  | 0 | 0 | 0 | 0
|  | Price is based on: Lifeboats and life rafts are |  | 0 |  | 0 | 0 | 0 | 0
|  | removed, PS and Stb side to be done and panels |  | 0 |  | 0 | 0 | 0 | 0
|  | can be prefabricated |  | 0 |  | 0 | 0 | 0 | 0
1079 |  | Renewal of window/glass in crew mess
|  | forward PS. |  | 1 | 11050 | 11050 | 0 | 0 | 11050
|  | Glass Owners delivery |  | 0 |  | 0 | 0 | 0 | 0
1080 |  | Repair of leaking pipe above 2 cabins on
|  | deck 10 | QUOTED | 1 | 73850 | 0 | 70000 | 3850 | 73850
1081 |  | Dis-/remounting and overhaul of 3 pcs.
|  | steam valves |  | 1 | 31500 | 31500 | 0 | 0 | 31500
|  | Pressuretest 3 pcs. valves |  | 1 | 4950 | 4950 | 0 | 0 | 4950
|  | Machining |  | 1 | 12000 | 12000 | 0 | 0 | 12000
|  | Insulation |  | 1 | 7375 | 0 | 7375 | 0 | 7375
1082 |  | Installing of valve on pipe for green filter
|  | f/bow thrusters |  | 2 | 9000 | 0 | 18000 | 0 | 18000
1083 |  | Modification of anchor chain stopper
|  | Modification of anchor chain stopper |  | 2 | 8500 | 17000 | 0 | 0 | 17000
1084 |  | Overhaul of fan for bow thruster room
|  | Overhaul of fan for bow thruster room | QUOTED | 1 | 35000 | 0 | 35000 | 0 | 35000
|  | Staging |  | 1 | 12000 | 0 | 0 | 12000 | 12000
1085 |  | Life boat to shore and covering
|  | Life boat to shore | QUOTED | 2 | 8500 | 17000 | 0 | 0 | 17000
|  | Covering | QUOTED | 1 | 5500 | 5500 | 0 | 0 | 5500
1086 |  | Repair of protection for scupper outlet
|  | shell plate, 4 pcs., each | QUOTED | 4 | 18000 | 72000 | 0 | 0 | 72000
|  | Possible paint repair |  | 1 | 3500 | 0 | 3500 | 0 | 3500
1087 |  | Delivery and installation of filter before
|  | sewage pumps |  | 2 | 21000 | 42000 | 0 | 0 | 42000
1088 |  | Overhaul of sea and overboard valve 6 pcs.
|  | Overhaul of sea and overboard valve 6 pcs. |  | 1 | 40500 | 40500 | 0 | 0 | 40500
|  | Additional 9 pcs. |  | 1 | 60750 | 0 | 60750 | 0 | 60750
|  | 5 pcs. remote controls repaired |  | 1 | 19650 | 0 | 19650 | 0 | 19650
|  | 3 pcs. valves cleaned for steel sand |  | 1 | 5850 | 0 | 5850 | 0 | 5850
1089 |  | Installation of 2 pcs. scupper port and stb.
|  | lifeboat | QUOTED | 2 | 38000 | 76000 | 0 | 0 | 76000
1090 |  | Repair of isolation in void space S 8
|  | Repair of isolation in void space S 8 |  | 1 | 45000 | 0 | 45000 | 0 | 45000
|  | Staging |  | 1 | 28000 | 28000 | 0 | 0 | 28000
1091 |  | Cleaning of tank top in separator room
|  | Mudtruck |  | 1 | 17250 | 17250 | 0 | 0 | 17250
|  | Disposal 2 m³ |  | 2 | 1200 | 2400 | 0 | 0 | 2400
|  | Assistance, materials |  | 1 | 16890 | 16890 | 0 | 0 | 16890
1092 |  | Cleaning of sludge tank
|  | Mudtruck |  | 1 | 8310 | 8310 | 0 | 0 | 8310
|  | Disposal 1 m³ |  | 1 | 1200 | 1200 | 0 | 0 | 1200
|  | Assistance, materials |  | 1 | 8670 | 8670 | 0 | 0 | 8670
1093 |  | Assistance to Frese (scaffolding)
|  | Assistance to Frese (scaffolding) |  | 1 | 17300 | 0 | 17300 | 0 | 17300
1094 |  | Asssistance to Global Boiler
|  | Asssistance to Global Boiler |  | 1 | 31600 | 0 | 31600 | 0 | 31600
1095 |  | Cleaning and adjustment of sprinkler nozzles
|  | below bridge wings STB + PS |  | 1 | 25000 | 0 | 25000 | 0 | 25000
|  | Lift | QUOTED | 2 | 7000 | 14000 | 0 | 0 | 14000
1096 |  | Cleaning of scrupper tank deck 7 PS+STB
|  | Manpower | QUOTED | 1 | 18700 | 0 | 18700 | 0 | 18700
|  | Mudtruck | QUOTED | 1 | 13225 | 0 | 13225 | 0 | 13225
|  | Disposal per m³ | QUOTED | 2 | 1200 | 0 | 2400 | 0 | 2400
1097 | VOR 1 | Cleaning and painting of WB tank 8
|  | Area/room as agreed |  | 0 |  | 0 | 0 | 0 | 0
|  | Wash |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning for sludge and mud |  | 0 |  | 0 | 0 | 0 | 0
|  | Mech. Cleaning min. 0,25 m²/spot |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning before painting |  | 0 |  | 0 | 0 | 0 | 0
|  | TU 2 coat |  | 0 |  | 0 | 0 | 0 | 0
|  | FC 1 coat |  | 0 |  | 0 | 0 | 0 | 0
|  | In total | VOR 1 | 1 | 75600 | 0 | 75600 | 0 | 75600
|  | Paint delivered by vessel |  | 0 |  | 0 | 0 | 0 | 0
1098 |  | Installation of Proximity and Load Sensors
|  | incl. related piping, fittings, piping in the stern |  | 0 |  | 0 | 0 | 0 | 0
|  | tubes, cabling and foundations for sensors |  | 0 |  | 0 | 0 | 0 | 0
|  | below shafts. |  | 1 | 485820 | 0 | 0 | 485820 | 485820
1099 |  | Change of cable shoes on power cable shaft
|  | generator PS |  | 1 | 15000 | 0 | 15000 | 0 | 15000
1100 |  | Food for owners sub-contractors in yards
|  | canteen. |  | 1 | 1870 | 0 | 0 | 1870 | 1870
1101 |  | MPI on main propeller shafts in way of aft
|  | bearing. |  | 0 |  | 0 | 0 | 0 | 0
1102 |  | Ass. to Wartsila for installation of vibracons
|  | below intermediate bearings. |  | 1 | 32700 | 0 | 0 | 32700 | 32700
|  | Partly incl. in job 1075 |  | 0 |  | 0 | 0 | 0 | 0
1103 |  | Cleaning of engine rooms / technical areas
|  | before departure |  | 1 | 169960 | 0 | 169960 | 0 | 169960
1104 |  | Various assistance to MacGregor
|  | Various assistance to MacGregor | QUOTED | 1 | 21250 | 0 | 25000 | -3750 | 21250
1106 |  | Change of vibration dampers on exhaust
|  | pipes PS + STB casing 6 pcs. |  | 2 | 28000 | 0 | 56000 | 0 | 56000
1107 |  | Replace of watermist sprinkler above
|  | generator aft engine room. |  | 1 | 6500 | 0 | 6500 | 0 | 6500
1108 |  | Dis- and remounting of wall panel in cabin 7-2-05 +
|  | 7-2-04 for inspection |  | 1 | 28095 | 0 | 0 | 28095 | 28095
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation |  | 1 | 20000 | 20000 | 0 | 0 | 20000
9993 |  | Discount according to agreement
|  | Discount according to agreement | 10% | 1 | -1537154 | -1424637 | -78993 | -33524 | -1537154
|  |  | DKK |  |  | 12821732 | 710942 | 472776 | 14005450 | 0