## Chapter 0
Ship name: |  | PRIMULA SEAWAYS
Case No.: |  | 231058
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-07-17 | 2023-07-20 | 2023-07-27 | 2023-08-03 | 2025-05-06 | Total
1000 |  | Sag
1001 | 200.01 - BW/HS | Drydocking
|  | A. Dock/undock and first day dues | QUOTED | 1 | 55000 | 55000 | 0 | 0 | 0 | 0 | 55000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | B. Cost for subsequent days, each day | QUOTED | 19 | 35000 | 665000 | 0 | 0 | 0 | 0 | 665000
|  | From 17/7 - 5/8 2023 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Lay by quay - 5/8 - 7/8 |  | 3 | 20000 | 40000 | 0 | 20000 | 0 | 0 | 60000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | E. Main engine crankshaft deflections, each time | QUOTED | 1 | 3920 | 3920 | 0 | 0 | 0 | 0 | 3920
1002 | BW/HS | Shore power connection
|  | Connection/disconnection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Electric power supply: 400 V, 50Hz, 1000 Amp | ON HOLD | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Maintenance per day | ON HOLD | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply of electric current, each KwH | ON HOLD |  | 3.2 | 0 | 0 | 0 | 0 | 0 | 0
1003 | BW/HS | Earth connection
|  | Earth connection | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1004 | BW/HS | Crane & Fork lift service
|  | Hourly rate for dockside cranes assistance | QUOTED | 50 | 1000 | 50000 | 0 | 0 | 0 | 0 | 50000
1005 | BW/HS | Fire Line Connection
|  | Price per connection | QUOTED | 2 | 2000 | 4000 | 0 | 0 | 0 | 0 | 4000
|  | Price per day in service | QUOTED | 40 | 350 | 14000 | 0 | 0 | 0 | 0 | 14000
1006 | BW/HS | Blocking of CO2
|  | Isolation/reconnection of CO2 plant | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1007 | BW/HS | Stock supply
|  | Stock supply | QUOTED | 1 | 100000 | 50000 | 0 | 50000 | 0 | 0 | 100000
1008 | BW/HS | Isolation
|  | Isolation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1009 | BW/HS | Garbage
|  | Garbage containers (4 m³) on the quay. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each time emptied, incl. disposal: | QUOTED | 10 | 5000 | 50000 | 0 | 0 | 0 | 0 | 50000
1010 | BW/HS | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1011 | BW/HS | Gangway
|  | Per installation/removal | QUOTED | 1 | 4000 | 8000 | 0 | -4000 | 0 | 0 | 4000
1012 | BW/HS | Cooling water connection
|  | Connection/disconnection, each connection | QUOTED | 4 | 2000 | 8000 | 0 | 0 | 0 | 0 | 8000
|  | Per day in service | QUOTED | 80 | 350 | 28000 | 0 | 0 | 0 | 0 | 28000
1013 | BW/HS | Fresh water connection
|  | Connection/disconnection of hose | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000
|  | Fresh water per m³ | QUOTED | 100 | 40 | 4000 | 0 | 0 | 0 | 0 | 4000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical water for boilers per m³, Estimated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | price per m³ as daily price will need to be aquired |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | from supplier after information of total amount |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of m³ needed is known. Each m³ |  | 0 | 4008 | 0 | 0 | 0 | 0 | 0 | 0
1014 | BW/HS | Sewage/Black water connection
|  | Grey + Black water disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Connection/disconnection, each | QUOTED | 2 | 4000 | 8000 | 0 | 0 | 0 | 0 | 8000
|  | Grey/Black water discharged and disposed per m³ | QUOTED | 100 | 95 | 9500 | 0 | 0 | 0 | 0 | 9500
|  | Mudtruck, each normal hour | QUOTED | 64 | 950 | 60800 | 0 | 0 | 0 | 0 | 60800
1015 | BW/HS | Oily water connection
|  | Connection/disconnection | QUOTED | 1 | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000
|  | Oil/water mixture discharged and disposed per m³ | QUOTED | 25 | 1200 | 30000 | 0 | 0 | 0 | 0 | 30000
|  | Mudtruck, each normal hour | QUOTED | 15 | 950 | 14250 | 0 | 0 | 0 | 0 | 14250
1016 | BW/HS | Internet Connection
|  | Conneciton via access point | CANCELLED | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0
1017 | BW/HS | Ballast water connection
|  | Connection/disconnection of Ballastwater, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each hose | QUOTED | 2 | 2000 | 4000 | 0 | 0 | 0 | 0 | 4000
|  | Supply of sea ballast water, each m³ | QUOTED | 4200 | 8 | 33600 | 0 | 0 | 0 | 0 | 33600
|  | Further assistance when ballasting: As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1018 | BW/HS | Gas free certifikate
|  | For initial visit - Gas free certificate | QUOTED | 4 | 3000 | 12000 | 0 | 0 | 0 | 0 | 12000
|  | For subsequent visit, each | QUOTED | 4 | 3000 | 12000 | 0 | 0 | 0 | 0 | 12000
1019 | 1001.01 - BW/HS | Repair of fender list
|  | Inspection of fender list |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fender list is half pipe HR 323,9 X 14,2mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Price per meter, min 2 meter per spot | CANCELLED | 0 | 10100 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on min 2 meter per spot, free access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | inside and excl. cleaning and painting of new |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and affected areas |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Inspection incl. lift | QUOTED | 1 | 7000 | 0 | 7000 | 0 | 0 | 0 | 7000
1020 | 1001.02 - BW/HS | Corrosion prevention anodes
|  | Work order Fitting of corrosion prevention |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | anodes (owner supplied) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Change of owner supplied Alu. anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 15 (1,5 kg.), each | QUOTED | 64 | 320 | 18240 | 2240 | 0 | 0 | 0 | 20480
|  | AL 60 (6,0 kg.), each | QUOTED | 44 | 645 | 28380 | 0 | 0 | 0 | 0 | 28380
|  | AL 114 (11,4 kg.), each | QUOTED | 6 | 860 | 15480 | -10320 | 0 | 0 | 0 | 5160
|  | Incl. cherry picker, demounting of old, mounting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of new, welded type, basis min. 50 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Change of yard delivered anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 15 (1,5 kg.), each |  | 4 | 440 | 0 | 1760 | 0 | 0 | 0 | 1760
|  | AL 60 (6,0 kg.), each |  | 6 | 1135 | 0 | 6810 | 0 | 0 | 0 | 6810
1021 | 1001.04 - BW/HS | ICCP system
|  | Asisstants to Owners service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Rental of Cherry picker, each per day | CANCELLED | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Driver for cherry picker, each normal hour | CANCELLED | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each man per 12 hour day shift | CANCELLED | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change of ICCP ref. anodes, each | CANCELLED | 0 | 12430 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change of ICCP main anodes, each | CANCELLED | 0 | 22660 | 0 | 0 | 0 | 0 | 0 | 0
1022 | 1001.05 - BW/HS | Cracks in shell and longitudinal reinforcement plates
|  | Vertical welding to be cropped out and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | longitudinal welding’s (upper and lower) to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | cropped out for about 1 meter on each side of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | the vertical welding. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each place | CANCELLED | 0 | 29500 | 29500 | -29500 | 0 | 0 | 0 | 0
|  | Subject to free access for hot work and excl. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | cleaning and painting of new and affected area. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners | CANCELLED | 0 | 10000 | 10000 | -10000 | 0 | 0 | 0 | 0
1023 | 1001.08 - BW/HS | Steel indent frame 225 starboard main deck
|  | Based 1 inset 3600 x 300 x 12 mm | QUOTED | 1 | 61400 | 61400 | 0 | 0 | 0 | 0 | 61400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paintwork | QUOTED | 1 | 4550 | 4550 | 0 | 0 | 0 | 0 | 4550
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 1 | 5000 | 10000 | 0 | -5000 | 0 | 0 | 5000
1024 | 1001.09 - BW/HS | Steel indent main deck at frame 185 Portside
|  | Based 2 pcs. Shell plates 1500 x 500 x 13 and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 longitudinal 2000 x 250 x 15 mm | CANCELLED | 0 | 88100 | 88100 | -88100 | 0 | 0 | 0 | 0
|  | Based job can be done without removing/reistalling |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | hydraulic pipes for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paintwork | CANCELLED | 0 | 15600 | 15600 | -15600 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners | CANCELLED | 0 | 10000 | 10000 | -10000 | 0 | 0 | 0 | 0
1025 | 1001.10 - BW/HS | Steel indent main deck at frame 201-205 Starboard side
|  | Based 2 pcs. Shell plates 2500 x 600 x 13 and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 longitudinal 2500 x 250 x 15 mm | CANCELLED | 0 | 133850 | 133850 | 0 | -133850 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paintwork | CANCELLED | 0 | 19800 | 19800 | 0 | -19800 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 0 | 5000 | 10000 | 0 | -10000 | 0 | 0 | 0
1026 | 1001.11 - BW/HS | Antifouling anodes
|  | 6 pcs. Anodes in sea chest to be replaced. Each | QUOTED | 6 | 4937 | 29622 | 0 | 0 | 0 | 0 | 29622
|  | 1 pcs. Cu anod in seachest for emg fire pump | CANCELLED | 0 | 4937 | 4937 | 0 | -4937 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift, each per day | QUOTED | 2 | 3500 | 7000 | 0 | 0 | 0 | 0 | 7000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible opening/closing of gratings for access, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each |  | 0 | 1760 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Supports for anodes fabricated and mounted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | upper/lower seachest, 6 pcs. | QUOTED | 1 | 27100 | 162600 | -135500 | 0 | 0 | 0 | 27100
1027 | 1016.01 - PS | Bottom treatment and paint
|  | Mechanical cleaning underwater hull of existing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | silicone paint system: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom area: 2900 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Flat bottom area: 4106 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Flat bottom area: 4106 m²: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP- wash of existing silicone paint | QUOTED | 4106 | 22 | 90332 | 0 | 0 | 0 | 0 | 90332
|  | Mechanical cleaning, based 5% | QUOTED | 205 | 103 | 42292 | -21146 | 0 | 0 | 0 | 21146
|  | Hosing down with FW | QUOTED | 4106 | 3.5 | 14371 | 0 | 0 | 0 | 0 | 14371
|  | 1 x TU, based 10% | QUOTED | 411 | 11.5 | 4722 | 0 | 0 | 0 | 0 | 4722
|  | 1 x TU, based 10% (Silicone paint) | QUOTED | 411 | 23 | 9444 | 0 | 0 | 0 | 0 | 9444
|  | 1 x TU, based 10% (Silicone paint) | QUOTED | 411 | 23 | 9444 | 0 | 0 | 0 | 0 | 9444
|  | 1 x TU, based 10% (Silicone paint) | QUOTED | 411 | 23 | 9444 | 0 | 0 | 0 | 0 | 9444
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom area: 2900 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP- wash of existing silicone paint | QUOTED | 2900 | 24 | 69600 | 0 | 0 | 0 | 0 | 69600
|  | Mechanical cleaning, based 5% | QUOTED | 145 | 103 | 29870 | -14935 | 0 | 0 | 0 | 14935
|  | Hosing down with FW | QUOTED | 2900 | 3.5 | 10150 | 0 | 0 | 0 | 0 | 10150
|  | 1 x TU, based 10% | QUOTED | 290 | 15.25 | 4423 | 0 | 0 | 0 | 0 | 4423
|  | 1 x TU, based 10% (Silicone paint) | QUOTED | 290 | 30.5 | 8845 | 0 | 0 | 0 | 0 | 8845
|  | 1 x TU, based 10% (Silicone paint) | QUOTED | 290 | 30.5 | 8845 | 0 | 0 | 0 | 0 | 8845
|  | 1 x TU, based 10% (Silicone paint) | QUOTED | 290 | 30.5 | 8845 | 0 | 0 | 0 | 0 | 8845
|  | Marking up water line, 492 meter | QUOTED | 492 | 11.5 | 5658 | 0 | 0 | 0 | 0 | 5658
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Rudder area: 47 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 47 | 10.5 | 494 | 0 | 0 | 0 | 0 | 494
|  | Mechanical cleaning, min. 0,25 m² per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 9,4 m² | QUOTED | 9 | 103 | 968 | 0 | 0 | 0 | 0 | 968
|  | Wash down with FW | QUOTED | 47 | 3.5 | 165 | 0 | 0 | 0 | 0 | 165
|  | Tu 1 coat, min. 0,25 m² / spot, basis 20%, 9,4m² | QUOTED | 9 | 13.75 | 129 | 0 | 0 | 0 | 0 | 129
|  | Tu 1 coat, min. 0,25 m² / spot, basis 20%, 9,4m² | QUOTED | 9 | 13.75 | 129 | 0 | 0 | 0 | 0 | 129
|  | Full coat 100 µm | QUOTED | 47 | 19 | 893 | 0 | 0 | 0 | 0 | 893
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional costs for silicone treatment: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering of topside againast overspray | QUOTED | 1 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000
|  | Destroyed paint hoses due to silicone paint | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Vertical sides underneat the fender list and 1,8 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | meters down and thruster tunnels are to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | repainted with HEMPELS ANTIFOULING |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | GLOBIC 9000 (traditional anti fouling). |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom area for traditional antifouling: 500 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 500 | 10.5 | 5250 | 0 | 0 | 0 | 0 | 5250
|  | Mechanical cleaning, min. 0,25 m² per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 5%, 25 m² | QUOTED | 25 | 103 | 25750 | -23175 | 0 | 0 | 0 | 2575
|  | Wash down with FW | QUOTED | 500 | 3.5 | 1750 | 0 | 0 | 0 | 0 | 1750
|  | Tu 1 coat, min. 0,25 m²/spot, basis 10%, 50 m² | QUOTED | 50 | 13.75 | 3438 | -2750 | 0 | 0 | 0 | 688
|  | Tu 1 coat, min. 0,25 m²/spot, basis 10%, 50 m² | QUOTED | 50 | 13.75 | 3438 | -2750 | 0 | 0 | 0 | 688
|  | Tu 1 coat, min. 0,25 m²/spot, basis 10%, 50 m² | QUOTED | 50 | 13.75 | 3438 | -2750 | 0 | 0 | 0 | 688
|  | 1 x FC with roller | QUOTED | 500 | 21 | 3438 | 7063 | 0 | 0 | 0 | 10500
|  | Marking up line, 492 meter | QUOTED | 492 | 11.5 | 5658 | 0 | 0 | 0 | 0 | 5658
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Thruster tunnels area: 89 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 89 | 10.5 | 935 | 0 | 0 | 0 | 0 | 935
|  | Mechanical cleaning, min. 0,25 m² per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 50%, 44,5 m² | CANCELLED | 45 | 103 | 4584 | 0 | 0 | 0 | 0 | 4584
|  | Wash down with FW | QUOTED | 89 | 3.5 | 312 | 0 | 0 | 0 | 0 | 312
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 13.75 | 612 | 0 | 0 | 0 | 0 | 612
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 13.75 | 612 | 0 | 0 | 0 | 0 | 612
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 13.75 | 612 | 0 | 0 | 0 | 0 | 612
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 13.75 | 612 | 0 | 0 | 0 | 0 | 612
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible Bilge keels blasting: excl. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering of: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Anodes and sensors, each | QUOTED | 8 | 21 | 168 | 0 | 0 | 0 | 0 | 168
|  | Propellers, each | QUOTED | 4 | 580 | 2320 | 0 | 0 | 0 | 0 | 2320
|  | ICCP anodes, each | QUOTED | 4 | 925 | 3700 | 0 | 0 | 0 | 0 | 3700
|  | Drainplugs fitted/removed, each | QUOTED | 16 | 130 | 2080 | 0 | 0 | 0 | 0 | 2080
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting existing cargo and plimsol, thruster |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and bulp markings marks | QUOTED | 1 | 5665 | 5665 | 0 | 0 | 0 | 0 | 5665
|  | Markings for in water survey to be painted. | QUOTED | 1 | 10450 | 10450 | 0 | 0 | 0 | 0 | 10450
|  | Special tape for silicone paint | QUOTED | 1 | 8470 | 8470 | 0 | 0 | 0 | 0 | 8470
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of dock bottom after WJ, before |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | painting with silicone paint | QUOTED | 1 | 100000 | 100000 | 0 | 0 | 0 | 0 | 100000
1028 | 1016.02 - PS | Sea chest cleaning and painting
|  | Lower seachest PS, frame 89 - 97, volume 41,1 m³, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | total area 200 m² | QUOTED | 41 | 695 | 28565 | 0 | 0 | 0 | 0 | 28565
|  | Upper seachest PS, frame 91 - 97, volume 48,2 m³, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | total area 143 m² | QUOTED | 48 | 695 | 33499 | 0 | 0 | 0 | 0 | 33499
|  | Forward seachest SB, frame 249 - 250, volume |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1,6 m³, total area 5 m² | QUOTED | 2 | 1940 | 3104 | 0 | 0 | 0 | 0 | 3104
|  | Based on max 1 m³ disposal per sea chest |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal of additional mud |  | 1 | 15000 | 30000 | 0 | -15000 | 0 | 0 | 15000
1029 | 1016.03 - PS | ICCP shields
|  | Blasting and application of epoxy filler (2 meter |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | diameter), each location | ON HOLD | 0 | 16800 | 0 | 0 | 0 | 0 | 0 | 0
1030 | 1018.01 - PS | White Topside cleaning and painting
|  | Total area: 3819 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 3819 m² | QUOTED | 3819 | 10.5 | 40100 | 0 | 0 | 0 | 0 | 40100
|  | Mechanical cleaning, min. 0,25 m² / spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 5%, 190,95 m² | QUOTED | 191 | 103 | 7828 | 11840 | 0 | 0 | 0 | 19668
|  | WJ2, based 5% | CANCELLED | 0 | 160 | 61120 | -61120 | 0 | 0 | 0 | 0
|  | Hosing down with Fw, basis 3819 m² | QUOTED | 3819 | 3.5 | 13367 | 0 | 0 | 0 | 0 | 13367
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 382 m² | QUOTED | 382 | 46.25 | 21183 | -3515 | 0 | 0 | 0 | 17668
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 382 m² | QUOTED | 382 | 46.25 | 21183 | -3515 | 0 | 0 | 0 | 17668
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 382 m² | QUOTED | 382 | 46.25 | 21183 | -3515 | 0 | 0 | 0 | 17668
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 382 m² | QUOTED | 382 | 46.25 | 0 | 17668 | 0 | 0 | 0 | 17668
|  | Up lining between blue and white area, each meter | QUOTED | 487 | 11.5 | 5601 | 0 | 0 | 0 | 0 | 5601
|  | Lift access for inside areas: | QUOTED | 1 | 17600 | 17600 | 0 | 0 | 0 | 0 | 17600
|  | Covering, cleaning and painting of windows |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | frames, each | ++ | 0 | 775 | 0 | 0 | 0 | 0 | 0 | 0
1031 | 1018.02 - PS | Blue Topside cleaning and painting
|  | Blue topside, excluding funnel, total areal: 3984 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 3984 m² | QUOTED | 3984 | 10.5 | 41832 | 0 | 0 | 0 | 0 | 41832
|  | Mechanical cleaning, min. 0,25 m² / spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 5%, 199,2 m² | QUOTED | 199 | 103 | 8209 | 12309 | 0 | 0 | 0 | 20518
|  | WJ2, based 5% | QUOTED | 199 | 160 | 63744 | 0 | -31872 | 0 | 0 | 31872
|  | Hosing down with Fw, basis 3984 m² | QUOTED | 3984 | 3.5 | 13944 | 0 | 0 | 0 | 0 | 13944
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 398,4 m² | QUOTED | 398 | 46.25 | 22108 | -3682 | 0 | 0 | 0 | 18426
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 398,4 m² | QUOTED | 398 | 46.25 | 22108 | -3682 | 0 | 0 | 0 | 18426
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 398,4 m² | QUOTED | 398 | 46.25 | 22108 | -3682 | 0 | 0 | 0 | 18426
|  | Up lining between blue and white area, each meter | QUOTED | 391 | 11.5 | 4497 | 0 | 0 | 0 | 0 | 4497
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Funnel cleaning and painting, area: 536 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 536 m² | QUOTED | 536 | 15.5 | 8308 | 0 | 0 | 0 | 0 | 8308
|  | Mechanical cleaning St3, min. 0,25 m² / spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 25 m² | QUOTED | 25 | 145 | 3625 | 0 | 0 | 0 | 0 | 3625
|  | Hosing down with Fw, basis 536 m² | QUOTED | 536 | 3.5 | 1876 | 0 | 0 | 0 | 0 | 1876
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 30 m² | QUOTED | 30 | 14.25 | 428 | 0 | 0 | 0 | 0 | 428
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 30 m² | QUOTED | 30 | 14.25 | 428 | 0 | 0 | 0 | 0 | 428
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, basis 30 m² | QUOTED | 30 | 14.25 | 428 | 0 | 0 | 0 | 0 | 428
|  | Covering off. | QUOTED | 1 | 3675 | 3675 | 0 | 0 | 0 | 0 | 3675
|  | Access/staging | QUOTED | 1 | 18480 | 18480 | 0 | 0 | 0 | 0 | 18480
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, min. 0,25 m² / spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each m² |  | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Stern ramp cleaning and painting, area: 744 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Stern ramp total area (outside including all |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | edges): 744 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Anticipate 50% or 372 m² to be WJ-2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 744 m² | QUOTED | 744 | 15.5 | 11532 | 0 | 0 | 0 | 0 | 11532
|  | WJ2, min. 0,25 m² / spot, basis 50%, 372 m² | CANCELLED | 0 | 160 | 59520 | 0 | -59520 | 0 | 0 | 0
|  | Mechanical cleaning where Wj-2 not possible |  | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down with Fw, basis 744 m² | CANCELLED | 0 | 3.5 | 2604 | 0 | -2604 | 0 | 0 | 0
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 372 m² | QUOTED | 372 | 14.25 | 5301 | 0 | 0 | 0 | 0 | 5301
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 372 m² | QUOTED | 372 | 14.25 | 5301 | 0 | 0 | 0 | 0 | 5301
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 372 m² | QUOTED | 372 | 14.25 | 5301 | 0 | 0 | 0 | 0 | 5301
|  | Lift for access | QUOTED | 1 | 16060 | 16060 | 0 | 0 | 0 | 0 | 16060
1032 | 1018.03 - PS | Ship name, logo and funnel mark
|  | Painting existing name and homeport | QUOTED | 1 | 6170 | 6170 | 0 | 0 | 0 | 0 | 6170
|  | Painting of existing Logo 6000 mm high |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | "DFDS" on port and starboard side | CANCELLED | 0 | 36960 | 36960 | 0 | -36960 | 0 | 0 | 0
|  | Painting of IMO number | QUOTED | 1 | 924 | 924 | 0 | 0 | 0 | 0 | 924
|  | Painting of existing DFDS logo on funnel on |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | port and starboard side | QUOTED | 1 | 11000 | 11000 | 0 | 0 | 0 | 0 | 11000
1033 | 1018.04 - BW/HS | Ventilation grids
|  | Grids cleaning and painting: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Ventilation grids for cargo fans on upper deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to be dismounted for blasting, Metaliced and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | painting. Size: 1500 x 1350 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bolts and nuts to be renewed where necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each grid | QUOTED | 20 | 22000 | 418000 | 11000 | 0 | 0 | 0 | 429000
|  | Bolts and nuts to be renewed where necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | As per account |  | 1 | 9026 | 0 | 0 | 9026 | 0 | 0 | 9026
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Frames around the ventilation grids: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning and painting of frame in connection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | with removed ventilation grid. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each frame | QUOTED | 20 | 4800 | 91200 | 2400 | 0 | 0 | 0 | 93600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total amount. 42 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Prices based on min. 10 pcs. to be done |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1034 | 1018.06 - PS | Bridge wings
|  | On area below bridge wings, starboard and port, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | rusty spots are to be mechanical cleaned to St 3. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and afterwards painted according to paint specification |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Area below bridge wings 2 x 3 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x 2 windows in bridge flooring to be covered |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for protection when cipping and painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Access by means of cherry picker included. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Treated areas on bridge wings to be coated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | according to the paint specification | QUOTED | 1 | 20575 | 20575 | 0 | 0 | 0 | 0 | 20575
1035 | 1041.01 - TA | Becker Rudder clearence
|  | Access for lower pintle measurement to be cut out. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each plate | QUOTED | 1 | 14100 | 14100 | 0 | 0 | 0 | 0 | 14100
|  | Rudder bearing clearances, with clock guage, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each time | QUOTED | 1 | 7000 | 7000 | 0 | 0 | 0 | 0 | 7000
|  | Rudder and Rudder horn drain plugs to be removed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to test for water ingress and re-fitted after check |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | by Owners Representative. | QUOTED | 1 | 1000 | 1000 | 0 | 0 | 0 | 0 | 1000
1036 | 1041.02 - TA | Becker Rudder
|  | Possible welding up pad eyes for dismounting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of rudder blade, each padeye | ON HOLD | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Access for lower pintle, each access plate | ON HOLD | 0 | 17300 | 17300 | -17300 | 0 | 0 | 0 | 0
|  | Pintle nut access plate to be removed for inspection. | ON HOLD | 0 | 27700 | 27700 | -27700 | 0 | 0 | 0 | 0
|  | Dismantling and remounting of rudder blade, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | based on free access | ON HOLD | 0 | 102000 | 102000 | -102000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bottom plug, pressure test after repair |  | 1 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000
1037 | 1041.03 - TA | Becker Rudder flap overhaul
|  | On-site machining of housings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | To be priced after inspection and agreement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of work scope on the Becker Rudder flap | ON HOLD | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1039 | 1102.01 - BW/HS | SAT lashing system
|  | Repair of SAT lashing pot by welding (per pcs.) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | incl. Lift for access, each | QUOTED | 5 | 4950 | 0 | 0 | 24750 | 0 | 0 | 24750
|  | Subject to free access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Repair of SAT lashing pot by renewal of new |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | owners supplied bottoms (per pcs.) incl. Lift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for access: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Single type, each | CANCELLED | 0 | 12000 | 72000 | 0 | -72000 | 0 | 0 | 0
|  | Double type, each | QUOTED | 18 | 16500 | 99000 | 0 | 198000 | 0 | 0 | 297000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning + painting lashings system, 19 pcs |  | 19 | 1300 | 0 | 0 | 24700 | 0 | 0 | 24700
|  | Incl lift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | In general: Subject to free access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1040 | 1102.02 - PS | Deck painting
|  | Lower hold |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total area of Lower hold deck: 1753 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 1285 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Main deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total area of Main deck: 4086 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 1560 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Upper deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total area of Upper deck: 3851 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 1100 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Weather deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total area of Weather deck: 4705 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 890 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total area: 4835 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning by chemical washing | QUOTED | 4835 | 24.5 | 118458 | 0 | 0 | 0 | 0 | 118458
|  | Cleaning for water before Cyclon cleaning | QUOTED | 4835 | 66 | 319110 | 0 | 0 | 0 | 0 | 319110
|  | Cyclone cleaning SA2 | QUOTED | 4835 | 130 | 628550 | 0 | 0 | 0 | 0 | 628550
|  | Cleaning after Cyclon cleaning, before painting | QUOTED | 4835 | 55 | 265925 | 0 | 0 | 0 | 0 | 265925
|  | Painting 1 Fc Hempadur Avantguard 750 – 80 µm DFT | QUOTED | 4835 | 13.25 | 64064 | 0 | 0 | 0 | 0 | 64064
|  | Painting 1 Fc Hempadur Mastic 45880 – 150 µm DFT | QUOTED | 4835 | 13.25 | 64064 | 0 | 0 | 0 | 0 | 64064
|  | HEMPEL'S ANTI-SLINT 67500, Antiskid | QUOTED | 4835 | 9.75 | 47141 | 0 | 0 | 0 | 0 | 47141
|  | Painting 1 Fc Hempadur Mastic 45880 – 125 µm DFT | QUOTED | 4835 | 13.25 | 64064 | 0 | 0 | 0 | 0 | 64064
|  | Covering off for paint spray | QUOTED | 4835 | 3.5 | 16923 | 0 | 0 | 0 | 0 | 16923
|  | Yellow stripes, each meter |  | 0 | 44.5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each |  | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lashing pots protection and painting of deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | part of lashing pot, each |  | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lashing pots cleaning, blasting and painting, each |  | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional unit prices: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where Cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | not possible |  | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar, each m² |  | 0 | 15.4 | 0 | 0 | 0 | 0 | 0 | 0
|  | Marking up lines and edges, each meter |  | 0 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Deck paintng weather deck, 410 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning by chemical washing | QUOTED | 410 | 24.5 | 0 | 10045 | 0 | 0 | 0 | 10045
|  | Cleaning for water before Cyclon cleaning | QUOTED | 410 | 66 | 0 | 27060 | 0 | 0 | 0 | 27060
|  | HEMPEL'S ANTI-SLINT 67500, Antiskid | QUOTED | 410 | 9.75 | 0 | 3998 | 0 | 0 | 0 | 3998
|  | 1 x FC | QUOTED | 410 | 13.25 | 0 | 5433 | 0 | 0 | 0 | 5433
|  | Covering off for paint spray | QUOTED | 410 | 3.5 | 0 | 1435 | 0 | 0 | 0 | 1435
1041 | 1102.03 - PS | Bimagrip
|  | (HP-wash, covering, mech. Cleaning spot, 3 x TU) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Including: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Locations with 3-5 mm aggregate |  | 0 | 520 | 104000 | -104000 | 0 | 0 | 0 | 0
|  | Locations with 1-3 mm aggregate | QUOTED | 486 | 520 | 270400 | -17784 | 0 | 0 | 0 | 252616
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional: Horisontal ramp, 15 m² | QUOTED | 15 | 520 | 0 | 7800 | 0 | 0 | 0 | 7800
|  | Additional : Weather deck, 15 m² | QUOTED | 15 | 520 | 0 | 7800 | 0 | 0 | 0 | 7800
|  | Additional : Weather deck, 16 m² | QUOTED | 16 | 520 | 0 | 0 | 8320 | 0 | 0 | 8320
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each |  | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lashing pots protection and painting of deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | part of lashing pot, each |  | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lashing pots cleaning, blasting and painting, each |  | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0
1042 | 1102.04 - BW/HS | Crack in center ramp/WB tk 22 and reinforcement of ramp
|  | New scope: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Inserts 2 pcs. 4900 x 600 x 10 mm | QUOTED | 1 | 193475 | 193475 | 0 | 0 | 0 | 0 | 193475
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Reinforcement of ramp with bulb bars 8 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4500 x HP160 | QUOTED | 1 | 98400 | 98400 | 0 | 0 | 0 | 0 | 98400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paintwork new and touched | QUOTED | 1 | 32500 | 32500 | 0 | 0 | 0 | 0 | 32500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Per additional fishbone, 49 pcs. | QUOTED | 49 | 1040 | 50960 | 0 | 0 | 0 | 0 | 50960
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Per additional meter flatbar, based 2*3 meter | QUOTED | 6 | 1585 | 9510 | 0 | 0 | 0 | 0 | 9510
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Treatment Bimagrip, incl.: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each m² |  | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Removal/applicaiton of Bimagrip. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 1 | 5000 | 10000 | 0 | -5000 | 0 | 0 | 5000
1043 | 1102.05 - BW/HS | Replacement of sounding plug in deck
|  | Sounding plug thread size 1 1/2" in sounding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | pipe to be refreshed and cut 15 mm longer in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | the sounding pipe and new longer plug for |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | pipe to be fabricated and mounted | QUOTED | 1 | 12500 | 12500 | 0 | 0 | 0 | 0 | 12500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | New design agreed with CE |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1044 | 1102.06 - BW/HS | Steel repair weather deck
|  | Work order Steel repair weather deck STB |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | frame 145: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Based insert 300 x 300 mm incl. Painting of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | new and touched | QUOTED | 1 | 8000 | 24600 | 0 | -16600 | 0 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 1 | 5000 | 10000 | 0 | -5000 | 0 | 0 | 5000
1045 | 1108.02 - BW/HS | Guard rails on center casing UD/WD
|  | Guard rails to be welded on center casing rails |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | on main deck, upper deck and weather deck: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Upperdeck PS app 50 m. | QUOTED | 50 | 1780 | 89000 | 0 | 0 | 0 | 0 | 89000
|  | Steel profile to be used: 80X120 U-profile |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint treatment according to agreement (2 x |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 50 meter x approx. 1,5 meter high) | CANCELLED | 0 | 32400 | 32400 | 0 | -32400 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. painting of new and touched. |  | 1 | 33800 | 0 | 0 | 33800 | 0 | 0 | 33800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners | CANCELLED | 0 | 10000 | 10000 | 0 | -10000 | 0 | 0 | 0
1046 | 1108.03 - PS | Washing down ceiling/under deck on upperdeck
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, based testarea of 100 m² | QUOTED | 100 | 150 | 15000 | 0 | 0 | 0 | 0 | 15000
|  | Incl. Lift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1047 | 1108.04 - BW/HS | Ceiling on weather deck
|  | Option 2: Replacement of ceiling per section |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Demount ceiling plates and sub-structure, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation new ceiling panels. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Made with 35x300x35mm u-profile panels in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1,5mm galvanized plate, mounted on top of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | existing T-beams so no substructure is needed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | A Z-profile will be mounted below panela |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | around T-beams to fasten panels. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | One section is the square between T-beams |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and between lightboxes (Approx. 3x3m). |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Price per section | QUOTED | 10 | 25410 | 254100 | 0 | 0 | 0 | 0 | 254100
|  | Price does not include chipping and painting, and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | price is based on minimum order of 10 sections. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning to St3 and painting according |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to the paint specification of the structure: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Work scope to be agreed after dismantling of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | ceiling plates. | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1048 | 1111.01 - BW/HS | Sludge and bilge tanks cleaning
|  | Open/cloose manholes including protection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of manhole, each place | BY CREW | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Sludge tank 81 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 8840
|  | Dirty oil tank 85 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 8840
|  | Dirty oil settling tank 87 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 8840
|  | Sludge tank 89 | CANCELLED | 0 | 8840 | 8840 | -8840 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible ventilation and gasfreeing of tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | As per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional cleaning: to be agreed upon |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | sludge, per m³ | QUOTED | 20 | 1200 | 12000 | 0 | 12000 | 0 | 0 | 24000
|  | Mudtruck, each normal hour | QUOTED | 28 | 1150 | 6900 | 0 | 25300 | 0 | 0 | 32200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning around manholes and walkways: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gas free certificate. See item 520.16 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1049 | 1111.02 - CD | Repair of heating coil tk 85
|  | Pressure test of heating coil before repair | QUOTED | 1 | 5800 | 5800 | 0 | 0 | 0 | 0 | 5800
|  | Repair of heating coil 1 m pipe DN50 to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | exchanged | QUOTED | 1 | 12500 | 12500 | 0 | 0 | 0 | 0 | 12500
|  | Pressure test of heating coil after repair | QUOTED | 1 | 5800 | 5800 | 0 | 0 | 0 | 0 | 5800
|  | Based empty, clean tank ready for hot-work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of tank 85 for hot work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Day 1 Mud truck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Day 2 mud truck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Day 3 mud truck + flushing | VOR 5 | 1 | 78000 | 0 | 78000 | 0 | 0 | 0 | 78000
|  | Dipsosal per m³ DKK 1.200 | VOR 5 | 3 | 1200 | 0 | 0 | 3600 | 0 | 0 | 3600
1050 | 1111.03 - BW/HS | Removal of sludge fuel settling tk 35
|  | Open/cloose manholes including protection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of manhole, each place | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of max 10 m³ of pumpable oily waste: | QUOTED | 1 | 23040 | 23040 | 0 | 0 | 0 | 0 | 23040
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional cleaning: To be agreed upon |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | sludge, per m³ |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mudtruck, each normal hour |  | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning + gas freeing | CANCELLED | 0 | 50000 | 0 | 50000 | -50000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Hot water washing + mud truck for emptying of tank | QUOTED | 1 | 175000 | 0 | 0 | 175000 | 0 | 0 | 175000
1051 | 1111.04 - CD | Repair of pipe support in MGO tk 52
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: | CANCELLED | 0 | 8840 | 8840 | -8840 | 0 | 0 | 0 | 0
|  | Possible further suction by vacuumtruck, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each normal hour | CANCELLED | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | sludge, per m³ | CANCELLED | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible further/local cleaning of sludge tank |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for hot-work: Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding of pipesupport | CANCELLED | 0 | 4400 | 4400 | -4400 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Changing of complete owners supplied SAT |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | lashing pot (as BEGONIA) | QUOTED | 1 | 23890 | 23890 | 0 | 0 | 0 | 0 | 23890
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning + gas freeing MGO tank 52 | QUOTED | 1 | 30000 | 0 | 30000 | 0 | 0 | 0 | 30000
1052 | 1114.01 - BW/HS | Ballast tanks
|  | The vessel's crew will open and close manholes |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to the tanks. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible protection of manhole by yard, each | BY CREW | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Below prices are based on empty, clean tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | ready for hot-work. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | In general: Excl. Possible access holes cut/closed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 1: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: 10 spots to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 10 m². | CANCELLED | 0 | 28400 | 28400 | -28400 | 0 | 0 | 0 | 0
|  | Scaffolding: No scaffolding needed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 3: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT4: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 5: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | No work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 6: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: 5 spots to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 5 m². | CANCELLED | 0 | 14200 | 14200 | -14200 | 0 | 0 | 0 | 0
|  | Steelwork: Welding of crack at lashing pot | CANCELLED | 0 | 6000 | 6000 | -6000 | 0 | 0 | 0 | 0
|  | Scaffolding: 20 m³ x 2 locations | CANCELLED | 0 | 16000 | 32000 | -32000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 7: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: corrosion at frame 161, 161 to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | treated and painted 4xTu with roller and brush. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Allow for 10 m² | CANCELLED | 0 | 28400 | 28400 | -28400 | 0 | 0 | 0 | 0
|  | Steelwork: Check of crack at frame 171 | CANCELLED | 0 | 1000 | 1000 | -1000 | 0 | 0 | 0 | 0
|  | Possible repair: Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Scaffolding: 30 m³ x 3 locations | CANCELLED | 0 | 18000 | 54000 | -54000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 8: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: Corrosion at frame 157, 143 PS and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 143 SB to be treated and painted 4xTu with roller |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and brush. Allow for 10 m² | CANCELLED | 0 | 28400 | 28400 | -28400 | 0 | 0 | 0 | 0
|  | Scaffolding: 30 m³ x 3 locations | CANCELLED | 0 | 18000 | 54000 | -54000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 9: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: Corrosion at frame 141, 145, 146 and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 157 to be treated and painted 4xTu with roller |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and brush. Allow for 10 m² | CANCELLED | 0 | 28400 | 28400 | -28400 | 0 | 0 | 0 | 0
|  | Steelwork: Check of crack at topplate near frame 157 | CANCELLED | 0 | 1000 | 1000 | -1000 | 0 | 0 | 0 | 0
|  | Possible repair: Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Scaffolding: 30 m³ x 4 locations | CANCELLED | 0 | 18000 | 72000 | -72000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Heeling tank 10: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: Steel work and 2 spots to be treated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted 4xTu with roller and brush. Allow |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for 5 m² | CANCELLED | 0 | 14200 | 14200 | -14200 | 0 | 0 | 0 | 0
|  | Steelwork: Repair sounding pipe | CANCELLED | 0 | 10200 | 10200 | -10200 | 0 | 0 | 0 | 0
|  | Scaffolding: No scaffolding needed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Heeling tank 11: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: Steel corrosion to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 5 m². | CANCELLED | 0 | 14200 | 14200 | -14200 | 0 | 0 | 0 | 0
|  | Steelwork: Check of crack at frame 141 and 144 | CANCELLED | 0 | 1000 | 1000 | -1000 | 0 | 0 | 0 | 0
|  | Possible repair: Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Steelwork: Repair sounding pipe | CANCELLED | 0 | 10200 | 10200 | -10200 | 0 | 0 | 0 | 0
|  | Scaffolding: 40 m³ x 3 locations | CANCELLED | 0 | 20000 | 60000 | -60000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 12: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: Steelwork at frame 135 to be treated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted 4xTu with roller and brush. Allow |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for 1 m² | CANCELLED | 0 | 6000 | 6000 | -6000 | 0 | 0 | 0 | 0
|  | Steelwork: Doubler plate in way of frame 135 | CANCELLED | 0 | 29800 | 29800 | -29800 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 12a: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | No work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 12b: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | No work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 13: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: Steelwork at frame 135 to be treated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted 4xTu with roller and brush. Allow |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for 1 m² | CANCELLED | 0 | 6000 | 6000 | -6000 | 0 | 0 | 0 | 0
|  | Steelwork: Doubler plate in way of frame 135 | CANCELLED | 0 | 29800 | 29800 | -29800 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 13a: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | No work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 13b: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | No work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Stab. Tank 14: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: Steelwork at frame 135 to be treated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted 4xTu with roller and brush. Allow |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for 2 m² | CANCELLED | 0 | 9000 | 9000 | -9000 | 0 | 0 | 0 | 0
|  | Steelwork: 2 pcs. Doubler plates in way of frame |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 135 (Based same plates as mentioned in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 12+13) | CANCELLED | 0 | 29800 | 59600 | -59600 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Stab. Tank 15: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | No work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Stab. Tank 16: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | No work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 17: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: New insert to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 2 m². | CANCELLED | 0 | 9000 | 9000 | -9000 | 0 | 0 | 0 | 0
|  | Steelwork: 1 pcs. Crack near manhole | CANCELLED | 0 | 22600 | 22600 | -22600 | 0 | 0 | 0 | 0
|  | Scaffolding: 20 m³ x 2 locations | CANCELLED | 0 | 16000 | 32000 | -32000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 18: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: New insert and 2 spots to be treated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted 4xTu with roller and brush. Allow |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for 15 m² | CANCELLED | 0 | 42600 | 42600 | -42600 | 0 | 0 | 0 | 0
|  | Steelwork: 6 pcs. Crack repaired by inserts |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 300 x 300 mm | CANCELLED | 0 | 100600 | 100600 | -100600 | 0 | 0 | 0 | 0
|  | Scaffolding: 40 m³ x 3 locations | CANCELLED | 0 | 20000 | 60000 | -60000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 19: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: New insert and 2 spots to be treated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted 4xTu with roller and brush. Allow |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for 20 m² | CANCELLED | 0 | 56800 | 56800 | -56800 | 0 | 0 | 0 | 0
|  | Steelwork: 6 pcs. Crack repaired by inserts |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 300 x 300 mm | CANCELLED | 0 | 100600 | 100600 | -100600 | 0 | 0 | 0 | 0
|  | Steelwork: 1 pcs. Bended frame repair y insert |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1000 x 500 mm | CANCELLED | 0 | 29800 | 29800 | -29800 | 0 | 0 | 0 | 0
|  | Scaffolding: 30 m³ x 2 locations | CANCELLED | 0 | 18000 | 36000 | -36000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 20: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: 20 spots to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 20 m². | CANCELLED | 0 | 56800 | 56800 | -56800 | 0 | 0 | 0 | 0
|  | Scaffolding: 40 m³ x 4 locations | CANCELLED | 0 | 20000 | 80000 | -80000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | WBT 21: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: 20 spots to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 20 m². | CANCELLED | 0 | 56800 | 56800 | -56800 | 0 | 0 | 0 | 0
|  | Scaffolding: 40 m³ x 4 locations | CANCELLED | 0 | 20000 | 80000 | -80000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Aft peak tank 22: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work: New insert and 10 spots to be treated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted 4xTu with roller and brush. Allow |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for 20 m² | CANCELLED | 0 | 56800 | 56800 | -56800 | 0 | 0 | 0 | 0
|  | Steelwork: 1 pcs. Crack repair by insert 300 x 300 mm | CANCELLED | 0 | 29800 | 29800 | -29800 | 0 | 0 | 0 | 0
|  | Scaffolding: 10 m³ x 1 locations | CANCELLED | 0 | 14000 | 14000 | -14000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners | CANCELLED | 0 | 50000 | 50000 | -50000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Extra: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tank 17: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 pcs if insert weebframe size 300x300x10 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tank 18: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 pcs of repair in web frame 3 repair made |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | by insert 300x300x10 and one repair |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | made by gauging and rewelding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | In total | QUOTED | 1 | 120000 | 0 | 120000 | 0 | 0 | 0 | 120000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work in tanks for steel work : |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Heeling tank 10 - 2 spot basis 5 m² |  | 1 | 13200 | 0 | 0 | 13200 | 0 | 0 | 13200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Ballast tank 10 - 2 spot bais 2 m² |  | 1 | 7200 | 0 | 0 | 7200 | 0 | 0 | 7200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Ballast tank 18 - 3 spot basis 15 m² |  | 1 | 39600 | 0 | 0 | 39600 | 0 | 0 | 39600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | After peak tank 20 - 1 spot basis 20 m² |  | 1 | 52800 | 0 | 0 | 52800 | 0 | 0 | 52800
1053 | 1121.01 - BW/HS | Replacement of door to paint shop
|  | Delivery of new A60 door: By owners |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Exchange of door incl. paint and isolation work | QUOTED | 1 | 37100 | 37100 | 0 | 0 | 0 | 0 | 37100
1054 | 1123.01 - PS | Maintenance on masts
|  | Stagning at topmast A-mast, based 200 m³: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Not needed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work (HP-wash, covering, mech. Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spot, 3 x TU) incl. Lift | QUOTED | 1 | 82600 | 82600 | 0 | 0 | 0 | 0 | 82600
|  | Possible stagning at formast, based 50 m² | CANCELLED | 0 | 11512.5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work formast (HP-wash, covering, mech. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning spot, 3 x TU) | CANCELLED | 0 | 19500 | 19500 | 0 | -19500 | 0 | 0 | 0
|  | Prices are excl. FC | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1055 | 1130.01 - BW/HS | Steel repair main engine room
|  | Insulation to be removed 2 x 1,5 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Scafoldings 2 x 6 meter in high. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | +steel 0,5 m2 deck plate. | QUOTED | 1 | 101300 | 101300 | 0 | 0 | 0 | 0 | 101300
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 1 | 5000 | 10000 | 0 | -5000 | 0 | 0 | 5000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional pipe removal / access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x Cyl cI pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FW pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x water spray pipe |  | 1 | 38500 | 0 | 0 | 38500 | 0 | 0 | 38500
1056 | 1201.01 - BW/HS | Anchors and chains
|  | Anchors and chains ranged in dock, Hp cleaning, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | measured an marked with SS bands | QUOTED | 1 | 29000 | 29000 | 0 | 0 | 0 | 0 | 29000
|  | Painting of anchors with 1 coat | QUOTED | 1 | 7700 | 7700 | 0 | 0 | 0 | 0 | 7700
|  | Painting of lenghts with red and white paint: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1057 | 1201.02 - BW/HS | Chainlockers
|  | 3 pcs. of manholes to be opened | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning and mud removal, included max 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | ton mud | CANCELLED | 0 | 34000 | 34000 | 0 | -34000 | 0 | 0 | 0
|  | Possible additional disposal of mud, each ton |  | 0 | 3750 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional cleaning and painting: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhaul of 2 pcs of drain valves, each | QUOTED | 2 | 3740 | 7480 | 0 | 0 | 0 | 0 | 7480
1059 | 1250.01 - BW/HS | Electrical jobs
|  | Electrician: Based 12 hour dayshift, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each person per day |  | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Roller staging, per pcs. |  | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scissor lift, each per day |  | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance |  | 1 | 10000 | 0 | 50000 | -40000 | 0 | 0 | 10000
1060 | 1302.01 - BW/HS | Fairlead rollers overhaul
|  | Dismounting, cleaning and remounting of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | rollers for fairleads, each | QUOTED | 2 | 6150 | 61500 | -49200 | 0 | 0 | 0 | 12300
|  | Possible loosening of rollers without dismounting, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each |  | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible dismounting, cleaning and remounting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of "turtle" rollers, each | CANCELLED | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible renewal of bushings in rollers, each | CANCELLED | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible lift for access, each per day | CANCELLED | 0 | 3500 | 14000 | -14000 | 0 | 0 | 0 | 0
|  | Possible cut-outs in vessel for dismounting of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | rollers, each |  | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0
|  | In general: Excl. Possible paint treatment |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1062 | 1302.03 - BW/HS | Mooring Winch aft
|  | Dismounting, disassembling, cleaning, reassembling |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and remounting of mooring winch, 1 pcs. | QUOTED | 1 | 60500 | 60500 | 0 | 0 | 0 | 0 | 60500
|  | Excl. Possible casting below |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining of brakesurfaces on drums, each surface | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Renewal of bushings in drums, each | QUOTED | 4 | 3625 | 3625 | 10875 | 0 | 0 | 0 | 14500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible dis- and remounting of shaft from |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | gearbox, each | CANCELLED | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Exchange of brake band |  | 2 | 14300 | 0 | 28600 | 0 | 0 | 0 | 28600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of brake surfaces |  | 2 | 3640 | 0 | 7280 | 0 | 0 | 0 | 7280
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional according to agreement |  | 1 | 27500 | 0 | 0 | 27500 | 0 | 0 | 27500
1063 | 1317.02 - BW/HS | Assistants in repair of RORO equipment
|  | Possible assistance to owners specialists: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift |  | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible crane assistance, each hour |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible lift assistance, each per day |  | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Stern ramp hinges: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance, ilt/gas, crane, lift etc. | QUOTED | 1 | 150000 | 150000 | 0 | 0 | 0 | 0 | 150000
1065 | 1317.06 - BW/HS | Cover to lower hold gasket replacement
|  | Tightness test per test, to be done by vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | before yard arrival |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gasket replacement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gasket replacement per running meter. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Seam for gasket mechanical cleaned and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | according to the paint specification before the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | new gasket is installed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each meter | CANCELLED | 0 | 1617 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry picker, each per day | CANCELLED | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tightness test to be performed using hose with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | fresh water after the repair is completed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each test | CANCELLED | 0 | 4375 | 4375 | 0 | -4375 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | New rubber gasket, glue and paint are delivered |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | by the Owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Meter price based on min. 10 meters to be renewed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1066 | 1317.07 - BW/HS | Hoistable ramp gasket repair
|  | Tightness test per test, to be done by vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | before yard arrival |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gasket replacement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gasket replacement per running meter. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Seam for gasket mechanical cleaned and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | according to the paint specification before the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | new gasket is installed: Based on free access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each meter |  | 0 | 1617 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry Picker for access, each per day |  | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible cut out for replacing gasket. As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Frame #109 forward |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Rubber gasket to be replaced. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Allow for lowering of hoistable ramp app. 200 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | mm to get access to gasket and channel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Seam for gasket mechanical cleaned and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | according to the paint specification before |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | new gasket is installed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Allow for cherry picker for access to hoistable |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | ramp hinges underneath. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | See attached pictures of repair from sister vessel. | CANCELLED | 0 | 72100 | 72100 | 0 | -72100 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tightness test to be performed using hose with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | fresh water after the repair is completed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each test | QUOTED | 1 | 4375 | 4375 | 0 | 0 | 0 | 0 | 4375
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and Owner | CANCELLED | 0 | 10000 | 10000 | 0 | -10000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | New rubber gasket, glue and paint are delivered |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | by the Owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Meter price based on min. 10 meters to be renewed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1067 | 1317.08 - BW/HS | Pilot door gasket replacement
|  | Replacement of gasket in Pilot doors |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gasket and glue is Owner supply |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Water tightness test. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each door/2 doors | CANCELLED | 0 | 34836 | 69672 | -69672 | 0 | 0 | 0 | 0
1069 | 1317.10 - BW/HS | Repair of flap on PS hoistable car deck access ramp
|  | Removal of 4 flaps and exchange of bottomplate |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 3280 x 200 x 5 mm - maybe split into 2 pcs. | QUOTED | 1 | 111130 | 111130 | 0 | 0 | 0 | 0 | 111130
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible repair of hinges: Priced after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | In general: Excl. Possible further repairs and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | spares not mentioned above |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1070 | 1317.11 - BW/HS | Steel replacement in hoistable ramp
|  | Repair of crack in hoistable ramp, Frame #69, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | allow for one pcs. insert of 2000x500x10 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | A36TM, work can be done from upper side |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | with backing for welding | QUOTED | 2 | 52000 | 52000 | 52000 | 0 | 0 | 0 | 104000
|  | Excl. Possible covering/removal of cables for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 1 | 5000 | 10000 | 0 | -5000 | 0 | 0 | 5000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bima Grip |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1071 | 1401.01 - BW/HS | Freefall lifeboat (FFB)
|  | Freefall lifeboat to be taken ashore and return |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | after polishing. | QUOTED | 1 | 12000 | 12000 | 0 | 0 | 0 | 0 | 12000
|  | Boat to be cleaned, covered off for polishing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and polished. | QUOTED | 1 | 49400 | 49400 | 0 | 0 | 0 | 0 | 49400
|  | David to be chemical cleaned, covered off for |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | painting, mechanical cleaned on rusti spods, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | washed down with FW, Tu coated 2 times with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | roller and brush on spods and Fc with with roller |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and brush 1 time, lift for access included in price. | QUOTED | 1 | 38840 | 38840 | 0 | 0 | 0 | 0 | 38840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible further assistance to owners |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | specialists: Each person per 12 hour day shift |  | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible fiberglass repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1072 | 1502.01 - CD | Main fire line repair
|  | Renewal of 6 pcs. Pipes as spec. incl. Painting of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | new and touched and incl. staging | QUOTED | 1 | 106100 | 106100 | 0 | 0 | 0 | 0 | 106100
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional 3 meter 6" pipe |  | 1 | 12500 | 0 | 0 | 12500 | 0 | 0 | 12500
1073 | 2701.01 - BW/HS | Ventilation duct cleaning
|  | Galley exhaust ventilation duct to be cleaned |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for dust and grease. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Galley exhaust is going inside galley and then |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | down to weatherdeck mid ship and continuing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to SB shipside. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Galley exhaust ducts approxymately 50 meter. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Necessary access and staging to perform the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | cleaning. | QUOTED | 1 | 93410 | 93410 | 0 | 0 | 0 | 0 | 93410
1074 | 2701.02 - CD | Sanitary pipe leak 1st house deck
|  | Pipe renewal 1 meter 2" galv. pipe incl. dis- |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and remount ceiling in corridor and meat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | room for access | QUOTED | 1 | 38040 | 38040 | 0 | 0 | 0 | 0 | 38040
|  | Based meatroom emptied by crew before arrival |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to yard |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Material |  | 1 | 2000 | 0 | 0 | 2000 | 0 | 0 | 2000
|  | 1 meter pipe 2 meter in total |  | 1 | 7500 | 0 | 0 | 7500 | 0 | 0 | 7500
1075 | 2713.01 - BW/HS | Floor in galley - YARD INFO ONLY
|  | Done by owners appointed subcontractor | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1077 | 3127.01 - BW/HS | Main engine auxiliary blowers
|  | 2 pieces of main engine auxiliary blowers to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | be overhauled with new shaft seals. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | The bearings in the electrical motors are to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | replaced. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | The fan impellers are to be balanced to the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | speed of the electrical motor. Each/2 pcs. | QUOTED | 2 | 37300 | 74600 | 0 | 0 | 0 | 0 | 74600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | The electrical motors will be disconnected by the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | vessel's electrician and reconnected again after |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | the overhaul. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Spare parts are supplied by the Owner |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of 4 pcs seals for aux blower |  | 1 | 4800 | 0 | 0 | 4800 | 0 | 0 | 4800
1078 | 3138.04 - BW/HS | Scrubber uptake & bypass valves overhaul
|  | Possible installation of new manholes to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | installed in the Main engine exhaust gas pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for access to damper valves for scrubber system |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each new manhole | CANCELLED | 0 | 35920 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on free acces for placing the manholes. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bypass valve - Tag: A1010. Maker: VVC, model |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | type DSK-D (double disc), DN1600, Location: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Top of casing (outside): |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Leaf Springs, gland packings and bearings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to be replaced. | CANCELLED | 0 | 43350 | 43350 | -43350 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Uptake valve - Tag: A1030 Maker: VVC, model |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | type DSK (single disc), DN1600, Location: Top |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of casing (inside) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gland packing, bearings to be replaced. | QUOTED | 1 | 41150 | 41150 | 0 | 0 | 0 | 0 | 41150
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Both actuators is to be dimounted, overhauled |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and mounted again: As per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible drilling of holes for adjustment: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Scrubber uptake & bypass valves overhaul. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Change of scope for outside valve .New price: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Access thin plate / insulation. | VOR 4 | 1 | 13000 | 0 | 13000 | 0 | 0 | 0 | 13000
|  | Dis- and remounting of owner delivered new valve. | VOR 4 | 1 | 55350 | 0 | 55350 | 0 | 0 | 0 | 55350
|  | Dis- and remounting of exhaust pipe for access. | VOR 4 | 1 | 29380 | 0 | 29380 | 0 | 0 | 0 | 29380
|  | 3 pcs. padeys, firewatch and cherry picker | VOR 4 | 1 | 38000 | 0 | 38000 | 0 | 0 | 0 | 38000
1079 | 3138.07 - CD | New silencer AE4
|  | Installation of new silencer as spec. | QUOTED | 1 | 110100 | 110100 | 0 | 0 | 0 | 0 | 110100
1080 | 3138.09 - BW/HS | Exhaust pipes on funnel top
|  | 1. Missing insulation and lining on 3 pcs DN |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 500 pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation of insulation and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | cladding in stainless steel on 3 x 1,5 meter DN500 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | exhaust pipes | QUOTED | 1 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Corrosion on rain covers (paint work) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Corrosion on funnel top (paint work) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Washing with soap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC | QUOTED | 1 | 15000 | 22900 | 0 | -7900 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible repair of steel, pipes etc. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1081 | 3301.01 - BW/HS | Scrubber SW pumps overhaul
|  | Scrubber pumps overhaul, 2 pcs. | QUOTED | 2 | 40230 | 80460 | 0 | 0 | 0 | 0 | 80460
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhaul of electrical motor, each | QUOTED | 2 | 33505 | 67010 | 0 | 0 | 0 | 0 | 67010
|  | Alignment of electrical motor and pump: Incl. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of scrupper pump housings with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | owners supplied Wencon, each | CANCELLED | 0 | 12250 | 24500 | 0 | -24500 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of wencon | QUOTED | 1 | 1320 | 0 | 1320 | 0 | 0 | 0 | 1320
|  | Repair |  | 1 | 5000 | 0 | 0 | 5000 | 0 | 0 | 5000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Blasting and painting of scrupper pump |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | housings (As on Freesia) | CANCELLED | 0 | 35380 | 70760 | 0 | -70760 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bushing of End -shield |  | 1 | 8000 | 0 | 8000 | 0 | 0 | 0 | 8000
1082 | 3302.01 - BW/HS | Cooler maintenance
|  | Job 1 Scrubber cooler 455 plates: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismantling, cleaning and reassembling with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | old gaskets | CANCELLED | 0 | 148785 | 148785 | -148785 | 0 | 0 | 0 | 0
|  | Possible change of owners supplied gaskets, each |  | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0
|  | Alternatively: Replacing of plates with new |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | overhauled plates of owners supply | QUOTED | 1 | 40000 | 0 | 40000 | 0 | 0 | 0 | 40000
|  | Anchor plate inspection, grinding, and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | coating: Priced after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Job 2 LT FW cooler 2x250 plates: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismantling, cleaning and reassembling with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | old gaskets | CANCELLED | 0 | 81750 | 163500 | -163500 | 0 | 0 | 0 | 0
|  | Possible change of owners supplied gaskets, each |  | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0
|  | Anchor plate inspection, grinding, and coating: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection | VOR 6 | 1 | 8060 | 0 | 8060 | 0 | 0 | 0 | 8060
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Job 3 LO cooler 440 plates: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismantling, cleaning and reassembling with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | new owners supplied gaskets | CANCELLED | 0 | 225720 | 225720 | -225720 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of wencon | VOR 6 | 1 | 2480 | 0 | 2480 | 0 | 0 | 0 | 2480
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Exchange of 4 pcs rubber liners cooler | VOR 6 | 1 | 8645 | 0 | 8645 | 0 | 0 | 0 | 8645
1083 | 3306.01 - CD | Repair of cunifer pipe
|  | Work order Repair of cunifer pipe DN 250 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | located at SW outlet side of central cooler: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Dis- and remounting of pipe. | QUOTED | 1 | 9775 | 9775 | 0 | 0 | 0 | 0 | 9775
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible repair/renewal: Priced after dismounting |  | 1 | 23000 | 0 | 0 | 23000 | 0 | 0 | 23000
1084 | 3306.02 - CD | Repair of LT cooling water pipe
|  | Pipe renewal as spec. 1,6 meter DN125 and 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | meter DN150, reduction DN150/125, 1 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | DN150 flange and 2 pcs. DN125 flanges. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | incl. Painting of new and touched | CANCELLED | 0 | 40140 | 40140 | 0 | -40140 | 0 | 0 | 0
1085 | 3330.01 - BW/HS | Damcos remote valve control system upgrade
|  | Assistance | QUOTED | 1 | 25000 | 0 | 25000 | 0 | 0 | 0 | 25000
1086 | 3331.01 - BW/HS | Power management system upgrade
|  | YARD INFO ONLY | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1087 | 3332.01 - BW/HS | Electrical main breakers to be checked
|  | Breakers in switchboard to be tested and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | checked: Level 3 + Service |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | All of type Merlin Gerin Masterpact. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each/21 pcs. | QUOTED | 21 | 3975 | 83475 | 0 | 0 | 0 | 0 | 83475
|  | All materials to be delivered by owner |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible repairs to be agreed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1088 | 3338.01 - CD | Scrubber outlet ship bottom
|  | Priced after inspection upon arrival | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1089 | 3338.02 - CD | Scrubber discharge pipe
|  | Priced after inspection and determination of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | workscope | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1090 | 3338.03 - BW/HS | Ship side valves
|  | Shipside valves 28 pcs according to attached |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | list valves to be opened/closed and overhauled |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and approved by Lloyds surveyor. | QUOTED | 1 | 64330 | 64330 | 0 | 0 | 0 | 0 | 64330
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Broken studs to be drilled out, re-tapped and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | studs replaced: As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Pipes between all sea valves and ship's side to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | be proven clear | QUOTED | 1 | 6800 | 6800 | 0 | 0 | 0 | 0 | 6800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of pipes, each |  | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subject to free access. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. possible remote controls and actuators. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Cone valves overhauled without dismounting of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | valve housing. Butterfly valves cleaned "in-situ" |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | without dismounting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Exchange of boiler blow don valve |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 pcs DN 50 valve in fair lead exchanged |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 pcs DN 50 valves dis and reounted for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 pcs pipes dis and remounted for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Various flooring and work under floor |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total additional |  | 1 | 41860 | 0 | 41860 | 0 | 0 | 0 | 41860
1091 | 3338.05 - CD | Black water discharge pipe
|  | Work order Black water discharge pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 114,3x10 mm. incl. Lift in dock for access | QUOTED | 1 | 36800 | 36800 | 0 | 0 | 0 | 0 | 36800
1092 | 3338.06 - BW/HS | Bilge overboard valve to be replaced
|  | Renewal of 1 pcs owners supplied valve | QUOTED | 1 | 4160 | 4160 | 0 | 0 | 0 | 0 | 4160
|  | Based plug-and-play |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1093 | 3341.01 - BW/HS | Ventilation grids EMG generator room
|  | Dis- and remounting of grids 1500x1000 mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Agreed half price due to claim | QUOTED | 1 | 13850 | 13850 | 0 | 0 | 0 | 0 | 13850
|  | Blasting and metalization: Free of charge |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1094 | 3401.01 - BW/HS | Oil fired boiler: Overhaul of valves and cleaning
|  | Aalborg AR 3C oil fired boiler |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Boiler to be opened on water and gas side. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Boiler to be vacuum cleaned on gas side. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | All valves according to list to be overhauled in situ. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valves to be dismantled and overhauled. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valves to be pressure tested to 9 bars |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and certificate isued. | QUOTED | 1 | 107960 | 107960 | 0 | 0 | 0 | 0 | 107960
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Reduction based on owner will supply new valves |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | instead of yard doing overhaul |  | 1 | -15730 | -15730 | 0 | 0 | 0 | 0 | -15730
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Exchange of 4 pcs level gate valves |  | 1 | 4800 | 0 | 0 | 4800 | 0 | 0 | 4800
|  | Exchange of 4 pcs DN 32 safety valves |  | 1 | 6480 | 0 | 0 | 6480 | 0 | 0 | 6480
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 pcs DN 32 safety valves: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Inspection, sealing and certificates |  | 1 | 2195 | 0 | 0 | 2195 | 0 | 0 | 2195
1095 | 3401.02 - BW/HS | Oil fired boiler: Firewall
|  | To be priced after inspection of Firewall | QUOTED | 1 | 15000 | 0 | 0 | 15000 | 0 | 0 | 15000
1096 | 3401.03 - CD | Steam pipes
|  | Work order Steam pipes | QUOTED | 1 | 28750 | 28750 | 0 | 0 | 0 | 0 | 28750
|  | Excl. Possible insulation removal/refitting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1097 | 3411.01 - BW/HS | ME exhaust gas boiler: Overhaul of valves and cleaning
|  | Work order ME Exhaust gas boiler Aalborg AQ 7 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Boiler to be opened on water and gas side. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Boiler to be vacuum cleaned on gas side. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | All valves according to list to be overhauled in situ. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valves to be dismantled and overhauled. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valves to be pressure tested to 9 bars |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and certificate isued. | QUOTED | 1 | 58030 | 58030 | 0 | 0 | 0 | 0 | 58030
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Reduction based on owner will supply new valves |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | instead of yard doing overhaul |  | 1 | -10725 | -10725 | 0 | 0 | 0 | 0 | -10725
1098 | 3411.02 - BW/HS | AE4 exhaust gas boiler: Overhaul of valves and cleaning
|  | Work order AE4 exhaust gas boiler: type GB-W-PT |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Boiler to be opened on water and gas side. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Boiler to be vacuum cleaned on gas side. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | All valves according to list to be overhauled in situ. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valves to be dismantled and overhauled. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valves to be pressure tested to 9 bars |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and certificate isued. | QUOTED | 1 | 77140 | 77140 | 0 | 0 | 0 | 0 | 77140
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Reduction based on owner will supply new valves |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | instead of yard doing overhaul |  | 1 | -8580 | -8580 | 0 | 0 | 0 | 0 | -8580
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 pcs DN 25 safety valves: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Inspection, sealing and certificates |  | 1 | 2195 | 0 | 0 | 2195 | 0 | 0 | 2195
1099 | 3411.03 - CD | Blowdown pipe boiler
|  | Replace Boiler blow down OB pipe. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Pipe has to be done in thick walled seamless |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | steel pipe, coating of pipe inside. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Pipe dimension 76,1x7,1. Flange DN65. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Material ST37-0 Lenght app. 470 mm. | QUOTED | 1 | 23334 | 23334 | 0 | 0 | 0 | 0 | 23334
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and Owner |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | To be priced after inspection. |  | 1 | 5000 | 10000 | 0 | -5000 | 0 | 0 | 5000
1100 | 3801.01 - TA | Polishing of propeller blades
|  | Normal polishing of propeller blades, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each blade | CANCELLED | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dye chech penetrant on blade root and blade |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | edge, each blade | CANCELLED | 0 | 4650 | 0 | 0 | 0 | 0 | 0 | 0
1101 | 3801.02 - TA | Ropeguard
|  | A.Fabrication of missing rope guard knives, 6 pcs. | CANCELLED | 0 | 3570 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rotation anti clockwise, max opening between |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | knife and rotation part 2 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | B.Fabrication of new rope guard | CANCELLED | 0 | 50300 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on straight cylindric rope guards |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1102 | 3801.04 - TA | Propeller hub overhaul
|  | Dismantling of propeller hub from propeller |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | shaft and refitting after overhaul: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Staging for dismantling ropeguard | QUOTED | 1 | 13200 | 13200 | 0 | 0 | 0 | 0 | 13200
|  | Dismantling and refit ropeguard | QUOTED | 1 | 24700 | 24700 | 0 | 0 | 0 | 0 | 24700
|  | Measuring of tail shaft wear down | QUOTED | 1 | 3200 | 3200 | 0 | 0 | 0 | 0 | 3200
|  | Draining of propeller and stern tupe oil by |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | yard and new oil refilled by crew | QUOTED | 1 | 15300 | 15300 | 0 | 0 | 0 | 0 | 15300
|  | Disposal of oil. Each m³ | QUOTED | 4 | 1200 | 4200 | 0 | 0 | 0 | 0 | 4200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Staging for dismantling and refitting of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | propeller blades | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Remove of blades and refit propeller blade. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each/4 pcs. | QUOTED | 4 | 18000 | 72000 | 0 | 0 | 0 | 0 | 72000
|  | Possible transport ahore and back, each | QUOTED | 4 | 2000 | 8000 | 0 | 0 | 0 | 0 | 8000
|  | Removed blade bolts to be measured in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | lenght and dye checked. Each/24 pcs. | CANCELLED | 0 | 1775 | 0 | 0 | 0 | 0 | 0 | 0
|  | Baking of propeller blade bolts in 3 hours at |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 180 degree C. Each/24 pcs. | ON HOLD | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dye penetrant crack detection of propeller blade. | ON HOLD | 0 | 4650 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismantling of propeller hub from propeller |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | shaft and refitting after overhaul | QUOTED | 1 | 250000 | 250000 | 0 | 0 | 0 | 0 | 250000
|  | Transport of hub to and from yard work shop | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist for dismantling |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of propeller hub in work shop, measure up |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | hub and resample. Each person per 12 hour shift | ON HOLD | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible machining of parts. To be agreed | ON HOLD | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding up pad eyes, each padeye | ON HOLD | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydraulic tools for total work scope. | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 0 | 25000
1103 | 3802.01 - TA | Stern Tube Seal
|  | 1. Relocation of header tank: | QUOTED | 1 | 397000 | 397000 | 0 | 0 | 0 | 0 | 397000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Aft seal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | AEGIR Marine type Prime-Secure 710 with APS. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Measuring of tail shaft wear down | QUOTED | 1 | 3200 | 3200 | 0 | 0 | 0 | 0 | 3200
|  | Assistance to owners specialist with installation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of new liner and. Each person per 12 hour shift, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | estimated 5 shifts | QUOTED | 5 | 7500 | 37500 | 0 | 0 | 0 | 0 | 37500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Forward seal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Forward seal system to be opened for upgrade |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to new system. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Existing system: Deep Sea Seal Limited 630 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | MOD 575 type LC seal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | New system: AEGIR PRIME 630 Viton (Non split) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist with installation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of new Forward seal system, type AEGIR PRIME |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 630 Viton (Non split) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour shift, estimated 5 shifts | QUOTED | 5 | 7500 | 37500 | 0 | 0 | 0 | 0 | 37500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | New Owner delivered seal tank to be installed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | according to drawing. Installation of new pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | supports. Pipe supports and pipes to be delivered |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | by the yard according to drawings. New pipes |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to be flushed and pressure tested. | QUOTED | 1 | 53800 | 53800 | 0 | 0 | 0 | 0 | 53800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Removal of SKF coupling for access to mount |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | the new forward shaft seal system | CANCELLED | 0 | 35300 | 35300 | 0 | -35300 | 0 | 0 | 0
1104 | 3805.01 - TA | OD box overhaul
|  | OD-Box on main propeller shaft to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | dismantled for overhaul: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Removing and refitting of platforms etc. for |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | access to dismantling and refitting of the OD shaft | QUOTED | 1 | 79400 | 79400 | 0 | 0 | 0 | 0 | 79400
|  | Dismantling and refitting of intermediate shaft |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | bearing and OD shaft for removing of the OD |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | box for the overhaul. | QUOTED | 1 | 375000 | 375000 | 0 | 0 | 0 | 0 | 375000
|  | Welding up pad eyes, each pad eye, estimated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 pcs. each | QUOTED | 5 | 10000 | 50000 | 0 | 0 | 0 | 0 | 50000
|  | Assistance with removing of the OD box from |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | OD shaft, transport to work shop, overhaul of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | OD box, transport back and fitting back the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | OD box on the OD shaft. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hours shift, estimated 30 pcs. | QUOTED | 30 | 7500 | 225000 | 0 | 0 | 0 | 0 | 225000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tools and materials for removing and refitting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of OD box from OD shaft | QUOTED | 1 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000
|  | Crane / Forklift | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000
|  | Transport of OD box Frederikshavn / Munkebo | CANCELLED | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Prices are based on propeller shaft and SKF |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | coupling are removed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Check and possible realignment of intermediat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | shaft bearing and shaft line to be done by |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | owners specialist, ordered and payed by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1105 | 3805.02 - TA | Propellershaft modyfied withdrawal
|  | Dismounting of BECKER RUDDER. See item 1041.02 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tailshaft to be withdrawn aft from the vessel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Tailshaft to be withdrawn as far as needed for |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | changin the inner seal to a Owner supplyied |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | new seal. | QUOTED | 1 | 107700 | 107700 | 0 | 0 | 0 | 0 | 107700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding up pad eyes. Each padeye | QUOTED | 4 | 10000 | 40000 | 0 | 0 | 0 | 0 | 40000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydraulic sleeve Coupling (SKF DKCA 550) in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | the engine room between tail shaft and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | intermediate shaft to be disconnected from |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | shaft and refitted on completion. | QUOTED | 1 | 35300 | 35300 | 0 | 0 | 0 | 0 | 35300
|  | Scope is not included in item 3805.01. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Vacuum truck | QUOTED | 1 | 10000 | 0 | 20000 | -10000 | 0 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Shaft lifted do to late delivery of OD pipe | ESTIMATED | 1 | 100000 | 0 | 0 | 100000 | 0 | 0 | 100000
1107 | 3811.01 - TA | Thruster cavitation rings repair
|  | Stainless steel overlay weld (cavitation ring) in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | thruster tunnels to be repaired by grinding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and welding. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Amount of repair to be decided after the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | investigation with the Owner's Representative |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | To be priced after inspection of cavitation in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Thruster ring area. |  | 1 | 15000 | 0 | 0 | 15000 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and Owner | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1108 | 3811.02 - TA | Bow Thruster no. 1 (forward)
|  | Bow Thruster no.1 dismantled for complete |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | overhaul in workshop: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Grid removal / reinstall, based on bolted/welded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | type, per unit | QUOTED | 2 | 12000 | 24000 | 0 | 0 | 0 | 0 | 24000
|  | Oil drained and refilled by crew incl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Per unit | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Removal/reinstall of propeller blade, per blade | CANCELLED | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Demount/refit of underwater part, included |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | transport to workshop for overhaul or shifting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to replacement unit: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on only access from outside, per unit | QUOTED | 1 | 60000 | 60000 | 0 | 0 | 0 | 0 | 60000
|  | Possible installation of padeys, each | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Excl. possible internal painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | QUOTED | 6 | 7500 | 45000 | 0 | 0 | 0 | 0 | 45000
|  | Disposal of oil, each m³ | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible machining of propeller blade foot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each foot | CANCELLED | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0
1109 | 3811.03 - TA | Bow Thruster no.2 (aft)
|  | Bow Thruster no.2 dismantled for replacement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of the propeller shaft seal: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Grid removal / reinstall, based on bolted/welded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | type, per unit | QUOTED | 2 | 12000 | 24000 | 0 | 0 | 0 | 0 | 24000
|  | Oil drained and refilled by crew incl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Per unit | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Possible installation of padeys, each | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000
|  | Excl. possible internal painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | QUOTED | 16 | 7500 | 120000 | 0 | 0 | 0 | 0 | 120000
|  | Disposal of oil, each m³ | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible removal/reinstall of propeller blade, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | per blade | QUOTED | 4 | 6000 | 24000 | 0 | 0 | 0 | 0 | 24000
|  | Possible machining of propeller blade foot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each foot |  | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0
1110 | 3811.04 - TA | Stern Thruster no. 1 (forward)
|  | Stern Thruster no.1 dismantled for complete |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | overhaul in workshop: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Grid removal / reinstall, based on bolted/welded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | type, per unit | QUOTED | 2 | 12000 | 24000 | 0 | 0 | 0 | 0 | 24000
|  | Oil drained and refilled by crew incl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Per unit | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Removal/reinstall of propeller blade, per blade | CANCELLED | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Demount/refit of underwater part, included |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | transport to workshop for overhaul or shifting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to replacement unit: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on only access from outside, per unit | QUOTED | 1 | 60000 | 60000 | 0 | 0 | 0 | 0 | 60000
|  | Possible installation of padeys, each | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Excl. possible internal painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | QUOTED | 6 | 7500 | 45000 | 0 | 0 | 0 | 0 | 45000
|  | Disposal of oil, each m³ | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible machining of propeller blade foot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each foot |  | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0
1111 | 3811.05 - TA | Stern Thruster no. 2 (aft)
|  | Stern Thruster no.2 dismantled for replacement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of the propeller shaft seal: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Grid removal / reinstall, based on bolted/welded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | type, per unit | QUOTED | 2 | 12000 | 24000 | 0 | 0 | 0 | 0 | 24000
|  | Oil drained and refilled by crew incl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Per unit | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000
|  | Possible installation of padeys, each | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000
|  | Excl. possible internal painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | QUOTED | 16 | 7500 | 120000 | 0 | 0 | 0 | 0 | 120000
|  | Disposal of oil, each m³ | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible removal/reinstall of propeller blade, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | per blade | CANCELLED | 0 | 6000 | 24000 | 0 | -24000 | 0 | 0 | 0
|  | Possible machining of propeller blade foot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | each foot | CANCELLED | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0
1112 | 9010.03 - CD | Temporary installations new sewage plant
|  | Rental and connecting of 2 pcs of temporary |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | mobile wagon with 4 pcs of vacuum toilets each |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | wagon and placed the wagons on vessel deck. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Rental of 4 pcs. of 5 m³ sewage tanks, placed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | on deck, each side of the car deck for collecting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of grey- and black water. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | External transport of rental eguipment, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | insurence, etc. | QUOTED | 1 | 164160 | 164160 | 0 | 0 | 0 | 0 | 164160
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Emptying of existing and temporary tanks by |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | sludge truck as nessesury, each hour |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal of sewage / grey water. Each m³ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | In total | QUOTED | 1 | 37000 | 37000 | 0 | 0 | 0 | 0 | 37000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Temparery rebuilding of existing grey and black |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | water drop system for connecting to 4 x 5 m³ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | sewage tanks during rebuilding of sewage system. | QUOTED | 1 | 75000 | 75000 | 0 | 0 | 0 | 0 | 75000
1113 | 9010.04 - CD | New sewage treatment plant
|  | New sewage treatment plant to be installed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | onboard. | QUOTED | 1 | 1428000 | 1428000 | 0 | 0 | 0 | 0 | 1428000
|  | Price based on new sludge tank is made in 6 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | stainless steel with outside reinforcements in black |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | coated steel and connedting to existing breakers. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2. Changes to existing sewage plant: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Above price is excl. removing of internal eguipment |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | in the old sewage treatment plant and opening |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of internal baffels. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Opening, flushing and cleaning of existing sewage |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | plant, removing of the old fiber casettes, cutting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of holes in the walls between the champers and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | after ward additional flushing and suction of tank, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | removing of old plastic hoses and pipes, not in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | use on existing sewage tank and disposal of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | sewage and fiber casettes. | QUOTED | 1 | 21200 | 21200 | 0 | 0 | 0 | 0 | 21200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivering and installation of 1 new relay for |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | NS breaker in MSB | QUOTED | 1 | 2780 | 2780 | 0 | 0 | 0 | 0 | 2780
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Level sensors old sewage tank, additional. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 new cables incl. supports in Ansi 316, 2 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | of new cable penetrasions and junchion box |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | incl. terminals and glands. | QUOTED | 1 | 13500 | 13500 | 0 | 0 | 0 | 0 | 13500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional due to additional request from owners: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation of ø200 spior ducting and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | fan, total of 7 bends, 10 meters, 1 fan and 1 diffuser |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismount and reestablish insulation in deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | for accesshole and on bulkhed for supports | QUOTED | 1 | 121440 | 121440 | 0 | 0 | 0 | 0 | 121440
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishing working air supply at new sewage plant | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishing working power at new sewage plant | QUOTED | 1 | 12000 | 12000 | 0 | 0 | 0 | 0 | 12000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation of plexi glass inspection window in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | top of tank | QUOTED | 1 | 4950 | 4950 | 0 | 0 | 0 | 0 | 4950
1058 | 1205.01 - BW/HS | Platform and ladders ME room FWD
|  | Steel platform to be made in front of main engine. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Platform to be done in angle iron and standard |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | steel pipes. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Steel gratings to be used on platform. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Ladders to be made in order to grant safe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | access to the platform. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Attached pictures from Ficaria, to show how |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | plateu should be made. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | It should be possible to acces pipes from coming |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | BWTS system as well as, floodlights, alarm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | panels and crane. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | All new and touched steel to be painted | QUOTED | 1 | 136200 | 136200 | 0 | 0 | 0 | 0 | 136200
|  | The Owner supplies all paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1116 | 10010.01 - CD | Ballast Water Treatment Plant
|  | Work order Ballast Water Treatment Plant: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1. Mechanical works |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1 Transport and mounting of Owner supplied |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | equipment |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation of: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Main control panel |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Backflush pump |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - CIP Unit |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - DESMI BWTS Unit | QUOTED | 1 | 44710 | 44710 | 0 | 0 | 0 | 0 | 44710
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Pipe & Valve works |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.1 Fabrication and mounting of pipes according |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | to Isometric Catalogue |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication and Installation of: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Ballast water diagram for BWTS - ISO catalog |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | REV.0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Tech. Water supply |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Drain pipe in BWTS room | QUOTED | 1 | 1261616 | 1261616 | 0 | 0 | 0 | 0 | 1261616
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2 Fabrication and mounting of pipe supports |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication and installation of New steel: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Beams and lifting device, 154 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastening of main panel, 69 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastning of BWTS CIP backflush |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | pump, 67 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastening of BWTS CIP dosing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | unit, 32 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastning of BWTS skid 102 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Gratings in Technical compartment |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | modification, 436 kg. | QUOTED | 1 | 52359 | 52359 | 0 | 0 | 0 | 0 | 52359
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.4 Mounting of Owner supplied valves |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation of owner delivered new valves: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE BFV LUG 350 NEX EAN |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | OOF 26 230 PN10 WITH EL.ACTUATOR 230V |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1ph.PN10 HQ060 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE LUG WITH HANDLEVER |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | DN80 PN10 GGG40 MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE LUG WITH GEARBOX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | DN250 PN10 GGG40 MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE LUG WITH GEARBOX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | DN250 PN10 GGG40 MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - NON RETURN VALVE WAFER PN10 DN 80 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - NON RETURN VALVE WAFER PN10 DN 50 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - NON RETURN VALVE WAFER PN10 DN 100 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | MARS VALVE EUROPE | QUOTED | 1 | 42985 | 42985 | 0 | 0 | 0 | 0 | 42985
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.5 Modifications of ballast piping system |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Modification to ballast pipes. | QUOTED | 1 | 91596 | 91596 | 0 | 0 | 0 | 0 | 91596
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.6 Dismantling and removal of non-reusable |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | parts of Ballast system |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Modifications : |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Sheet 31/44: Existing ballast pipe to be modified |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | (The change included in 3897-8.1-WD_801-002). |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Sheet 38/44 : Heater to be removed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Sheet 39/44 : Platform to be modified. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Sheet 42/44 : Cylinder oil tank to be removed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Sheet 43/44 : Hydraulic pipes to WT door to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | be modified | QUOTED | 1 | 181931 | 181931 | 0 | 0 | 0 | 0 | 181931
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subjects in difference report |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | All subjects of mechanical works in the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | difference report. | QUOTED | 1 | 171882 | 171882 | 0 | 0 | 0 | 0 | 171882
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Electrical works: updated price to owner 04.03-22 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Price on electrical works include: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Delivery and installation of cables according cable |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | list. Added extra cable Main panel to BWTS PDB |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | -Termination of fiber optic cable+ Fiber optic |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | converters |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - New breakers in MSB |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Fabricate and install new PDB |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Inst. Of lights, fire detectionand PAGA . |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment not included. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Modifications in bridge panel. (FWD Bridge Consol) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Inst. Remote Panel in CCR |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Modification in fire damper panel in BWTS room |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and Valve mimic panel in safety control room |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Neccessary cabletrays and brackets included |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - 2 pcs of Roxtec penetrations included |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Modifications in Bridge Panel for GPS |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Lamps to be relocated on platform deck |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | - Delivery and installation of ventilation and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | fire damper. | QUOTED | 1 | 755562 | 755562 | 0 | 0 | 0 | 0 | 755562
|  | Price on electrical works is exclusive: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Light fixtures, PAGA, Smoke detector, Call |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Point, Participation on seatrial |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Power supply cable for BWTS valves W3-RM2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | and W4-RM1: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivering and installation of 75 meterpower |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | supply cable |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | The valves is moved from BWTS room to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | engine room. | QUOTED | 1 | 15372 | 15372 | 0 | 0 | 0 | 0 | 15372
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Steel works |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication and installation of New steel: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Beams and lifting device, 154 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastening of main panel, 69 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastning of BWTS CIP backflush |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | pump, 67 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastening of BWTS CIP dosing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | unit, 32 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastning of BWTS skid 102 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Gratings in Technical compartment |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | modification, 436 kg. | QUOTED | 1 | 267450 | 267450 | 0 | 0 | 0 | 0 | 267450
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.1 Fabrication of new BWTS room including |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | access way | QUOTED | 1 | 242946 | 242946 | 0 | 0 | 0 | 0 | 242946
|  | Installation of protection barrier |  | 1 | 26500 | 0 | 0 | 26500 | 0 | 0 | 26500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additionals: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | According to received collision report: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Existing small electrical cabinet to be relocated |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | in ER. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Existing light column to be relocated. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Existing cable tray and ducting to modification. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Lamp to relocation. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Fastening of the pumps start/stop buttons to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | be modified | QUOTED | 1 | 32500 | 32500 | 0 | 0 | 0 | 0 | 32500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additionals based on work done on |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Freesia Seaways: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible delivery of 6 pcs. valves | QUOTED | 1 | 37350 | 37350 | 0 | 0 | 0 | 0 | 37350
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation of cabinet for HMI |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | panel in BWTS room. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of power supply 24 VDC. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of circuit breaker. | QUOTED | 1 | 7770 | 7770 | 0 | 0 | 0 | 0 | 7770
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional new 2 x DN 250 counber valves |  | 1 | 9700 | 0 | 0 | 9700 | 0 | 0 | 9700
1117 | ADD D1 - BW/HS | Crack in plate STB side
|  | Crack in plate SB side just below accomodation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | deck to be cut out and new plate inserted, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | approx. 1000x1000x12 mm, new and touched to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | be painted after repair. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Scafolding from weather deck to below |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | accomodation deck. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Price is based on Ceiling under accomodation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | deck is going to be renewed in are aft of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | cracked plate. | QUOTED | 1 | 88900 | 88900 | 0 | 0 | 0 | 0 | 88900
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners |  | 1 | 5000 | 10000 | 0 | -5000 | 0 | 0 | 5000
1118 | ADD 02 - BW/HS | Steel repair frame 89 PS engine room
|  | Insert of 500 x 300 x 10 mm (A36TM) to be made |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | in webframe. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | See attached pictures and drawings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Damage located in engine room stores room. | CANCELLED | 0 | 82500 | 82500 | -82500 | 0 | 0 | 0 | 0
|  | All accesswork except from staging are done |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible NDT to be agreed with LR and owners | CANCELLED | 0 | 10000 | 10000 | -10000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional access work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1119 | 1102.07A - BW/HS | Steel renewal engine room frame 96-97 PS
|  | Based 1 pcs. Insert and 1 pcs. Girder plate as spec. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | -1 pcs. Transverse bulkhead plate Inserts 500 x |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 300 x 9 mm = 10,5 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | -1 pcs Longitudinal Girder plate 400 x 300 x 7,5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | mm = 7 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. firewatches in multiple compartments. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. covering of electrical cables |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subject to empty, clean tanks ready for hot-work | CANCELLED | 0 | 67000 | 67000 | 0 | -67000 | 0 | 0 | 0
|  | Excl. possible painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1120 | 1102.08A - BW/HS | Installation of manhole in pipe tunnel
|  | Installation of manhole in pipe tunnel | QUOTED | 1 | 32000 | 32000 | 0 | 0 | 0 | 0 | 32000
|  | Excl. possible painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Reinforcement |  | 1 | 15000 | 0 | 15000 | 0 | 0 | 0 | 15000
1121 | 500.11 | Bottom plugs
|  | Price pr. plug off and on | QUOTED | 20 | 200 | 4000 | 0 | 0 | 0 | 0 | 4000
|  | Vacum test per plug | QUOTED | 20 | 200 | 4000 | 0 | 0 | 0 | 0 | 4000
1122 | 500.13 | Man hole covers
|  | Per manhole cover | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on MAX size 600*800mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation of protection on opened manhole, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | per manhole | QUOTED | 20 | 1500 | 30000 | 0 | 0 | 0 | 0 | 30000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Renewal of gaskets. Each | CANCELLED | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Repair of studs: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | By turning out, min 5 pcs per manhole. Each |  | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0
|  | By drilling out, min. 5 pcs per manhole. Each | QUOTED | 50 | 275 | 0 | 0 | 13750 | 0 | 0 | 13750
1123 | 3306.03A | SW cunifer pipe LT coolers
|  | Option 1: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Repair of pipe: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Dis- and remounting of pipe | QUOTED | 1 | 24000 | 24000 | -24000 | 24000 | 0 | 0 | 24000
|  | Necessary repairs: Priced after inspection | VOR 10 | 1 | 33000 | 0 | 0 | 33000 | 0 | 0 | 33000
|  | Additional of pittings in additional pipe | VOR 10 | 1 | 12300 | 0 | 0 | 12300 | 0 | 0 | 12300
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Option 2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible renewal of pipe as spec. | CANCELLED | 0 | 94380 | 0 | 94380 | -94380 | 0 | 0 | 0
1125 | 3306.04A | Turning of scrubber overboard valve
|  | Turning of valve DN600 incl. Modification of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. Hy. pipes | QUOTED | 1 | 28500 | 28500 | 0 | 0 | 0 | 0 | 28500
1127 |  | Rep. of rudder flap in dock
|  | New busing for link-system |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Owners delivered spare parts | VOR 2 | 1 | 200000 | 0 | 200000 | 0 | 0 | 0 | 200000
1128 |  | Paint repair in front of rudder on damaged
|  | area |  | 1 | 20000 | 0 | 20000 | 0 | 0 | 0 | 20000
1129 | VOR 3 | Bridge wings S/P repir comfort insulation, as on Magnolia
|  | Bridge wings S/P repir comfort insulation, as on Magnolia | VOR 3 | 1 | 90000 | 0 | 90000 | 0 | 0 | 0 | 90000
|  | Repair of sprinkler |  | 1 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000
1130 |  | Leaking on shaft coupling
|  | Leaking on shaft coupling | QUOTED | 1 | 35000 | 0 | 35000 | 0 | 0 | 0 | 35000
1131 |  | Flushing and pressure test of pipes in stern tubes.
|  | Flushing and pressure test of pipes in stern tubes. | QUOTED | 1 | 20000 | 0 | 20000 | 0 | 0 | 0 | 20000
1132 |  | Inspection, grinding and welding of 3 pcs cracks in STB
|  | rudder skeg | QUOTED | 1 | 25000 | 0 | 25000 | 0 | 0 | 0 | 25000
|  | Ex paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1133 |  | Check electrical temperature sensor
|  | Check electrical temperature sensor | QUOTED | 1 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000
1134 |  | Repair of crack in wing tank, regarding superintendent
|  | Repair of crack in wing tank, regarding superintendent |  | 1 | 65000 | 0 | 0 | 65000 | 0 | 0 | 65000
1135 |  | Repair of crack in bottom of lover ramp by frame 113 SB.
|  | Repair of crack in bottom of lover ramp by frame 113 SB. |  | 1 | 9500 | 0 | 0 | 9500 | 0 | 0 | 9500
1137 |  | Cleaning of void in connection whit job 1120.
|  | Clearet whit superintend 21/7-23. |  | 1 | 30000 | 0 | 0 | 30000 | 0 | 0 | 30000
1138 |  | Banding of SMO plate after order from superintend
|  | 21/7-23. |  | 1 | 8000 | 0 | 0 | 8000 | 0 | 0 | 8000
1139 |  | Modify and change alu anodes for FWD bow thruster and
|  | FWD stern thruster | QUOTED | 1 | 20000 | 0 | 0 | 20000 | 0 | 0 | 20000
1140 | VOR 7 | Rain guard
|  | Chipping and painting of corroded area before |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | installing of new rain guard for exhuast pipe for scrubber |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation of new rain guard | VOR 7 | 1 | 49800 | 0 | 0 | 49800 | 0 | 0 | 49800
1141 |  | Scaffold inside scrubber for owners SUB.
|  | According to chief engineer instruction. |  | 1 | 35000 | 0 | 0 | 35000 | 0 | 0 | 35000
1142 |  | Cleaning of FO tank 50
|  | Cleaning according to agreement | VOR 9 | 1 | 16500 | 0 | 0 | 16500 | 0 | 0 | 16500
|  | Mud truck | VOR 9 | 6 | 950 | 0 | 0 | 5700 | 0 | 0 | 5700
|  | Disposal per m3 DKK 1.200,00 | VOR 9 | 3 | 1200 | 0 | 0 | 3600 | 0 | 0 | 3600
1143 |  | Dyi check of thruster blades
|  | Dyi check of thruster blades | QUOTED | 1 | 8000 | 0 | 0 | 8000 | 0 | 0 | 8000
1144 |  | Modification of pipe to scrupper valve on funnel top
|  | Modification of pipe to scrupper valve on funnel top | QUOTED | 1 | 21500 | 0 | 0 | 21500 | 0 | 0 | 21500
1145 |  | MPI test on propeller shaft
|  | MPI test on propeller shaft | QUOTED | 1 | 15000 | 0 | 0 | 15000 | 0 | 0 | 15000
1146 |  | New hydr. pipes and fittings on bow thrusters
|  | New hydr. pipes and fittings on bow thrusters | QUOTED | 1 | 26500 | 0 | 0 | 26500 | 0 | 0 | 26500
1147 |  | Brake test for mooring winch
|  | Brake test for mooring winch, 2 pcs |  | 2 | 2860 | 0 | 0 | 5720 | 0 | 0 | 5720
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000
9993 |  | Discount according to agreement
|  | Discount according to agreement | 10% | 1 | -1776757.287 | -1914517 | 169194 | -31434 | 0 | 0 | -1776757
|  | Add. Discount according to agreement |  | 1 | -600000 | -600000 | 0 | 0 | 0 | 0 | -600000
|  | Additonal discount agreed with superintendent |  | 1 | -175000 | 0 | 0 | 0 | -175000 | 0 | -175000
|  |  | DKK |  |  | 17230670 | -1522743 | 282904 | -175000 | 0 | 15815830 | 0