## Chapter 0
Ship name: |  | PEARL SEAWAYS
Case No.: |  | 221228
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-01-10 | 2023-01-18 | 2023-01-31 | 2025-05-06 | Total
1000 |  | Sag
1001 | D200.02 | Docking in/out - Dock hire - voyage
|  | A. Dock/undock and first day dues | QUOTED | 1 | 65000 | 65000 | 0 | 0 | 0 | 65000
|  | B. Cost for subsequent days, each | QUOTED | 19 | 20000 | 400000 | 0 | -20000 | 0 | 380000
1003 | D501.01 | Earthing of vessel
|  | Free of charge, included in docking cost | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1004 | D530.01 | Crane assistance
|  | Based yards rail cranes, up to 45 t, each hour | QUOTED | 30 | 1500 | 45000 | 0 | 0 | 0 | 45000
|  | Based mobile cranes, each normal hour | QUOTED | 10 | 2000 | 20000 | 0 | 0 | 0 | 20000
1005 | D503.01+D504.01 | Fire Line Pressure
|  | Fire Line under pressure max. 5 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Connection, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Supply of SW |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Price per day in service | QUOTED | 20 | 500 | 10500 | 0 | -500 | 0 | 10000
|  | Rental of fire extinguisher |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each per day | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Temporary fire connections |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. at hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1006 | D502.01 | CO2 plant
|  | CO2 plant | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 1200
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 250093 | 100000 | 50000 | 100093 | 0 | 250093
|  | Levering af rustfri plader og profiler i AISI316 | QUOTED | 1 | 25410 | 25410 | 0 | 0 | 0 | 25410
1008 |  | Isolation
|  | Isolation | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1009 | D516.01 | Garbage disposal
|  | Garbage containers (4 m³ + incl. 20 m³) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Garbage container on the quay |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each time emptied, incl. disposal | QUOTED | 35 | 5000 | 300000 | 0 | 325000 | -450000 | 175000
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1011 | D508.01 | Gangways
|  | Gangway, each | QUOTED | 4 | 4000 | 16000 | 0 | 0 | 0 | 16000
|  | Additional cost |  | 1 | 10000 | 0 | 0 | 10000 | 0 | 10000
1012 | D511.01+D512.01 | Cooling for Aux Engines
|  | Cooling water connection for Aux. Engines, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Outlets, each | QUOTED | 4 | 3000 | 12000 | 0 | 0 | 0 | 12000
|  | Supply of Cooling water SW/maintenance per day | QUOTED | 100 | 500 | 52500 | 0 | -2500 | 0 | 50000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cooling for provision |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cooling water connection for provision, each | QUOTED | 2 | 3000 | 6000 | 0 | 0 | 0 | 6000
|  | Supply of Cooling water SW/maintenance per day | QUOTED | 40 | 500 | 21000 | 0 | -1000 | 0 | 20000
1013 | D510.01 | Portable water supply
|  | Potable water connection, each time | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Supply of FW per m³ | QUOTED | 807 | 40 | 8000 | 0 | 24280 | 0 | 32280
1014 | D517.01+D518.01 | Black water disposal
|  | Sewage connection/disconnection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Disposal per m³ | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible use of mud truck, each hour | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gray water disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sewage connection/disconnection | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal per m³ | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible use of mud truck, each hour | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1015 | D519.01 | Oily water disposal
|  | Connection, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Mudtruck per hour - per 5/1-2023 | QUOTED | 12 | 1150 | 13800 | 0 | 0 | 0 | 13800
|  | Disposal per m³ - per 5/1-2023 | QUOTED | 7 | 1200 | 8400 | 0 | 0 | 0 | 8400
|  | Mudtruck per hour - per 17/1-2023 | QUOTED | 24 | 1150 | 0 | 0 | 27600 | 0 | 27600
|  | Disposal per m³ - per 17/1-2023 | QUOTED | 13 | 1200 | 0 | 0 | 15600 | 0 | 15600
1016 |  | Internet Connection
|  | Internet Connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 20 | 500 | 10500 | 0 | -500 | 0 | 10000
1017 | D514.01 | Ballast Water supply
|  | Connection of Ballastwater, each hose | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Supply of ballast water, each m³ | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further assistance with ballasting, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1018 | D525.01 | Gas free certificate
|  | Each gasfree certificate | QUOTED | 2 | 3500 | 7000 | 0 | 0 | 0 | 7000
1020 | D200.03 | Agency + tugs + boarding wages
|  | By own agent | VIA AGENT | 0 |  | 0 | 0 | 0 | 0 | 0
1021 | D300.01 | Painting And Treatment
|  | See unit price in below paint prices. | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1022 | D505.01 | Fire Watch
|  | Fire Watch, incl. in jobs with hot work | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1023 | D506.01 | Watch keeping
|  | For account, see item D 507.01 | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1025 | D515.01 | Ventilation fans
|  | Rental of vent. Fan, each fan per day | QUOTED | 3 | 550 | 0 | 1650 | 0 | 0 | 1650
|  | Ventilation fan connection/disconnection as |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
1026 | D520.01 | Man hole covers
|  | Manhole covers off/on incl. new gasket, each | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1027 | D521.01 | Bottom Plugs
|  | Bottom plugs out/ in, each | QUOTED | 12 | 200 | 2400 | 0 | 0 | 0 | 2400
1033 | D529.01 | Thickness Measurements
|  | Ultrasonic thickness measurements (UTM-based |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | on 1000 spots). Minimum 350 shots, each shot | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. access, staging and lifts |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker, each per day | QUOTED | 3 | 3500 | 21000 | 0 | -10500 | 0 | 10500
1034 | D531.01 | Cherry picker rental
|  | Cherry picker up to 27 meter incl. consumptions, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each per day, max. 12 hour | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1035 | D533.01 | NDT testing
|  | A. Ultrasonic testing (UT) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | B. Magnetic particle Inspection (MPI) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | C. Liquid penetrant inspection (LPI) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | A. B. C. Done by 3rd party, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Force Tecnology has office on the location | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1036 | D1001.01 | Hull Corrosion prevention anodes
|  | a) Type 170 Al (15.3 kg) - 8 pce. | QUOTED | 8 | 1295 | 10360 | 0 | 0 | 0 | 10360
|  | b) Type 114 Al (10.6 kg) - 26 pce. | QUOTED | 26 | 860 | 22360 | 0 | 0 | 0 | 22360
|  | c) Type 60 Al (6.0 kg) - 4 pce. | QUOTED | 4 | 645 | 2580 | 0 | 0 | 0 | 2580
|  | d) Type 43 Al (3.6 kg)- 34 pce. | QUOTED | 34 | 540 | 18360 | 0 | 0 | 0 | 18360
|  | AL 15 (1,5 kg.) each | QUOTED | 16 | 320 | 5120 | 0 | 0 | 0 | 5120
|  | Owner deliver new AL anodes. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional cost for anodes Type 114 Al |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | delivered by Yard |  | 1 | 21320 | 0 | 0 | 21320 | 0 | 21320
|  | Prices are incl. cherry picker, demounting of old, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | mounting of new, welded type, basis min. 50 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | in total |  | 0 |  | 0 | 0 | 0 | 0 | 0
1039 | 1001.04 | Damage SB aft Sponsoon
|  | SB aft damage to be repaired. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | SB aft outside corner of sponsoon to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | renewed app 1000 mm x 2000 mm, including |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaning and painting of new and attached |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel. | QUOTED | 1 | 203070 | 203070 | 0 | 0 | 0 | 203070
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Damaged fender renewal |  | 1 | 18000 | 0 | 18000 | 0 | 0 | 18000
|  | Cherry picker, each per day |  | 2 | 3500 | 0 | 7000 | 0 | 0 | 7000
1040 | 1001.05 | Damage SB at fra 150-153
|  | Repair damage between fr 150-153 SB above |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | car deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hull plating approx. 160 x 9 x 1500 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Web frame insert 400 x 900 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Including cleaning and painting of new and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | attached steel. Reduced price due to less work | QUOTED | 1 | 95350 | 125625 | -30275 | 0 | 0 | 95350
1041 | 1001.06 | Damage fr 162
|  | Repair damage at Fr 162 SB above car deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Insert in web frame approx. 1500 x 400 mm | QUOTED | 1 | 66225 | 66225 | 0 | 0 | 0 | 66225
1042 | 1001.07 | Damage Sb fr 144-147
|  | Repair damage between fr 144-147 SB above |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | car deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Insert webframe approx 1500 x 400mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renew 2 pcs. of bulb HP 140 x 9 x 2000 mm | QUOTED | 1 | 92820 | 92820 | 0 | 0 | 0 | 92820
|  | Paint see job 1188 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1043 | D1016.01 | Sea chest Cleaning and painting
|  | Frame 54-56 SB After chest (Compressor room) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 6,4 m³ | QUOTED | 6 | 1620 | 10368 | 0 | 0 | 0 | 10368
|  | Frame 73-75 SB upper chest (ME room) - 7,5 m³ | QUOTED | 8 | 1620 | 12150 | 0 | 0 | 0 | 12150
|  | Frame 75-78 SB lower chest (AE room) - 11,2 m³ | QUOTED | 11 | 1390 | 15568 | 0 | 0 | 0 | 15568
|  | Frame 109-111 PS (pump room) - 27,6 m³ | QUOTED | 28 | 695 | 19182 | 0 | 0 | 0 | 19182
|  | Based on max 1 m³ disposal per sea chest |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal of mussels |  | 2 | 8500 | 17000 | 0 | 0 | 0 | 17000
1044 | D1016.03 | Sea chest antifouling anodes
|  | 16 pieces of anodes in total, 8 pce CU and 8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pce FE anodes located in 4 sea chests to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | replaced. Each | QUOTED | 16 | 5500 | 88000 | 0 | 0 | 0 | 88000
1047 | D1016.09 | Painting - vertical bottom - upper red ice
|  | breaker belt cleaning, blasting and painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vertical sides - From 4,4 m to 6,9 m: 900 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 900 | 10.5 | 9450 | 0 | 0 | 0 | 9450
|  | Mechanical cleaning, min. 0,25 m² per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | based 3 %, 27 m² | QUOTED | 27 | 113.5 | 3065 | 0 | 0 | 0 | 3065
|  | Wash down with FW, based on 900 m² | QUOTED | 900 | 3.5 | 3150 | 0 | 0 | 0 | 3150
|  | 2 x Tu 1 coat with roller and brush, min. 0,25 m²/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | spot, basis 8%, 72 m² | QUOTED | 144 | 27.5 | 3960 | 0 | 0 | 0 | 3960
|  | Tu 1 coat with roller and brush, min. 0,25 m²/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 90 m² | QUOTED | 90 | 27.5 | 2475 | 0 | 0 | 0 | 2475
|  | 2 x Fc 1 coat with roller and brush, 900 m² | QUOTED | 1800 | 19 | 34200 | 0 | 0 | 0 | 34200
|  | Covering of topside | QUOTED | 1 | 30000 | 30000 | 0 | 0 | 0 | 30000
1048 | D1016.12 | Painting - Diver stribes and markings
|  | Painting existing Cargo and plimsol, thruster |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and bulp markingsmarks | QUOTED | 1 | 5665 | 5665 | 0 | 0 | 0 | 5665
|  | Markings for in water survey to be painted, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | special tape for silicone paint | QUOTED | 1 | 21505 | 21505 | 0 | 0 | 0 | 21505
1049 | D1018.03 | Painting White Topside
|  | White topside: 4700 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 4700 m² | QUOTED | 4700 | 10.5 | 49350 | 0 | 0 | 0 | 49350
|  | Mechanical cleaning, min. 0,25 m²/spot, basis |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 5%, 235 m² | QUOTED | 235 | 103 | 24205 | 0 | 0 | 0 | 24205
|  | Hosing down with Fw, basis 4700 m² | QUOTED | 4700 | 3.5 | 16450 | 0 | 0 | 0 | 16450
|  | 3 x Tu 1 coat with roller and brush, min. 0,25 m²/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | spot, basis 10%, 470 m² | QUOTED | 1410 | 46.25 | 65213 | 0 | 0 | 0 | 65213
|  | Fc 1 coat with roller and brush, 4700 m² | QUOTED | 4700 | 28.5 | 133950 | 0 | 0 | 0 | 133950
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Up lining between blue and white area, 391 m | QUOTED | 391 | 11.5 | 4497 | 0 | 0 | 0 | 4497
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering, cleaning and painting of port holes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | frames, each | QUOTED | 14 | 520 | 7280 | 0 | 0 | 0 | 7280
|  | Covering, cleaning and painting of windows |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | frames, each | QUOTED | 386 | 775 | 299150 | 0 | 0 | 0 | 299150
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additional covering, as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
1050 | D1018.04 | Painting Blue Topside
|  | Blue topside, total areal: 4700 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 4700 m² | QUOTED | 4700 | 10.5 | 49350 | 0 | 0 | 0 | 49350
|  | Mechanical cleaning, min. 0,25 m² / spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 7%, 329 m² | QUOTED | 329 | 103 | 33887 | 0 | 0 | 0 | 33887
|  | Hosing down with Fw, basis 4700 m² | QUOTED | 4700 | 3.5 | 16450 | 0 | 0 | 0 | 16450
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | spot, basis 12%, 564 m² | QUOTED | 564 | 46.25 | 26085 | 0 | 0 | 0 | 26085
|  | Tu 1 coat with roller and brush, min. 0,25 m² / |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | spot, basis 12%, 564 m² | QUOTED | 564 | 46.25 | 26085 | 0 | 0 | 0 | 26085
|  | Fc 1 coat, 4700 m² | QUOTED | 4700 | 14.25 | 66975 | 0 | 0 | 0 | 66975
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Up lining between blue and white area, 600 meter | QUOTED | 600 | 11.5 | 6900 | 0 | 0 | 0 | 6900
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting existing name and homeport | QUOTED | 1 | 6170 | 6170 | 0 | 0 | 0 | 6170
|  | Painting of existing logo "DFDS" Stb and Ps | QUOTED | 1 | 38640 | 38640 | 0 | 0 | 0 | 38640
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering, cleaning and painting of windows |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | frames, each | QUOTED | 50 | 775 | 38750 | 0 | 0 | 0 | 38750
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additional covering, as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
1051 | D1018.05 | Painting - windows Fore part Restaurants
|  | Fore part deck 6-8 as well as bridge deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bottom, to be treaded as following: | QUOTED | 1 | 79200 | 79200 | 0 | 0 | 0 | 79200
|  | HP wash with 170 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, min. 0,25 m²/spot. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on 5% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hose down 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu. 2 coat, with roller and brush, min. 0,25 m²/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | spot. Based on 5% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc. 1 coat, with roller and brush |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering of windows. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sealing of windows in bottom with dark |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | silicone outside and 100 mm up each side | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1053 | 1018.23 | Bridge
|  | Out side painting of brigde house. (300m²), to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be treaded as following: | QUOTED | 1 | 171286.5 | 171287 | 0 | 0 | 0 | 171287
|  | HP wash with 170 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, min. 0,25 m²/spot. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on 10% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hose down 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu. 2 coat, with roller and brush, min. 0,25 m²/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | spot. Based on 10% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering of windows. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sealing of windows in bottom with dark |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | silicone outside and 100 mm up each side | QUOTED | 1 | 14960 | 14960 | 0 | 0 | 0 | 14960
1054 | D1041.01 | Rudder pressure test
|  | Each test each rudder | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bottom plugs to be released with DNV |  | 2 | 500 | 1000 | 0 | 0 | 0 | 1000
1055 | D1041.02 | Rudder bearing and jump stop clearance
|  | Staging each rudder/each side | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rudder- bearing and jump stop clearance, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each rudder | QUOTED | 2 | 5000 | 10000 | 0 | 0 | 0 | 10000
|  | Demount/refit of rudder access plates, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker, each per day | QUOTED | 1 | 3500 | 3500 | 0 | 0 | 0 | 3500
1060 | D1102.03 | FWD mooring station
|  | STB side: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ceiling approx. 3 m² to be repaired. (stainless |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steal plates) | QUOTED | 1 | 19270 | 19270 | 0 | 0 | 0 | 19270
|  | Bulkhead to be treated: Mechanical cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bulkhead to be treated with 2 times primer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (damaged area) and 1 time topcoat |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Updated price due to new scope | NEW PRICE | 1 | 23400 | 23400 | 0 | 0 | 0 | 23400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Center forward: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bulkhead to be mechanical cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bulkhead to be painted with 2 times primer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (damaged area) and 1 time topcoat |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Updated price due to new scope | NEW PRICE | 1 | 57850 | 57850 | 0 | 0 | 0 | 57850
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bulkhead to be treated with 2 times primer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (damaged area) and 1 time topcoat. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be priced after dismantling and repair of steel. | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1061 | D1102.04 | Corrosion in top of seachest
|  | Sea chest in pump room: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sea chest corroded on top corner plate (corner |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | between heeling tank and shipside). |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Also stifferne is heavily corroded and need to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be changed. | QUOTED | 1 | 66350 | 66350 | 0 | 0 | 0 | 66350
|  | All touched steel (both sides) to be repainted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | according to paint spec. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access demounting pipe + new flange |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | connection top sea chest |  | 1 | 8800 | 0 | 8800 | 0 | 0 | 8800
1062 | D1108.01 | Car deck and aft ramps- blasting and painting
|  | Cardeck to be painted according to below: | QUOTED | 1 | 262492.2 | 262492 | 0 | 0 | 0 | 262492
|  | HP wash with soap. 3411 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, basis 5%, 170.55 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Wash with FW. 3411 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat with ruller and brush, basis 5%, 170.55 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat with ruller and brush, basis 5%, 170.55 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of edges |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat on 3411 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint of lane marking, aprox 1000 meter. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint drains, 16 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint of lane numbers. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional: Tu 1 coat with ruller and brush, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 5%, 170.55 m² |  | 1 | 7888 | 7888 | 0 | 0 | 0 | 7888
|  | Additional for 1 x FC done with roll - reduction |  | 1 | 18080 | 0 | 53080 | -35000 | 0 | 18080
1063 | D1108.02 | Cardeck Ramp
|  | Applicable for two cardeck ramps: 1PS & 5SB. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cardeck Ramp SB on spots |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning/ mejselhammer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TU 2 coat incl. sand |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. - nyt scope | QUOTED | 1 | 25900 | 25900 | 0 | 0 | 0 | 25900
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cardeck Ramp PS front remove all |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning/ mejselhammer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TU 2 coat incl. sand |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. - nyt scope | QUOTED | 1 | 54100 | 54100 | 0 | 0 | 0 | 54100
1073 | D1114.11 | Painting- Ballast Tk. 1301 + 1302 painting
|  | and anodes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ballast Tk 1301 - 95 m³, basis 285 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on empty and open tank: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of tanks by flushing through bottom |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | plug, based on in side flush bottom plugs | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible disposal of mud per m³ | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access hole in shell plate | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scaffolding in dock bottom for access to tank | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scaffolding in tank | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Note: Scope to be agreed after completion of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TU 3 coat inside tank |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TU 2 coat in room above tank |  | 1 | 85540 | 0 | 0 | 85540 | 0 | 85540
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ballast Tk 1302- 95 m³, basis 285 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on empty and open tank: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of tanks by flush through bottom |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | plug | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible disposal of mud per m³ | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access hole in shell plate | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scaffolding in dock bottom for access to tank | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scaffolding in tank | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Note: Scope to be agreed after completion of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TU 3 coat inside tank |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TU 2 coat in room above tank |  | 1 | 76160 | 0 | 76160 | 0 | 0 | 76160
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Manhole covers removed and refitted with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | existing gaskets, each | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible supply of new yard standard rubber |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | gaskets, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible heating or dehumidifier. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account. | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1077 | D1120.01 | Ramps and Hatch Covers - overhaul
|  | Yard assistance to McGreggor, see job 1158 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1078 | D1123.01 | Ceiling Mooring Deck (Deck 5)
|  | Ceiling on aft mooring to be repaired/renewed: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount existing ceiling plates, delivery and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | installation of new ceiling plates in stainless |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel. 2 plates in PS and 2 plates in STBD. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New plates to be painted. 2x primer and 1x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | topcoat | QUOTED | 1 | 20480 | 20480 | 0 | 0 | 0 | 20480
|  | 2 pcs. additional plates, all galvanied, so price |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | remaines |  | 0 |  | 0 | 0 | 0 | 0 | 0
1079 | D1123.02 | Window Deck 6 aft
|  | Window PS aft on deck 6/7 embarcation deck: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Window to be removed and closed of by steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | plate. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount flashing and insulation around |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | window coaming for access to steel work, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reestablish of insulation and installation of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | coverplate on light bulkhead |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New plate to be painted after instalation 2x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | primer and 1x topcoat | QUOTED | 1 | 56020 | 56020 | 0 | 0 | 0 | 56020
|  | Crew to remove and reinstall shelvings in front |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of window. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1081 | D1130.35 | Deck 6 BZ PS+SB SPA bottom renewal,
|  | Steel, Treatment & Painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ceiling plates below 2 pcs. Spa on deck 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | mooring deck: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount ceiling plates and insulation under |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | SPA’s for access to steelwork, reestablish of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | same with new insulation and 80% existing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ceiling plates and 20% new ceiling plates. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on 14 m² in PS and 14 m² in STBD. | QUOTED | 1 | 68770 | 68770 | 0 | 0 | 0 | 68770
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New drain in STB spa, access in steel deck and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | modification of piang |  | 1 | 27430 | 0 | 27430 | 0 | 0 | 27430
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All corroded steel to be repaired/ renewed as |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | found necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be priced after ceiling removal and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | agreement of work scope. | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ceiling below pool: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount cladding and insulation on pool sides, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bottom and ceiling 1 meter out from pool side, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | delivery and installation of new insulation, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | substructure and cladding of same, made in |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | stainless steel plates. Total of 60 m². | QUOTED | 1 | 177740 | 0 | 177740 | 0 | 0 | 177740
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All marked galvanized pipes to be renewed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | please see attached. To be priced after ceiling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | removal and agreement of work scope. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Budget price for renewing of marked plastic |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pipes, based no existing supports and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | penetrations can be reused | QUOTED | 1 | 233000 | 200000 | 0 | 33000 | 0 | 233000
|  | OBS: Steel pipes |  | 0 |  | 0 | 0 | 0 | 0 | 0
1082 | D1130.36 | Steel, Treatment & Painting
|  | Steel repair to be done according to the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | attacehed steel calculation from DTMS: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Following prices are estimated budget prices |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and to be adjusted after final agreement of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | work scopes. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Car Deck Frame # -5 to #46 Sketch S1: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A: 600 x 10000 x 13 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A2: 600 x 4000 x 13 mm - add. steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A10: 3260 x 1000 x 13 mm - cancelled |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total steel Car Deck Frame # -5 to #46: 1.138 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | kg steel. | NEW PRICE | 1 | 225000 | 281450 | -56450 | 0 | 0 | 225000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Insulation access in the following locations |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with ref. to thickness measurement report Car |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck Frame # -5 to #46: for access to hotwork: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sketch S1:-A10, Demount and reestablish |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | insulation in deckhead. Approx. 10 m². | CANCELLED | 0 |  | 25000 | 0 | -25000 | 0 | 0
|  | All other access exept scaffolding is as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Car Deck Frame # 47 to #120 Sketch S2: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A1: 600 x 300 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A2: 1000 x 300 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A3: 300 x 2100 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A4: 500 x 300 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A5: 300 x 5100 x 12 mm - above |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Switch Board, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Car Deck Frame # 47 to #120: 268 kg steel. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Welding up and grinding of corroded areas |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | only. (no insert of steel) | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Insulation access in the following locations |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with ref. to thickness measurement report Car |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck Frame # 47 to #120: for access to hotwork: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sketch S2: A1 and A2, Demount and reestablish |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | insulation in deckhead. Approx. 2 m². | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All other access exept scaffolding is as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Car Deck Frame # 121 to #160 Sketch S3: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A1: 1000 x 300 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A2: 300 x 800 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A3: 600 x 300 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A4: 4000 x 700 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A5: 800 x 800 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Car Deck Frame # 121 to #160: 399 kg steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Welding up and grinding of corroded areas |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | only. (no insert of steel) | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Insulation access in the following locations |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with ref. to thickness measurement report Car |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck Frame # 121 to #160: for access to hotwork: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sketch S3: A1, A2, A3, A4. and A5, Demount |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and reestablish insulation in deckhead. | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All other access exept scaffolding is as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tank Top, Deck No. 2 PS: WBT No.1302 fr. #33- |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 100mm to #46+100mm. Sketch S4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A: 6.500 x 2.000 x 7 mm - reduced |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 9 x HP profiles + brackets |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Deck No. 2 PS: WBT No.1302 fr. #33- |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 100mm to #46+100mm.: 1.823 kg steel | NEW PRICE | 1 | 445000 | 480000 | -35000 | 0 | 0 | 445000
|  | Demount and reinstall 3 meters of bulkhead |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | panels and insulation 500mm up on FR#46: | CANCELLED | 0 |  | 20000 | -20000 | 0 | 0 | 0
|  | All other access exept scaffolding is as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of new and affected areas to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | priced after agreemrnt of work scope: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | See job 1188 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tank Top, Deck No. 2 SB: WBT No.1301 fr. #33- |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 100mm to #46+100mm. Sketch S5 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deck plate A1: 10.600 x 3.070 x 7 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional 9 pcs. HP deck beams |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | LONG BHD: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | BHD PLATE B1: 900 x 300 x 8 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | BHD PLATE B2: 600 x 800 x 8 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Deck No. 2 SB: WBT No.1301 fr. #33- |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 100mm to #46+100mm.: 1.871 kg steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel weight | NEW PRICE | 1 | 622390 | 500000 | 122390 | 0 | 0 | 622390
|  | Demount and reinstall 3 meters of bulkhead |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | panels and insulation 500mm up on FR#46: | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
|  | All other access exept scaffolding is as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of new and affected areas to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | priced after agreemrnt of work scope: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | See job 1188 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transverse WT BHT Fr.: #194. FOREPEAK, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sketch S6: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TRANSVERSE WT BHD FR.#194: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | BHD PLATE A1: 3.600 x 300 x 12 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | BHD PLATE A2: 300 x 1.500 x 11 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional stringer renewed/bulkhead to forepeak |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Transverse WT BHT Fr.: #194. FOREPEAK.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 144 kg steel | NEW PRICE | 1 | 175000 | 145000 | 30000 | 0 | 0 | 175000
|  | Access for renewing of steel, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | El cables demounting + mounting |  | 1 | 14500 | 0 | 14500 | 0 | 0 | 14500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Inner Bottom Plating in Boiler room, Sketch S7: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | INNER BOTTOM PLATE A1: 800 x 1250 x 10 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Inner Bottom Plating in Boiler room: 76 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel. | QUOTED | 1 | 120000 | 120000 | 0 | 0 | 0 | 120000
|  | Access for renewing of steel, as per account. | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transverse W.T. Bulkhead Fr.: #109 PS Engine |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | room, Sketch S8: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TRANSVERSE WT BHD FR.109: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | BHD PLATE A1: 2.000 x 300 x 8 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total Transverse W.T. Bulkhead Fr.: #109 PS |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Engine room: 39 kg steel. | QUOTED | 1 | 90000 | 90000 | 0 | 0 | 0 | 90000
|  | Access for renewing of steel, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of F.O. tanks - see job 1160 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sea Chest PS: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TANK TOP PLATE A1: 600 x 400 x 15 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | See item D 1102.04 / job 1061 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | FWD Section Trans. W.T. Bulkhead PS, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Stabilizer Room. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | FWD BHD PLATE A1: 2.300 x 300 x 15 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total FWD Section Trans. W.T. Bulkhead PS, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Stabilizer Room: 83 kg steel. | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access for renewing of steel, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Re-welding only + MPI | NEW PRICE | 1 | 25000 | 25000 | 0 | 0 | 0 | 25000
1083 | D1201.02 | Anchors, Chains, Chain Locker
|  | Anchors and chains ranged in dock, hp, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | messured and marked with steel band | QUOTED | 1 | 34000 | 34000 | 0 | 0 | 0 | 34000
|  | Painting of anchors and chains | QUOTED | 1 | 15400 | 15400 | 0 | 0 | 0 | 15400
|  | Possible painting of chain length markings as |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of chainlocker: | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional cleaning for painting and painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to be priced after inspection of chain lockers | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Posible staging, price after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1084 | D1201.03 | Anchors
|  | Worn areas on anchor to be filled by welding. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Approx. 5 kg material to be welded on each |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | anchor. | QUOTED | 1 | 23000 | 23000 | 0 | 0 | 0 | 23000
1090 | D1302.04 | Mooring Winch Tension
|  | Tension system to be inspected and adjusted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | by subcontractor PennoMarine |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Subcontractor: PennoMarine | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1091 | D1303.01 | Steering Gear & Accessories
|  | Job to be performed by Kongsberg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Change of feed back motors and belts on |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | handles for Pitch propellers on bridge. | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1092 | D1309.01 | Service of Heeling System
|  | For yard information only | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1093 | D1312.01 | Blowers Cardeck
|  | Insulation to be repaired in one (deck 5 SB) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation channel for cardeck ventilation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mounting of new isolation and new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | protection cover for the insulation | QUOTED | 1 | 32350 | 32350 | 0 | 0 | 0 | 32350
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting fan inside |  | 1 | 9750 | 0 | 0 | 9750 | 0 | 9750
1094 | D1401.02 | Life Boats - lift off
|  | Life boats taken ashore and back, each | QUOTED | 8 | 10000 | 80000 | 0 | 0 | 0 | 80000
|  | Transported to inside store and return, incl. 7 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | days in store | QUOTED | 8 | 8000 | 64000 | 0 | 0 | 0 | 64000
|  | FRB taken ashore for polishing and return to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | vessel | QUOTED | 2 | 7500 | 15000 | 0 | 0 | 0 | 15000
|  | Additional days inside workshop, each day |  | 8 | 4000 | 32000 | 0 | 0 | 0 | 32000
1095 | D1401.03 | Wires for lifeboats Davits
|  | Wires to be changed on all lifeboats including |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | MOB. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Jobe to be done by owners subcontractor | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scaffolding | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 25000
|  | Crane assistance incl. job 1004 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1097 | D2201.23 | Furnitures and Fixtures
|  | Window bottom plate at Frh. Lounge to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | changed: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount existing bottom plates at 3 windows, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | delivery and installation of new bottom plates |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | in stainless steel with backplate in IMO |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | approved material. | QUOTED | 1 | 32460 | 32460 | 0 | 0 | 0 | 32460
|  | 1 additional window |  | 1 | 10820 | 0 | 10820 | 0 | 0 | 10820
1098 | D2202.01 | Lifts
|  | Change internal door at lift 10. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Job will be performed by subcontractor |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ordered by DFDS | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1099 | D2701.02 | Ventilation cleaning
|  | Clanning of ventilation Cannels in accomondation: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Galley exhaust: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of horizontal exhaust duchess in |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Galley, hot Galey and Pizza using existing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | access holes and hatches, as done in 2021 | QUOTED | 1 | 134980 | 134980 | 0 | 0 | 0 | 134980
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cabin exhausts: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of exhaust ventilation from 703 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cabins, using existing access holes and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hatches and cabinets. Add. 187 pcs. cabins. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total 890 cabins | QUOTED | 1 | 508174 | 401400 | 106774 | 0 | 0 | 508174
1100 | D2701.03 | AC 3:2, change of reheat piping
|  | Renewal of reheat and preheat piping below |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation unit.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Change of 2 pcs. of 3"" pipes incl 4 pcs. of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bends app. 10 meters |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Change of 2 pcs. of 6"" pipes incl 4 pcs. of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bends app. 10 meters |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipes to be mounted in existing pipe supports |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and insulated with 13 mm Armaflex. | QUOTED | 1 | 174640 | 174640 | 0 | 0 | 0 | 174640
|  | Reduced scope |  | 1 | -70000 | 0 | -70000 | 0 | 0 | -70000
1101 | D2701.04 | Ventilation - & Air Condition System
|  | Upgrade of ventilation control system |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | External compagny to be ordered by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In order to upgrade the ventilation control |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | system | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1102 | D2701.05 | Ventilation duct repair
|  | Demount existing ducting, delivery, and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | installation of new ducting made in 1mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | galvanized sheet metal. Including insulation of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ducts where applicable: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ventilation channels below AC 4:2: To be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | changed total of 3 reduction sections and one |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bend. Duct size 1600x1000mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ventilation channels below AC 3:5: Total of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | one reduction section, one bend and 6 x 6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | meters of straight duct below AC. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AC 2:6 – Duct will be repaired from inside: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total of 1.5 meters, duct size 1600x1000mm. | QUOTED | 1 | 327460 | 327460 | 0 | 0 | 0 | 327460
1103 | D2713.01 | Pantry and Laundry Equipment/machinery
|  | Doors for cooling rooms in Hot and cold |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | galley to be changed . – 110k (Huurre, Oslo) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Job to be done by subcontractor ordered and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | paid by DFDS | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1104 | D2730.01 | Radio, TV, Video
|  | Scene Columbus |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Electrical connections, cables switches- sound |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to be overhauled, by owners specialist | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1105 | D3103.01 | Renk Gear and geislinger damper -
|  | Bearings/damper |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renk Gear ME 3+4 bearing change inner and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | outer. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 4 pc Roller bearing pos 5360 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 4 pc Roller bearing pos 5360 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 2 pc Roller bearing pos 5370 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 2 pc Roller bearing pos 5371 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 4 pc V-ring pos 5973 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - felt strip pos 1314 and 1315 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 4 pc ring pos 5731 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 4 pc ring pos 5735 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 8 pc ring pos 5937 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Geislinger coupling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Driveline for engine #3 to be overhauled |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Power intake shafts on both PS and SB side |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | gear box (4 pce in total) to have bearings |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | exchanged. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - In addition to above yard quote shall cover |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | include rigging and transportation to and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from work shop. | QUOTED | 1 | 682500 | 682500 | 0 | 0 | 0 | 682500
|  | Reduction due to Geislinger coupling not done |  | 1 | -48000 | 0 | 0 | -48000 | 0 | -48000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard supply: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - rigging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - transports |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - lightning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 4 chain blocks for approx. 3500 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - eye-bolts M30 and M20. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible further assistance to owners |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | specialists: Each person per 12 hours shift | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Owners supply: Spare parts |  | 0 |  | 0 | 0 | 0 | 0 | 0
1106 | D3123.01 | Fuel System
|  | Change drain valve at HFO service tank. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Job to be done by Crew | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1107 | D3128.01 | Air Cooler & Air Filter, Air Duct
|  | Change charge air cooler ME3 (Overhauled |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | placed at stock, Oslo) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Change by crew | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1108 | D3128.02 | Air Cooler & Air Filter, Air Duct
|  | Change gaskets to charge air cooler at all ME. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Between charge air cooler and in- and outlet |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pipes. Changed by Crew | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1109 | D3138.02 | ME exhaust pipe after Turbo charger
|  | Isolation on all 4 ME needs to be renewed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | including new cladding. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Diameter of exhaust pipes DN800 ( 813 mm) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Thickness of insulation 100 mm approx. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | outher diameter 1013 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount existing cladding and insulation on |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 21 meters and 7 elbows of exhaust pipe, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | delivery and installation of new insulation and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cladding for same made in galvanized cladding: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ME1 approx 7 meters and two elbows to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | changed. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ME2 approx 2 meter and one elbow to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | changed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ME3 approx. 5 meters and one elbow to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | changed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ME4 approx. 7 meters and 3 elbows to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | changed | QUOTED | 1 | 379200 | 379200 | 0 | 0 | 0 | 379200
1110 | D3138.03 | ME exhaust pipe manifold
|  | Covers on exhaust manifold on 4 pcs ME to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | re isolation inside. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covers to be dismantled by crew and numbered. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard to demount existing perforated plate and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | insulation inside Hotbox covers, delivery and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | installation of new 75mm ceramic insulation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and perforated plate in stainless steel. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | After reneval of insulation covers to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reinstalled by crew | QUOTED | 1 | 184000 | 184000 | 0 | 0 | 0 | 184000
|  | Crew to dismantle and remount of covers, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | deliver the covers on deck 3 and and pick up |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | again on deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
1112 | 3306.02 | Cooling Water Pipes
|  | Change of Rubber compensators Cooling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | water and lub oil, ME room. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be done by Crew | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1113 | D3317.01 | Cleaning and change of gaskets on Lub oil
|  | coolers ME |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning and change of gaskets on ME lub oil |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | coolers ME 1 + ME 2 + ME 3+ ME 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Job no. 921+924+925+926 | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1114 | 3331.01 | Generators
|  | Emergency generator |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Major Service to be performed at emergency |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | generator. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Job to be done by DFDS Sub contractor | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1115 | D3332.02 | Emergency Switch Board
|  | Below currrent transformres to be changed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. Current transformers section 4. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 6 pcs. Current transformers at section 2. | QUOTED | 1 | 21800 | 21800 | 0 | 0 | 0 | 21800
|  | Price is exclusive: Modification of copper bars |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | if necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1116 | D3332.03 | Main Switchboard, Electrical Instruments
|  | Change of Breakers in Stb. MSB |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 8 pcs. of owner delivered breakers to be changed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with new. Total price 8 pcs. | QUOTED | 1 | 14800 | 14800 | 0 | 0 | 0 | 14800
|  | Based on new breakers is as plug and play. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1117 | D3338.01 | Ship side outlets cleaning
|  | Ship side under water pipe outlets to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaned for hard marine fouling by scraping. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning to be done in pipe the hole way to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | the over board/scupper valves. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipes to be coated internally with two coats of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | anticorrosive/anti fouling paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each pipe | QUOTED | 18 | 3696 | 66528 | 0 | 0 | 0 | 66528
|  | All outlets to be mounted with plugs to avoid |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | water on hull paint. See item D1016.08 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1118 | D3338.02 | Scupper valves
|  | Overhaul of scubber valve from deck, each | QUOTED | 5 | 6175 | 30875 | 0 | 0 | 0 | 30875
|  | Hose test, each | QUOTED | 5 | 500 | 2500 | 0 | 0 | 0 | 2500
|  | Scupper valves opened/closed for inspection, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 24 pcs., each |  | 24 | 2860 | 68640 | 0 | 0 | 0 | 68640
|  | Replacement of owner delivered scubber |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | valve. Each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of owner delivered scubber valve, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | is based on plug and play. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The prices is based on free access to scrubber |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | valves and excl. possible repairs of valves and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | remoute controls. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 pcs. additional scupper valves overhauled |  | 3 | 6175 | 0 | 0 | 18525 | 0 | 18525
1119 | D3338.03 | Ship side valves
|  | Shipside according to specified valves list to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be opened/closed and overhauled and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | approved by DNV surveyor. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total 40 pcs of valves to be overhauled for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | approval of DNV | QUOTED | 1 | 99110 | 99110 | 0 | 0 | 0 | 99110
|  | The prices is based on free access to valves, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | butterfly valves standard overhaul/cleaning, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | in situ. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. possible remote controls and actuators |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pc. DN 50 valve off/on for repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pc. DN 250 butterfly valve and actuator off/on |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 pcs. pipes off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Misc. floorboards off/on, remote control off/on, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | access and work beneath floorboards |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total: |  | 1 | 24700 | 24700 | 0 | 0 | 0 | 24700
1120 | D3341.01 | Overhaul of 4 pcs. ME room fans
|  | 4 pcs. ME Room fans situated in center of fan |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | room between fr. 61-66 on deck 11 to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | overhauled: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dismount/ remount motor and fan incl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | transport to/from workshop. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Motor is washed, oven dried and evt. varnished |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bearings renewed. (Owner supply) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Balancing of blower fan. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Meggertest and report. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Price 4 pcs. | QUOTED | 1 | 118600 | 118600 | 0 | 0 | 0 | 118600
|  | Price is exclusive: Materials and possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on e-motors are max. 35 KW |  | 0 |  | 0 | 0 | 0 | 0 | 0
1121 | D3401.05 | Overboard Flange
|  | Overboard flange for the Boiler to be changed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with new treaded flange. | QUOTED | 1 | 24100 | 24100 | 0 | 0 | 0 | 24100
|  | Price is excl. cleaning and painting of new and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | affected areas |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vaccum truck, each hour - per 9/1-2023 | QUOTED | 4 | 1150 | 4600 | 0 | 0 | 0 | 4600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Modification of pipe inside |  | 1 | 2350 | 0 | 2350 | 0 | 0 | 2350
1122 | D3411.01 | Exh. Boiler ME - INFO
|  | Main engine Economizer. (deck 11+12) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be repaired according to inspection report | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1123 | D3411.05 | Washing of exhaust boilers for ME & AE
|  | 2 pcs. of exhaust gas boilers for Aux to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | opened (2 minor covers on each boiler) and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaned to the satifaction of ships crew. | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Before cleaning, exhaust pipes to be blinded |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to avoid any water entering auxillary engines. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Only 2 pcs. of exhaust gas boilers for ME to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | opened (4 covers on each boiler) and cleaned |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to the satifaction of ships crew. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Before cleaning, exhaust pipes to be blinded |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to avoid any water entering main engines. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Price to be updated - only ME 1 & 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of 2 pcs. Exhaust for ME |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Open/closing of boilers |  | 1 | 69810 | 0 | 0 | 69810 | 0 | 69810
|  | Mudtruck |  | 1 | 17250 | 0 | 0 | 17250 | 0 | 17250
|  | Oily disposal 10 m³ |  | 1 | 12000 | 0 | 0 | 12000 | 0 | 12000
|  | Assistance, materials |  | 1 | 19550 | 0 | 0 | 19550 | 0 | 19550
1124 | D3801.02 | Propeller- polish
|  | Main propellers Bronze CuNiAl. Propeller |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | diameter is 4.8 metres. Kamewa Hub 157 XF3/4: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | A: All 8 propeller blades to be polished. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each blade | QUOTED | 8 | 10000 | 80000 | 0 | 0 | 0 | 80000
|  | B: All blade edge to be crack tested by dye |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | checked. / 8 blades. Each blade | QUOTED | 8 | 5000 | 40000 | 0 | 0 | 0 | 40000
1125 | D3801.03 | Propeller, Lifting and inspection of propeller
|  | blades |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Main propellers Bronze CuNiAl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Propeller diameter is 4.8 metres. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Kamewa Hub 157 XF3/4, 1800 kg each blade |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | A, D, F: Loosening of all propeller blades bolt |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | head size 85 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mounting all blades in place after overhaul. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tightening of all bolts - Torque 16800 Nm and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | securing bolts. Each blade | QUOTED | 8 | 20000 | 160000 | 0 | 0 | 0 | 160000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | B: Transport of 2x4 blades from dry dock |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to Fayard work shop and return. Each blade | QUOTED | 8 | 4600 | 36800 | 0 | 0 | 0 | 36800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | C: Machining of blade foot excl. transport to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and from workshop. Each blade | QUOTED | 7 | 25000 | 175000 | 0 | 0 | 0 | 175000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rental of hydraulic tool for blade bolts | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 25000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on propeller hub is drained and refilled |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | by crew. Owner Supply: Spare parts, Oil |  | 0 |  | 0 | 0 | 0 | 0 | 0
1126 | 3801.04 | Propellers, hubs & ropeguard
|  | Main propellers Kamewa 157 XF3/4: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Prices each side: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scaffolding | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 0 | 20000
|  | Draining of sterntupe oil and refilling by crew | QUOTED | 2 | 8000 | 16000 | 0 | 0 | 0 | 16000
|  | Draining of Hub oil incl. disposal and filling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | after repair | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 0 | 20000
|  | Dismantling and mounting of 4 pcs. of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | propeller blades - see job 1125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dismantling and refitting of outer shaft seal - |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | see job 1128 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transport of 4 pcs. of propeller blades from |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | dock to and from Fayard work shop - see job 1125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dismantling and refitting of propeller hub |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Promas | QUOTED | 2 | 29200 | 58400 | 0 | 0 | 0 | 58400
|  | Dismantling and refitting of propeller hub |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from propeller shaft | QUOTED | 2 | 147500 | 295000 | 0 | 0 | 0 | 295000
|  | Rental of hydraulic tools for tightening of bolts |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | See job 1125 | CANCELLED | 0 |  | 25000 | -25000 | 0 | 0 | 0
|  | Transport of propeller hub from dock, to and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from Fayard work shop | QUOTED | 2 | 6500 | 13000 | 0 | 0 | 0 | 13000
|  | Possible further assisance to owners specialist, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each person per 12 hour shift | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Prices based on propeller hub can be dismantlet |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with-out disconnecting and moving the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | propeller shaft and excl. dismantling of the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | rudder blade. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | SKF/Kongsberg Service engineer to be ordered |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and paid by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | General: Excl. spare parts, oil and special tools |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Refill of oil by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transport 2 x HUBto Kongsberg workshop |  | 1 | 15000 | 15000 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ordering spareparts: O-rings |  | 1 | 4500 | 0 | 4500 | 0 | 0 | 4500
1127 | D3802.01 | Tail shaft wear down
|  | Staging. Each side - see job 1126 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demounting / refit of Rope guard, each | QUOTED | 2 | 20000 | 40000 | 0 | 0 | 0 | 40000
|  | Renewal of owners delivered anodes (6 pcs, 1 kg) | QUOTED | 2 | 5500 | 0 | 11000 | 0 | 0 | 11000
|  | Blasting and painting of rope guards. Each | QUOTED | 2 | 5150 | 0 | 10300 | 0 | 0 | 10300
1128 | D3802.02 | Stern Tubes - Outer and inner seals to be
|  | changed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | PS and SB stern seals to be changed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Outher seal type Simplex SC-1 size 630 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | seal to be renewed. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging. Each side - see job 1126 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Drain of oil, refill by crew. Each side | QUOTED | 2 | 16000 | 32000 | 0 | 0 | 0 | 32000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard assistance to owners specialist. Each |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | person per 12 hour shift |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to timesheet per 7/1-23 | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  | According to timesheet per 8/1-23 | QUOTED | 1 | 21000 | 21000 | 0 | 0 | 0 | 21000
|  | According to timesheet per 9/1-23 | QUOTED | 1 | 8500 | 8500 | 0 | 0 | 0 | 8500
|  | According to timesheet per 10/1-23 | QUOTED | 1 | 9500 | 0 | 9500 | 0 | 0 | 9500
1131 | D3812.01 | Stabilizers - Inspection
|  | Staging by stabilizer pocket, each | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 0 | 20000
|  | Drain of oil out side, each stabilizer | QUOTED | 1 | 24000 | 24000 | 0 | 0 | 0 | 24000
|  | Possible cut out in shell plating for draining of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | oil, each stabilizer | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Oil to be filled by crew. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further assistance to owners specialist. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour shift. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to timesheet per 3/1-23 | QUOTED | 1 | 12000 | 12000 | 0 | 0 | 0 | 12000
|  | According to timesheet per 4/1-23 | QUOTED | 1 | 73000 | 73000 | 0 | 0 | 0 | 73000
|  | According to timesheet per 5/1-23 | QUOTED | 1 | 42000 | 42000 | 0 | 0 | 0 | 42000
|  | According to timesheet per 6/1-23 | QUOTED | 1 | 65000 | 65000 | 0 | 0 | 0 | 65000
|  | According to timesheet per 7/1-23 | QUOTED | 1 | 65550 | 65550 | 0 | 0 | 0 | 65550
|  | According to timesheet per 8/1-23 | QUOTED | 1 | 68850 | 68850 | 0 | 0 | 0 | 68850
|  | According to timesheet per 9/1-23 | QUOTED | 1 | 84100 | 84100 | 0 | 0 | 0 | 84100
|  | According to timesheet per 10/1-23 | QUOTED | 1 | 55500 | 0 | 55500 | 0 | 0 | 55500
|  | According to timesheet per 11/1-23 | QUOTED | 1 | 36000 | 0 | 36000 | 0 | 0 | 36000
1133 | ADD 2 | Corroded frames SB in Sewage room frame
|  | #120 and #121 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. of corroded frames to be renewed: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. bulb 240 x 1000 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. bulb 320 x 1000 mm. | QUOTED | 1 | 28850 | 28850 | 0 | 0 | 0 | 28850
|  | Priced based on free access for hot work and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | excl. cleaning and coating of new and affected |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | areas - see job 1188 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1135 | 1018.24 | Windows in conference room
|  | 6 pcs. windows on deck 10 between fr 50 to Fr |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 120 to be dismantled and changed. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Windows to be dismantled. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New windows to be reinstalled with new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | gaskets and sealant outside. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each window glass | QUOTED | 8 | 17940 | 107640 | 35880 | 0 | 0 | 143520
|  | Price is excl. cleaning and painting of frame |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and possible repairs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Windows to be delivered by DFDS. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1138 | D1130.39 | Renewal of deck Ventilation room #3 dk. 6
|  | behind AC 1.4. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ventilation room deck 6, room 3. Renewal of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel deck according to the sketch: | QUOTED | 1 | 1308280 | 1308280 | 0 | 0 | 0 | 1308280
|  | Reduction |  | 1 | -150000 | 0 | 0 | -150000 | 0 | -150000
|  | 5 cabins and walkway fr #12 to #37 to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | dismantled and covered off for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ventilation channels to be removed and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | refitted below deck 6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Insulation in affected areas to be removed and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | refitted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. of AHUs`to be disconnected from deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and supported from above |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renewing of steel deck between deck 5 and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | deck 6, approx. 20 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fireguard, cleaning during and after renewal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of new and affected area |  | 0 |  | 0 | 0 | 0 | 0 | 0
1144 | ADD 4D | Deck 6 - Skift af dæk i korridor
|  | Skiftning af ca. 8 m2 stål dæk i korridor på |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | dæk 6: | QUOTED | 1 | 284200 | 284200 | 0 | 0 | 0 | 284200
|  | De- og genmontering af loft paneler, lamper og |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | brand detektorer samt isolation for adkomst |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | De- og genmontering af pergo belægning på |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | dæk 6 i korridor af |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demontering af ventilations kanaler for adkomst |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Brand vagt og afdækning af kabler og rør for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | varmt arbejde |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Udskæring og ispundsning af stål dæk ca. 8 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Maling af nyt og berørt |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Prisen er baseret på at der kun er adkomst, for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | skiftning af stål dæk, i korridor områder på |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | både Dæk 5 og Dæk 6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1145 | D1114.12 | Collisionvalve - new updated price.
|  | Inspection/ overhaul of collision valve inside |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fore Peak TK | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Reinstatement of remote control mechanism |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from tank top to deck 3. | QUOTED | 1 | 59950 | 59950 | 0 | 0 | 0 | 59950
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible further repair of remote control. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be priced after Inspection and funktion test |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of remote control. | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1147 |  | Afdækning / telt foran vindues parti på
|  | forkant af aptering for udskiftning af glas. | QUOTED | 1 | 123000 | 123000 | 0 | 0 | 0 | 123000
|  | Kran assistance |  | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
1148 |  | Afslibning af fladjern på skibsside SB+BB,
|  | basis 2x140m. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker, each per day | QUOTED | 6 | 3500 | 21000 | 0 | 0 | 0 | 21000
|  | Fugning af fladjern under op |  | 1 | 20800 | 4200 | 16600 | 0 | 0 | 20800
1149 | D1018.01 | Windows dismantling Carpets/Garbage
|  | 3 pcs. windows deck 7+8 around frame 116 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | incl. 2 frame rod to be dismantled and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reassembled. (window on deck 8 only) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Please refer to attached sketch |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Window and frame rod to be dismantled as |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | soon as possible, and reassembled and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | painted before leaving dock. |  | 1 | 110100 | 110100 | 0 | 0 | 0 | 110100
|  | Paint work |  | 1 | 6240 | 6240 | 0 | 0 | 0 | 6240
|  | Purpose for above is garbage removal and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | carpet handling. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard/Contractor supply: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging / lifts |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Lightning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Removal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bolts / Nuts |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scrap of empty paint buckets to be included |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Owner supply: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All painting supplied by owner where |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | otherwisse nothing is montioned. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | A) dismounting / mounting windows |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | B) one flat rack container for carpet handling |  | 0 |  | 0 | 0 | 0 | 0 | 0
1150 |  | 3D scanning af skibs skrog.
|  | 3D scanning af skibs skrog. |  | 1 | 75750 | 150000 | 0 | -74250 | 0 | 75750
1152 |  | 2 pcs. ICCP anodes in way of new farring
|  | to be moved forward to new position. |  | 1 | 62000 | 0 | 62000 | 0 | 0 | 62000
|  | Force test MPI |  | 1 | 12500 | 0 | 12500 | 0 | 0 | 12500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Change of 2 pcs. ICCP zinc anodes |  | 2 | 12430 | 0 | 24860 | 0 | 0 | 24860
|  | Mounting of 2 pcs. ICCP main anodes |  | 2 | 22660 | 0 | 45320 | 0 | 0 | 45320
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. ICCP: Filler, covering, painting |  | 1 | 57200 | 57200 | 0 | 0 | 0 | 57200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting inside engine room |  | 1 | 9620 | 0 | 9620 | 0 | 0 | 9620
1154 | D2701.06 | Ventilation channel to be repaired AHU 1:4
|  | Channel is leaking in cabin 6505 |  | 1 | 28700 | 0 | 28700 | 0 | 0 | 28700
|  | Cherry picker |  | 1 | 7000 | 0 | 7000 | 0 | 0 | 7000
1157 |  | Welding crack on SB Main propeller blade.
|  | Incl. report from Force |  | 1 | 18000 | 18000 | 0 | 0 | 0 | 18000
1158 |  | Ass. Til macgregor
|  | Ass. Til macgregor | QUOTED | 1 | 33200 | 40000 | 0 | -6800 | 0 | 33200
1159 |  | Adkomst for stål rep. For job 1146
|  | Adkomst for stål rep. For job 1146 |  | 1 | 21500 | 20000 | 1500 | 0 | 0 | 21500
1160 |  | Adkomst for stål reo. For job 1082
|  | Adkomst for stål reo. For job 1082 | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tank cleaning etc. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1161 |  | Vacuum truck for void space 600 to be
|  | emptied for DNV inspection. |  | 1 | 27840 | 27840 | 0 | 0 | 0 | 27840
1162 |  | Repair of damaged thread on bottom plugs.
|  | Machining, each hour | QUOTED | 5 | 1150 | 0 | 5750 | 0 | 0 | 5750
|  | Assistance | QUOTED | 1 | 8500 | 0 | 8500 | 0 | 0 | 8500
1163 |  | Machining of four new boltes for SB gear
|  | box. Incl. material. | QUOTED | 1 | 19800 | 16500 | 0 | 3300 | 0 | 19800
1164 |  | Fabrication and mounting of scupper pipe
|  | Splash protection on shell side. | QUOTED | 1 | 22300 | 22300 | 0 | 0 | 0 | 22300
1165 |  | NDT test of Main propeller blade and Hub
|  | bolts. | QUOTED | 84 | 650 | 54600 | 0 | 0 | 0 | 54600
1166 |  | Repair of window frames in front deck 6/8
|  | Repair of window frames in front deck 6/8 | QUOTED | 1 | 70000 | 70000 | 0 | 0 | 0 | 70000
1167 |  | Steel repair between tank T901 Dirty oil
|  | and D1000 Frame 87-88 approx 300x700. | QUOTED | 1 | 45300 | 0 | 45300 | 0 | 0 | 45300
|  | Cleaning of tanks for hotwork: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mudtruck, each hour | QUOTED | 9 | 1150 | 0 | 10350 | 0 | 0 | 10350
|  | Assistance, materials | QUOTED | 1 | 19880 | 0 | 19880 | 0 | 0 | 19880
|  | Disposal of slop per m³ | QUOTED | 6 | 1200 | 0 | 7200 | 0 | 0 | 7200
1168 |  | NEW Steel repair around WT door frame & deck
|  | Afdækning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning min. 0,25 m²/spot |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ht spuling med 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 3 coat pensel/rulle primer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 2 coat pensel/rulle topcoat | QUOTED | 1 | 59800 | 59800 | 0 | 0 | 0 | 59800
1169 |  | Roof over sky bar front (Alu.)
|  | Afdækning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning min. 0,25 m²/spot |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vask |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 2 coat pensel/rulle primer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat pensel/rulle topcoat | QUOTED | 1 | 55500 | 55500 | 0 | 0 | 0 | 55500
1170 |  | Renewal approx. 300x300 mm tank top in
|  | bow thruster room. Incl. scaffolding |  | 1 | 43200 | 43200 | 0 | 0 | 0 | 43200
1171 |  | Suction pipe from sludge tank to be renewed.
|  | Ændring af 1 stk. 2 1/2" rør | QUOTED | 1 | 17850 | 0 | 17850 | 0 | 0 | 17850
|  | Ændring af 2 stk. 1" rør | QUOTED | 1 | 13500 | 0 | 13500 | 0 | 0 | 13500
|  | Brandvagt | QUOTED | 1 | 12000 | 0 | 12000 | 0 | 0 | 12000
|  | Rengøring af setlings tank for hot work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mudtruck, assistance, spul, materialer etc. |  | 1 | 40715 | 0 | 13700 | 27015 | 0 | 40715
|  | Disposal pr. m³ |  | 8 | 1200 | 0 | 6000 | 3600 | 0 | 9600
1172 |  | Renewal of (8 pcs.) deck drains, deck 8, 3 and 1.
|  | T&M |  | 1 | 297300 | 0 | 297300 | 0 | 0 | 297300
1173 |  | Preheating pipe in A/C room deck 6.
|  | Preheating pipe in A/C room deck 6. |  | 1 | 21400 | 0 | 21400 | 0 | 0 | 21400
|  | Additional pipe + T-piece |  | 1 | 18800 | 0 | 0 | 18800 | 0 | 18800
1175 |  | Ass. / material for C.A.T.C.
|  | Ass. / material for C.A.T.C. |  | 1 | 15000 | 0 | 15000 | 0 | 0 | 15000
1177 |  | Kontrol samt skift af nav i Geislinger kobling
|  | på HVM no.1 | QUOTED | 1 | 119300 | 119300 | 0 | 0 | 0 | 119300
1178 |  | Assistance to CC. Jensen.
|  | Cables/power/ass. welding machine | QUOTED | 1 | 20800 | 0 | 20000 | 800 | 0 | 20800
|  | Staging/cherry picker | QUOTED | 1 | 18000 | 0 | 18000 | 0 | 0 | 18000
1179 |  | Assistance to Kongsberg.
|  | Access in panel etc. | QUOTED | 1 | 10000 | 0 | 10000 | 0 | 0 | 10000
1180 |  | Filling sloths on PS - Sb rudder and Center
|  | keel. | QUOTED | 1 | 48828 | 48828 | 0 | 0 | 0 | 48828
1181 |  | Ass. to owners subcontractor AVN.
|  | Ass. to owners subcontractor AVN. | QUOTED | 1 | 8500 | 15000 | -6500 | 0 | 0 | 8500
1182 |  | Exchang of Eng Room Vent Fans SB + BB
|  | Disconnection of old |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Removal of Fire dampers |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cutting old Fan in 2 pcs. to get it out |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dismantling new fan to get it in / assembling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of fan |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Connection of new fan |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fit back fire damper if Plug and play |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each unit | QUOTED | 2 | 44200 | 88400 | 0 | 0 | 0 | 88400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Supply/installation of new "bell" |  | 1 | 11700 | 0 | 11700 | 0 | 0 | 11700
1183 |  | Assistance to Glas service, lift + driver
|  | 06.01.23. |  | 1 | 6100 | 0 | 6100 | 0 | 0 | 6100
1184 |  | Insert plate in Water Tank FR 150 below
|  | bakery | QUOTED | 1 | 56700 | 56700 | 0 | 0 | 0 | 56700
1185 |  | Main deck ventilation room STB FR. 174 and
|  | 171 2 insert plates | QUOTED | 1 | 26300 | 26300 | 0 | 0 | 0 | 26300
1186 |  | FWD ventilation room
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning / Nålebanke |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 2 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat | QUOTED | 1 | 93600 | 93600 | 0 | 0 | 0 | 93600
1187 |  | Wast deck for container
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning + spartel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 2 coat | QUOTED | 1 | 24500 | 24500 | 0 | 0 | 0 | 24500
1188 |  | Painting of new and touched steel where
|  | not already included in initial quotation. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be recorded area per area. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Thruster room + forpeak New steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sea chest New steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New zink rudder + stern tube |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Stabilisator outside |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Stabilisator inside PS New steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Thruster outside |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Per 18/1-23 |  | 1 | 80550 | 0 | 80550 | 0 | 0 | 80550
|  | New steel: Deck+tank ved rampe |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel: Cofferdam + maskinrum |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel: Deck 6 new deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel: Ventilonsrum |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel: SB / PS Engine room |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel: SB / PS ved finder |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel: Deck 3 main deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New steel: Fore peck (halsjern) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Silicone damaged / crack after paint completed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mooring deck: New pipe on tank, pipe supports |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Nyt rør i maskinrum + dørk fundament |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional per 26/1-23 |  | 1 | 246400 | 0 | 0 | 246400 | 0 | 246400
1189 |  | Udskiftning af bolte i 4 stk. spil fundamenter
|  | til davids for livbåde dæk 6. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Inkl. levering af 32 stk. 8.8 bolte med møtrikker. | QUOTED | 1 | 22450 | 22450 | 0 | 0 | 0 | 22450
1190 |  | Wire wheel for david ps. 1 pcs.
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Nålebanke |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 2 coat primer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 2 coat top coat |  | 1 | 12610 | 12610 | 0 | 0 | 0 | 12610
|  | Additional 1 pcs. |  | 1 | 12610 | 0 | 12610 | 0 | 0 | 12610
1191 |  | Stabilisator (in B6)
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling | QUOTED | 1 | 11700 | 11700 | 0 | 0 | 0 | 11700
1192 |  | Stabilisator (in Dock)
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling | QUOTED | 1 | 6500 | 6500 | 0 | 0 | 0 | 6500
1193 |  | Bushing of motor bearing shields
|  | Bushing of motor bearing shields on 2 pcs. Motors. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 bearing shields out of 4 to be bushed. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Materials and machining included. | QUOTED | 1 | 13728 | 13728 | 0 | 0 | 0 | 13728
|  | Additional 2 pcs. |  | 1 | 9152 | 0 | 9152 | 0 | 0 | 9152
|  | Welding of crack in 1 pcs. wing for blower |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | incl. balancing |  | 1 | 3020 | 0 | 3020 | 0 | 0 | 3020
1194 |  | Tømning af tank 911 inkl. deponi. 11.01.23.
|  | Mudtruck per hour | QUOTED | 18 | 1150 | 0 | 20700 | 0 | 0 | 20700
|  | Disposal per m³ | QUOTED | 25 | 1200 | 0 | 30000 | 0 | 0 | 30000
1195 |  | Job 1145 fortsat:
|  | Kollisions ventil i forepeak. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Levering af 1 stk. ny DN 250 ventil inkl. 3.2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | DNV certifikat. | QUOTED | 1 | 28300 | 0 | 28300 | 0 | 0 | 28300
|  | Fragt | QUOTED | 1 | 5000 | 0 | 5000 | 0 | 0 | 5000
|  | Udskiftning af ventil samt tilpasning af fjerntræk. | QUOTED | 1 | 26200 | 0 | 26200 | 0 | 0 | 26200
|  | Slamsugning/rengøring i forepeak for adkomst. | QUOTED | 1 | 7000 | 0 | 7000 | 0 | 0 | 7000
|  | Adkomst hul for ny ventil |  | 1 | 25000 | 0 | 25000 | 0 | 0 | 25000
1196 |  | MOB og redningsbåde:
|  | M.O.B både 2 stk. (små) komplet afrens/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | polering/coatning, pr. stk. | QUOTED | 2 | 35100 | 0 | 70200 | 0 | 0 | 70200
|  | Store Livbåde 6 stk. kun afrensning samt coating |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pris pr. stk. | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Store liv både med vinduer (2 stk.) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vandslibning/polering/coatning af alle vinduer. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pris pr. stk. | QUOTED | 2 | 13800 | 0 | 27600 | 0 | 0 | 27600
1197 |  | Brandspjæld dæk 12 afmonteres, adskilles,
|  | renses og genmonteres | QUOTED | 1 | 9750 | 0 | 9750 | 0 | 0 | 9750
1198 |  | Rengøring og nedspuling af tank 901
|  | Rengøring med Grøn Total samt nedspuling af |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 49.8 m³ tank. | QUOTED | 1 | 60600 | 0 | 60600 | 0 | 0 | 60600
|  | Inkl. spuleanlæg, slamsuger og materialer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Deponi af 8 m³ olievand | QUOTED | 1 | 9600 | 0 | 9600 | 0 | 0 | 9600
1199 |  | 4 pcs. of brackets, engine room
|  | 4 pcs. of brackets for govenors, engine room |  | 1 | 23400 | 0 | 0 | 23400 | 0 | 23400
1200 |  | 1 x cable penetration deck 7-8
|  | 1 x cable penetration deck 7-8 |  | 1 | 30760 | 0 | 30760 | 0 | 0 | 30760
1201 |  | Insert deck 11-12 # 75 PS
|  | 2 pcs. |  | 1 | 79590 | 0 | 0 | 79590 | 0 | 79590
1202 |  | Maskinrums ventilonsrum SB
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat pensel/rulle |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat pensel/rulle |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat pensel/rulle | QUOTED | 1 | 103600 | 0 | 103600 | 0 | 0 | 103600
1203 |  | Maskinrums ventilonsrum BB
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat pensel/rulle |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat pensel/rulle |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat pensel/rulle | QUOTED | 1 | 121800 | 0 | 121800 | 0 | 0 | 121800
1204 |  | Tilpasning af 1 stk. låge i hoved tavle samt
|  | fremstilling af 1 stk. ny låge, grundet nye brydere. |  | 1 | 12400 | 0 | 12400 | 0 | 0 | 12400
1205 |  | Owner supplied 2 component paint to be
|  | applied in way of corroded area on deck 3. |  | 1 | 26400 | 0 | 0 | 26400 | 0 | 26400
1206 |  | Mekanisk rengøring af tanktop forrest i
|  | separator rum. Incl. opmaling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Udskiftning af plade i tanktop efter aftale. | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tank 904 tømmes og rengøres for adkomst. |  | 1 | 36320 | 0 | 36320 | 0 | 0 | 36320
|  | Disposal pr. m³ |  | 8 | 1200 | 0 | 9600 | 0 | 0 | 9600
|  | Maling |  | 1 | 17550 | 0 | 17550 | 0 | 0 | 17550
1207 |  | Ass. m/stikkontakter og antenne stik på
|  | 2 stk. mandskabskamre dæk 6. |  | 1 | 52620 | 0 | 0 | 52620 | 0 | 52620
1208 |  | 1) Reparation af bund i ventilationskanal ved
|  | A/C 3.2 | QUOTED | 1 | 10500 | 0 | 0 | 10500 | 0 | 10500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2) Fugning af sprosser ved vinduer på |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | agterkanten | QUOTED | 1 | 5400 | 0 | 0 | 5400 | 0 | 5400
|  | Lift | QUOTED | 1 | 4000 | 0 | 0 | 4000 | 0 | 4000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3) Fugning af 18 vinduer på dæk 7 ved nye |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bundlysninger | QUOTED | 1 | 11340 | 0 | 0 | 11340 | 0 | 11340
|  | Lift | QUOTED | 1 | 8000 | 0 | 0 | 8000 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4) Reparation af bund og isolering på |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilationskanal i AHU rum 8 | QUOTED | 1 | 10500 | 0 | 0 | 10500 | 0 | 10500
1209 |  | De – genmontering af kompensatorer på
|  | HVM udstødsrør for syn/ opryd efter kedel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reparation. |  | 1 | 30600 | 0 | 0 | 30600 | 0 | 30600
1210 |  | Fastgørelse af kabelrør samt diverse kabel
|  | arbejde i ventilationsrum dæk 12. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Udskiftning af wire for brandspjæld inkl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | afprøvning. |  | 1 | 82675 | 0 | 0 | 82675 | 0 | 82675
1211 |  | Kabler samt kabelrør på fortøjningsdæk
|  | 21/1-23 |  | 1 | 113400 | 0 | 0 | 113400 | 0 | 113400
1212 |  | Indoor pool, inside wall
|  | Overdækning af pool for støv |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning af spot |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Slibe hele pool / rugøre |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. | QUOTED | 1 | 67760 | 0 | 0 | 67760 | 0 | 67760
1213 |  | Udskiftning af 1 stk. ekstra tyndplade på
|  | fortøjningsdæk. |  | 1 | 7200 | 0 | 0 | 7200 | 0 | 7200
1214 |  | Handling of Yokohama fendere inside
|  | dock 1 and at pier 63/64 | UNIT PRICE | 2 | 5000 | 0 | 0 | 10000 | 0 | 10000
1215 |  | Maling af dead-end SB + BB side.
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. |  | 1 | 5200 | 0 | 0 | 5200 | 0 | 5200
1216 |  | Ass. to Renk service engineer on gear.
|  | Incl. delivery of valve and o-rings |  | 1 | 28500 | 0 | 0 | 28500 | 0 | 28500
1217 |  | Painting frame at fore castle deck.
|  | Nyt & berørt |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Lift |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. |  | 1 | 21580 | 0 | 0 | 21580 | 0 | 21580
1218 |  | Painting deck in front of windows forward.
|  | Nyt & berørt |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. |  | 1 | 23660 | 0 | 0 | 23660 | 0 | 23660
|  | Lift |  | 1 | 10500 | 0 | 0 | 10500 | 0 | 10500
1219 |  | Painting deck at wheelhouse.
|  | Nyt & berørt |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. |  | 1 | 4550 | 0 | 0 | 4550 | 0 | 4550
1220 |  | Painting below mooring deck aft.
|  | Nyt & berørt |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Emulsionsrensning incl. rensevæske |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mek. afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. |  | 1 | 9360 | 0 | 0 | 9360 | 0 | 9360
1221 |  | Cleaning new windows forward.
|  | Because of glue material. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vask |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Afrensning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rengøring |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Opmaling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | I alt som spec. |  | 1 | 29250 | 0 | 0 | 29250 | 0 | 29250
1222 |  | Installering af ny udsuger fra MBR dæk 12.
|  | Installering af ny udsuger fra MBR dæk 12. |  | 1 | 8000 | 0 | 0 | 8000 | 0 | 8000
1223 |  | Painting New and affected areas at the new
|  | installed BWTS. | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1224 |  | Insert plate in tank 1302
|  | Insert plate in tank 1302 |  | 1 | 27900 | 0 | 0 | 27900 | 0 | 27900
1225 |  | Maler arbejde ombord under sejlads fra
|  | Fayard til København inkl. hjemtransport. |  | 1 | 57600 | 0 | 0 | 57600 | 0 | 57600
1226 |  | Bil ombord inden afgang.
|  | Bil ombord inden afgang. | UNIT PRICE | 1 | 5000 | 0 | 0 | 5000 | 0 | 5000
1227 |  | Fugning af kasketskygge over vinduer på
|  | forkant af overbygning. |  | 1 | 5550 | 0 | 0 | 5550 | 0 | 5550
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation |  | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
9993 |  | Discount according to agreement
|  | Discount according to agreement | 12% | 1 | -3402607 | -2247293 | -201866 | -953448 | 0 | -3402607
|  | Additional discount agreed with Superintendent |  | 1 | -100000 | 0 | 0 | 0 | -100000 | -100000
|  |  | DKK |  |  | 11423838 | 1949225 | 541770 | -550000 | 13364833 | 0