## Chapter 0
Ship name: |  | COTE DES DUNES
Case No.: |  | 221235
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-02-07 | 2023-02-08 | 2023-02-15 | 2025-05-06 | Total
1000 |  | Sag
1001 |  | Docking
|  | DRY DOCKING OF THE VESSEL |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Docking / undocking including first day | QUOTED | 1 | 70000 | 70000 | 0 | 0 | 0 | 70000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each following day | QUOTED | 14 | 30000 | 420000 | 0 | 30000 | -30000 | 420000
1003 |  | Earth connection
|  | Earth connection | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1004 |  | Crane riggers (2 riggers each crane/hr) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Price per man, each normal hour | QUOTED | 30 | 400 | 12000 | 0 | 0 | 0 | 12000
1005 |  | Fire Line Connection
|  | Fire Line under pressure max. 5 bar, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each connection | QUOTED | 2 | 3000 | 6000 | 0 | 0 | 0 | 6000
|  | Maintenance per day incl. Electrical consumption | QUOTED | 30 | 350 | 10500 | 0 | 0 | 0 | 10500
1006 |  | Blocking of CO2
|  | Blocking of CO2 | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1007 |  | Stock supply
|  | Stock supply per 8/2-23 | QUOTED | 1 | 109389 | 115000 | -5611 | 0 | 0 | 109389
|  | Stock supply per 13/2-23 | QUOTED | 1 | 20899 | 0 | 10000 | 10899 | 0 | 20899
|  | Moved to accomodation works |  | 1 | -65144 | 0 | 0 | 0 | -65144 | -65144
1008 |  | Isolation
|  | Isolation |  | 0 |  | 0 | 0 | 0 | 0 | 0
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1011 |  | Gangway
|  | Each gangway | QUOTED | 2 | 4000 | 8000 | 0 | 0 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gangway and tower for owners subcontractors |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to deck 05 | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Large ramp 50 ton from jetty to vessel main deck | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 25000
1012 |  | Cooling water connection
|  | Shore supply of coolingwater for Generator Plant |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Connection of cooling water, each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Cooling out, each connection | QUOTED | 4 | 3000 | 12000 | 0 | 0 | 0 | 12000
1013 |  | Fresh water connection
|  | Supply of pressurized domestic fresh water |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Connection of FW hose, Each time | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Supply of FW, per m³ | QUOTED | 567 | 40 | 8000 | 0 | 14680 | 0 | 22680
1014 |  | Grey/Black water discharge to Yard facilities |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (mixed BW/GW) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mud truck per hour - 31/1-23 | QUOTED | 8 | 1150 | 9200 | 0 | 0 | 0 | 9200
|  | Based on normal working hours |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal per m³ - 31/1-23 | QUOTED | 40 | 95 | 3800 | 0 | 0 | 0 | 3800
1015 |  | Oily water connection
|  | Bilge water disposal (engine room) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal of oily waste, each m³ - 10/2-23 | CANCELLED | 0 |  | 0 | 0 | 54000 | -54000 | 0
|  | Mud truck per hour - 10/2-23 | CANCELLED | 0 |  | 0 | 0 | 20700 | -20700 | 0
|  | Based on normal working hours |  | 0 |  | 0 | 0 | 0 | 0 | 0
1017 |  | Ballast water connection
|  | Connection of Ballast water connection, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each hose | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Supply of ballast water, each m³ | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further assistance with ballasting: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1018 |  | Gas free certifikate
|  | First initial gas free certificate | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Additional gas free certificate, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1020 | 21.2 | TAILSHAFT WEARDOWN
|  | Measuring of tailshaft clearances, each side | QUOTED | 2 | 7000 | 14000 | 0 | 0 | 0 | 14000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible yard assistance with cherrypicker / |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging (Becker) |  | 1 | 3500 | 0 | 0 | 3500 | 0 | 3500
1023 | 21.5 | RUDDERS
|  | Only measuring of clearances STB+PS, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each time | QUOTED | 2 | 7000 | 14000 | 0 | 0 | 0 | 14000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bottom plug out/in, each |  | 4 | 1500 | 6000 | 0 | 0 | 0 | 6000
1024 | 21.6 | THRUSTER BT4 STANDARD EXCHANGE
|  | Staging and draining of oil, each thruster | QUOTED | 1 | 32000 | 32000 | 0 | 0 | 0 | 32000
|  | Oil refilled by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible disposal of oil, each m³ | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Propeller blades removed/refitted, each | QUOTED | 4 | 6000 | 24000 | 0 | 0 | 0 | 24000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Damaged blade refitted/removed, each |  | 4 | 6000 | 24000 | 0 | 0 | 0 | 24000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount/refit of underwater part, included |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | transport to workshop for overhaul, each | QUOTED | 1 | 80000 | 80000 | 0 | 0 | 0 | 80000
|  | Based on only access from outside. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible welding up additonal pad eyes for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | handling, each padeye | QUOTED | 3 | 10000 | 30000 | 0 | 0 | 0 | 30000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to Teams Meeting 23.01.2023: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Supervisor will attend 31.01.2023 A.M. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New oil is onboard. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Check of lengths of supports before exchanging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | thruster #4. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Check alignment after mounting of new thruster. |  | 2 | 7500 | 0 | 0 | 15000 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to owners service eng.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to timesheet per 3/2-23 | QUOTED | 1 | 20500 | 20500 | 0 | 0 | 0 | 20500
|  | According to timesheet per 4/2-23 | QUOTED | 1 | 18000 | 18000 | 0 | 0 | 0 | 18000
|  | According to timesheet per 5/2-23 | QUOTED | 1 | 17000 | 17000 | 0 | 0 | 0 | 17000
|  | According to timesheet per 6/2-23 | QUOTED | 1 | 17000 | 17000 | 0 | 0 | 0 | 17000
|  | According to timesheet per 7/2-23 | QUOTED | 1 | 35300 | 35300 | 0 | 0 | 0 | 35300
|  | According to timesheet per 8/2-23 | QUOTED | 1 | 26500 | 0 | 0 | 26500 | 0 | 26500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Machining of blade carriers |  | 4 | 2500 | 0 | 0 | 10000 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
1027 | 21.10 | Stabilizer port
|  | Staging for access, each stabilizer | QUOTED | 1 | 8000 | 8000 | 0 | 0 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard assistance to owners service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to timesheet per 30/1-23 | QUOTED | 1 | 27600 | 27600 | 0 | 0 | 0 | 27600
|  | According to timesheet per 31/1-23 | QUOTED | 1 | 36100 | 36100 | 0 | 0 | 0 | 36100
|  | According to timesheet per 1/2-23 | QUOTED | 1 | 36100 | 36100 | 0 | 0 | 0 | 36100
|  | According to timesheet per 2/2-23 | QUOTED | 1 | 19100 | 19100 | 0 | 0 | 0 | 19100
|  | Reduction for staging on timesheets |  | 1 | -8400 | 0 | -8400 | 0 | 0 | -8400
1028 | 21.11 | Steering gear distributing valves
|  | Removal of 4 x 2 valves incl. cleaning contact |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | surfaces. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation of 4 x 2 valves with new seals |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | delivered by owner. | QUOTED | 1 | 19450 | 19450 | 0 | 0 | 0 | 19450
|  | Crew will drain the system. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Subject to free access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (Wrong quote, should be net cost 44.000 DKK) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery of seals |  | 1 | 7618 | 7618 | 0 | 0 | 0 | 7618
1033 | 14.1 | Hydraulic pipes renewal on Bow doors
|  | Replacement of hydraulic pipes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renewing of pipes on bowdoor according to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | recived drawings/pictures. 13 pcs. | VOR 23 | 1 | 104000 | 0 | 0 | 104000 | 0 | 104000
|  | Scaffolding | VOR 23 | 1 | 5500 | 0 | 0 | 5500 | 0 | 5500
1034 | 14.2 | Cargo access repairs
|  | Priced after more info or after inspection and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | determination of workscope. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Only possible assistance. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging/cherry picker |  | 1 | 43300 | 30000 | 0 | 13300 | 0 | 43300
1040 | 15.5 | FO heaters
|  | Dismounting, disassembling, cleaning, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reassembling and remounting of heaters, 3 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each | QUOTED | 3 | 22770 | 68310 | 0 | 0 | 0 | 68310
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Machining of cover plates |  | 1 | 2500 | 2500 | 0 | 0 | 0 | 2500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery of gasket |  | 1 | 5571 | 5571 | 0 | 0 | 0 | 5571
1041 | 15.6 | Exchanger heat recovery / steam
|  | Dismounting, disassembling, cleaning, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reassembling and remounting of heaters, 2 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each | QUOTED | 2 | 22770 | 45540 | 0 | 0 | 0 | 45540
1042 | 15.7 | LT coolers Overhaul
|  | LT coolers for ME 1+2: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of plates incl. Packing of owners |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | supply renewed: 2 x 82 pcs., each | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | LT coolers for ME 3+4: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of plates incl. Packing of owners |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | supply renewed: 2 x 142 pcs., each | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | LT coolers for LT propulsion STB/PORT: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disassembling and reassembling of coolers |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | included transport |  | 1 | 37340 | 37340 | 0 | 0 | 0 | 37340
|  | Frame plates off/on and overhaul bolts |  | 1 | 29380 | 29380 | 0 | 0 | 0 | 29380
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | LT coolers for LT Aux. STB/PORT: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disassembling and reassembling of coolers |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | included transport |  | 1 | 94440 | 94440 | 0 | 0 | 0 | 94440
|  | Frame plates off/on and overhaul bolts |  | 1 | 44070 | 44070 | 0 | 0 | 0 | 44070
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In general: Excl. Frame plates |  | 0 |  | 0 | 0 | 0 | 0 | 0
1043 | 23.1 | SEACHEST AND CROSSOVER
|  | Seachests opened, cleaned and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (as allready offered): |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. 4,25 m³ | QUOTED | 4 | 1940 | 8245 | 0 | 0 | 0 | 8245
|  | 1 pcs. 1,7 m³ | QUOTED | 2 | 1940 | 3298 | 0 | 0 | 0 | 3298
|  | 1 pcs. 3,4 m³ | QUOTED | 3 | 1940 | 6596 | 0 | 0 | 0 | 6596
|  | 1 pcs. 7,7 m³ | QUOTED | 8 | 1620 | 12474 | 0 | 0 | 0 | 12474
|  | 1 pcs. 13,7 m³ | QUOTED | 14 | 1390 | 19043 | 0 | 0 | 0 | 19043
|  | Disposal of mussels per ton |  | 3 | 7500 | 0 | 0 | 22500 | 0 | 22500
|  | Staging |  | 1 | 22500 | 22500 | 0 | 0 | 0 | 22500
1044 | 23.2 | Change of owner supplied Alu. anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AL 25 (2,5 kg.) each | QUOTED | 2 | 430 | 0 | 0 | 860 | 0 | 860
|  | AL 43 (4,3 kg.) each | QUOTED | 20 | 540 | 0 | 0 | 10800 | 0 | 10800
|  | AL 60 (6,0 kg.) each | QUOTED | 6 | 645 | 0 | 0 | 3870 | 0 | 3870
|  | AL 80 (8,0 kg.) each | QUOTED | 18 | 685 | 0 | 0 | 12330 | 0 | 12330
|  | AL 116 (11,6 kg.) each | QUOTED | 4 | 860 | 0 | 0 | 3440 | 0 | 3440
|  | Incl. dismounting of old and mounting of new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | welded type anode |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Change of yard supplied Alu. anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AL 25 (2,5 kg.) each | QUOTED | 12 | 645 | 0 | 0 | 7740 | 0 | 7740
|  | AL 35 (3,5 kg.) each | QUOTED | 6 | 770 | 0 | 0 | 4620 | 0 | 4620
|  | AL 60 (6,0 kg.) each | QUOTED | 2 | 1135 | 0 | 0 | 2270 | 0 | 2270
|  | AL 80 (8,0 kg.) each | QUOTED | 14 | 1240 | 0 | 0 | 17360 | 0 | 17360
|  | AL 90 (9,0 kg.) each | QUOTED | 8 | 1345 | 0 | 0 | 10760 | 0 | 10760
|  | AL 116 (11,6 kg.) each | QUOTED | 9 | 1680 | 0 | 0 | 15120 | 0 | 15120
|  | Incl. dismounting of old and mounting of new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | welded type anode |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker for zinc renewal, each per day | QUOTED | 8 | 3500 | 21000 | 0 | 7000 | 0 | 28000
1045 | 23.3 | Cowcatcher repairs
|  | Priced after more info or after inspection and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | determination of exact workscope |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mounting of flatbar on cowcatcher approx. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 18 meter 120 x 12 mm | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Subject to free internal access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel Repair Cowchatcher SB and PS side |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to agreement with super intendent. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel | VOR 1 | 1 | 208000 | 208000 | 0 | 0 | 0 | 208000
|  | Cherry picker | VOR 1 | 1 | 44100 | 44100 | 0 | 0 | 0 | 44100
|  | Material | VOR 1 | 1 | 23100 | 23100 | 0 | 0 | 0 | 23100
|  | SOW | VOR 1 | 1 | 9975 | 9975 | 0 | 0 | 0 | 9975
|  | Fireguard | VOR 1 | 1 | 31500 | 31500 | 0 | 0 | 0 | 31500
|  | Excl. Paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
1046 | 23.4 | Grey water tank cleaning
|  | Cleaning of grey water tank | VOR 12 | 1 | 254500 | 254500 | 0 | 0 | 0 | 254500
|  | Vacuum trucks and spuling devices |  | 1 | 140000 | 140000 | 0 | 0 | 0 | 140000
|  | Disposal of solid and pumpable waste |  | 1 | 40000 | 40000 | 0 | 0 | 0 | 40000
|  | Discount for reduced scope |  | 1 | -97300 | -97300 | 0 | 0 | 0 | -97300
1047 | 23.5 | Oily bilge water high tank aft
|  | Cleaning of tank, ready for hot work |  | 1 | 123800 | 123800 | 0 | 0 | 0 | 123800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel repair in top of tank: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection and determination of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | exact workscope | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount insulation and cladding outside tank |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and in toilet for access to steel work and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reestablish of same, total of approx. 15 m² | QUOTED | 1 | 42500 | 42500 | 0 | 0 | 0 | 42500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steelwork, based: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 x 2500 x 1500 x 10 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 x 2500 x 800 x 10 mm | QUOTED | 1 | 550000 | 550000 | 0 | 0 | 0 | 550000
|  | Based empty and clean tanks ready for hotwork |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Remove concrete in toilet | QUOTED | 1 | 7000 | 18000 | -5000 | -6000 | 0 | 7000
1049 | 23.8 | Ship side valves inspection
|  | Inspect overboard sea & sanitary valves |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Globular and gate Valves, standard overhaul: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | DN 300, each | QUOTED | 1 | 5520 | 5520 | 0 | 0 | 0 | 5520
|  | Subject to free access. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. possible remote controls, actuators, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | repairs and renewals |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible lift assistance, each lift per day | QUOTED | 1 | 3500 | 3500 | 0 | 0 | 0 | 3500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Butterfly valves, standard overhaul "in-situ": |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | DN 150, each | QUOTED | 4 | 1150 | 4600 | 0 | 0 | 0 | 4600
|  | Subject to free access. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. possible remote controls, actuators, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | repairs and renewals |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 pcs. pipes cleaned together with inspection |  | 1 | 3600 | 3600 | 0 | 0 | 0 | 3600
1050 | 20.1 | ANCHOR & CABLES
|  | Anchors and chains ranged in dock, HP-cleaned, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | measured and marked with SS bands | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of anchors with 1 coat | QUOTED | 1 | 7700 | 7700 | 0 | 0 | 0 | 7700
1053 | 22.1 | Lifeboats Landing.
|  | Lifeboats taken ashore and back, 4 pcs., each | QUOTED | 4 | 8000 | 32000 | 0 | 0 | 0 | 32000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Maintenance and repair: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Done by crew and/or owners arranged specialist |  | 0 |  | 0 | 0 | 0 | 0 | 0
1055 | 22.5 | MES lines supports
|  | Remove and refit screws with silicone applied: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection |  | 1 | 10640 | 10640 | 0 | 0 | 0 | 10640
|  | Cherry picker, each per day |  | 2 | 3500 | 7000 | 0 | 0 | 0 | 7000
1059 | 16.5 | Megger test on alternator
|  | Megger test on alternator, 11 pcs. Units in total |  | 1 | 10540 | 10540 | 0 | 0 | 0 | 10540
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1060 | 41.40 | COMPANY LOGO ON SHIPS SIDE
|  | COMPANY LOGO ON SHIPS SIDE | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1063 | 41.43 | Grinding Deck 3
|  | Grinding Deck 3, 3534 m²: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing with soap |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Removal of water and preparation for cyclone |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaning of deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclone cleaning of deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before paint application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 x FC with owners supplied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering against overspray | QUOTED | 1 | 1309347 | 1309347 | 0 | 0 | 0 | 1309347
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additional unit prices: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of edges, each meter | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible mechanical cleaning where cyclone |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaning not possible, each m² | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible application of sand, each m² | QUOTED | 3534 | 11 | 38874 | 0 | 0 | 0 | 38874
|  | Removal of water and preparation for cyclone |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaning of deck, 1.378 m² | QUOTED | 1378 | 72.75 | 100250 | 0 | 0 | 0 | 100250
|  | Cyclone cleaning of deck 533 m² PS + 845 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | STB = 1.378 m² |  | 1378 | 143 | 197054 | 0 | 0 | 0 | 197054
|  | HP-wash of deck with soap water, 1.378 m² | QUOTED | 1378 | 27.25 | 37551 | 0 | 0 | 0 | 37551
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Marking and painting of stribes, each meter |  | 2094 | 49 | 0 | 0 | 102606 | 0 | 102606
|  | Reduction due to only 1. Layer |  | 1 | -22000 | 0 | 0 | 0 | -22000 | -22000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Lashing pots: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering and painting of lashing pot tops, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering and painting of lashing pots, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1067 | 41.43A | Deck 3 - all recesses STB+PORT:
|  | Job done by crew | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1072 | 23.10 | Steel plate renewal on aft deck 3
|  | Aft cargo deck above steering gear room: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renewal of deck, approx. 5000 x 3000 mm incl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fitting of owners supplied 6 pcs. lashing pots | QUOTED | 1 | 234000 | 234000 | 0 | 0 | 0 | 234000
|  | Excl. Possible access below deck and painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access and isolation |  | 1 | 53700 | 0 | 0 | 53700 | 0 | 53700
|  | Additional 6 m² steel deck |  | 1 | 78000 | 78000 | 0 | 0 | 0 | 78000
1073 | 16.7 | Possible Yard ass. to WRS cathodic may be
|  | rewired for replacement of reference anodes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to timesheet per 31/1-23 | QUOTED | 1 | 32000 | 32000 | 0 | 0 | 0 | 32000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ass. to service engineer exchanging of 4 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ICCP anodes | VOR 10 | 1 | 38480 | 38480 | 0 | 0 | 0 | 38480
|  | Exchanging of 6 pcs. main ICCP anodes | VOR 10 | 1 | 106080 | 106080 | 0 | 0 | 0 | 106080
|  | Staging | VOR 10 | 1 | 18000 | 18000 | 0 | 0 | 0 | 18000
|  | Excl. paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
1074 | 16.9 | Winch W1 electrical motor overhaul, 1 pcs.
|  | Cleaning and change of bearings |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Extra Cleaning do to grease inside windings |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rep. of shaft for Encoder |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of brakes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Draining and filling of oil on Gearbox incl. seals |  | 1 | 36995 | 36995 | 0 | 0 | 0 | 36995
|  | Bearing are Ship supply |  | 0 |  | 0 | 0 | 0 | 0 | 0
1075 | 22.6 | Lifeboat fall replacement cable wire
|  | Lifeboat fall replacement wire SB. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New wire will be delivered by Owner | VOR 21 | 1 | 45500 | 0 | 0 | 45500 | 0 | 45500
|  | Crane | VOR 21 | 1 | 8800 | 0 | 0 | 8800 | 0 | 8800
|  | Disposal old wire | CANCELLED | 0 |  | 0 | 0 | 5000 | -5000 | 0
|  | Additional persons due to condition of existing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | clamps etc. |  | 1 | 22500 | 0 | 0 | 22500 | 0 | 22500
1079 |  | Cleaning of ventilation ducting etc.
|  | Cleaning of ventilation ducting etc. | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1084 |  | Bottom plugs in and out.
|  | Each | QUOTED | 17 | 300 | 5100 | 0 | 0 | 0 | 5100
1085 | 23.11 | Cowcatcher modifications for Roro3
|  | Mounting of owners delivered adaptors STB+PS |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | according to received pictures/drawing | VOR 17 | 1 | 91000 | 91000 | 0 | 0 | 0 | 91000
|  | Cherrry picker | VOR 17 | 1 | 21000 | 21000 | 0 | 0 | 0 | 21000
|  | Crane | VOR 17 | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  | Forklift | VOR 17 | 1 | 4000 | 4000 | 0 | 0 | 0 | 4000
|  | Excl. paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work | INCL. | 0 |  | 0 | 0 | 8300 | -8300 | 0
1086 |  | Repair of crack on deck 3 by Grinding -
|  | welding - NDT test |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Will only be repaired from the top. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Eash crack max 300 mm | VOR 7 | 58 | 3813 | 221154 | 0 | 0 | 0 | 221154
|  | Excl. Paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
1087 |  | Repair 2 x insert plate deck 3 PS
|  | Steel work | VOR 6 | 1 | 39200 | 39200 | 0 | 0 | 0 | 39200
|  | Scaffolding | VOR 6 | 1 | 12350 | 12350 | 0 | 0 | 0 | 12350
|  | SOW | VOR 6 | 1 | 7875 | 7875 | 0 | 0 | 0 | 7875
|  | NDT test | VOR 6 | 1 | 13125 | 13125 | 0 | 0 | 0 | 13125
|  | Excl. paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
1088 |  | Fabrication of new ropeguard for SB and PS
|  | main propeller. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dismounting - mounting and repair of rope |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | guard by renewing the edge by a flatbar. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel | VOR 2 | 1 | 73500 | 73500 | 0 | 0 | 0 | 73500
|  | Scaffolding | VOR 2 | 1 | 22575 | 22575 | 0 | 0 | 0 | 22575
|  | Material | VOR 2 | 1 | 5460 | 5460 | 0 | 0 | 0 | 5460
|  | SOW | VOR 2 | 1 | 7875 | 7875 | 0 | 0 | 0 | 7875
1089 |  | Welding of crack in stainless steel liner in
|  | stern thruster and aft bow thruster. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Welding up stainless band inside thruster |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | tunnel - Stern thruster | VOR 3 | 1 | 39900 | 39900 | 0 | 0 | 0 | 39900
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional welding of steel outside |  | 1 | 28700 | 28700 | 0 | 0 | 0 | 28700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Welding up stainless steel band inside thruster |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | tunnel 3 x bow thruster. | VOR 4 | 1 | 50400 | 50400 | 0 | 0 | 0 | 50400
1090 |  | Repair of cracks in rudders incl. pressure test.
|  | Rudder SB and PS lekage repair and pressure |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | test |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repair | VOR 8 | 1 | 18900 | 18900 | 0 | 0 | 0 | 18900
|  | Cherry picker | VOR 8 | 1 | 14700 | 14700 | 0 | 0 | 0 | 14700
|  | Pressure test | VOR 8 | 1 | 15750 | 15750 | 0 | 0 | 0 | 15750
1091 |  | Welding of cavitated areas on hull.
|  | Scope to be agreed with superintendent. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Welding up cavatations area on V brachet |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | SB and PS | VOR 5 | 1 | 39900 | 39900 | 0 | 0 | 0 | 39900
|  | Cherry picker | VOR 5 | 1 | 11025 | 11025 | 0 | 0 | 0 | 11025
1092 |  | Welding / grinding of coupling on Stb
|  | forward windlass. |  | 1 | 8300 | 8300 | 0 | 0 | 0 | 8300
1093 |  | Repair of cracks Car deck no.5.
|  | Each crack (price VOR 7) | QUOTED | 8 | 3813 | 30504 | 0 | 0 | 0 | 30504
1095 | VOR 11 | Supplying of new plates for 4 heatexchanger
|  | incl. new gasket | VOR 11 | 1 | 374951 | 374951 | 0 | 0 | 0 | 374951
|  | Overhauling of front and aft plate for 4 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | heatexchanger | VOR 11 | 1 | 31200 | 31200 | 0 | 0 | 0 | 31200
|  | Sandblasting - zinc primer and painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. new gasket |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery time will be 3 working days from order. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1097 |  | Ass. to owners subcontractor for Window
|  | repair/exchance. See job 1106 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1098 | VOR 13 | Renewal hydraulic pipes at thruster
|  | Remove 2 pcs. old pipes and install 2 pcs. new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pipes. Delivery and fabrication of 2 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hydraulic pipes. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Carbon steel pipes and chromatized fittings. | VOR 13 | 1 | 19200 | 19200 | 0 | 0 | 0 | 19200
|  | Assuming std. European flange type. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Painting and flushing. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assuming free access to hydraulic pipes |  | 0 |  | 0 | 0 | 0 | 0 | 0
1099 |  | Ass. to radio Holland in installation of new
|  | speed log transducer. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. cable installation on bridge |  | 1 | 44020 | 20000 | 0 | 24020 | 0 | 44020
|  | Machining of bolts |  | 1 | 3000 | 0 | 0 | 3000 | 0 | 3000
1101 | VOR 16 | Fabrication of 2 new elbow pipes incl. material
|  | and galvanizing | VOR 16 | 1 | 25800 | 25800 | 0 | 0 | 0 | 25800
|  | Galvanazing of 1 pipe | VOR 16 | 1 | 4500 | 4500 | 0 | 0 | 0 | 4500
|  | Transport | VOR 16 | 1 | 5000 | 5000 | 0 | 0 | 0 | 5000
|  | Pipes will be completed Wednesday 8-2-2023 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | afternoon and ready for mounting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crew will dismount and mount the pipes and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bring them to quay side. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 pcs. additional pipes blasted and galvanized |  | 3 | 4500 | 0 | 0 | 13500 | 0 | 13500
1102 | VOR 18 | Gelcoat repair on FRB and lifeboats.
|  | Repair of Gelcoat cracks on Lifeboat 7, 8, 9, 10 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and FRB, total of 42 locations. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repairs on FRB can be done onboard. | VOR 18 | 1 | 35800 | 35800 | 0 | 0 | 0 | 35800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional repairs pointed out 12/2-23 |  | 1 | 6200 | 0 | 0 | 6200 | 0 | 6200
1103 | VOR 14 | Renewal seals on hydraulic cylinders
|  | Disassembling cylinder in SH Group workshop |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Inspection of cylinder |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assembling cylinder with new seal-kit |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | delivered by vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pressure testing and overhaul report |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | MacGregor to deliver cylinders + seal-kit on |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | keyside. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each cylinder | VOR 14 | 1 | 29650 | 29650 | 0 | 0 | 0 | 29650
|  | Excl. Repairs and materials |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | It is assumed that pin bolts can be removed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with a force of max. 60T without use of heat |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Oil for filling cylinder is quoted seperately if |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not delivered by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repair spot and rechrome spot Ø100x100 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | on pistonrod. Pistonrod will be ready for pick- |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | up at subcontractor Thursday morning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement hydraulic pipe on cylinder. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dress-up threads on pistonrod/inside cylinder |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pipe. | VOR 25 | 1 | 19890 | 20580 | 0 | -690 | 0 | 19890
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Honing cylinderpipe | VOR 25 | 1 | 1924 | 1930 | 0 | -6 | 0 | 1924
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Machining threads on pistonrod/inside |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cylinderpipe. | VOR 25 | 1 | 9153 | 0 | 0 | 9153 | 0 | 9153
1104 |  | Establish heaters and covering on main deck,
|  | in order to achieve enough temperature for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | deck paint. |  | 1 | 30800 | 26000 | 0 | 4800 | 0 | 30800
|  | Rent of heaters for Calais | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1106 |  | Ass. to glass service d. 7/2 for dismantling of
|  | windows. Crane and banksman. |  | 1 | 36800 | 0 | 0 | 36800 | 0 | 36800
|  | Cherry picker, each per day |  | 8 | 3500 | 28000 | 0 | 0 | 0 | 28000
1107 | VOR 19 | Washing and cleaning bilge in seperator room.
|  | Incl. mud truck. | VOR 19 | 1 | 136500 | 0 | 136500 | 0 | 0 | 136500
|  | Disposal 15 m³ oil sludge | VOR 19 | 1 | 18000 | 0 | 18000 | 0 | 0 | 18000
|  | Material | VOR 19 | 1 | 5600 | 0 | 5600 | 0 | 0 | 5600
1108 |  | Delivery of new ballast valve incl. machining
|  | of adapter flanges. |  | 1 | 6970 | 0 | 0 | 6970 | 0 | 6970
|  | New valve included in stock supply job 1007 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1109 | VOR 22 | Machining of Stern thruster propeller
|  | according the service engineer instruction | VOR 22 | 1 | 66500 | 0 | 0 | 66500 | 0 | 66500
|  | Transport | VOR 22 | 1 | 10000 | 0 | 0 | 10000 | 0 | 10000
1110 | VOR 20 | Painting new steel inside bilge water tank
|  | and void space |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mech. grinding and cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting 2 x FC Hempadur Easy | VOR 20 | 1 | 15340 | 0 | 0 | 15340 | 0 | 15340
1111 | VOR 24 | Renewing of 2x cooling water pipe for
|  | Heat Exchanger. | VOR 24 | 1 | 27300 | 0 | 0 | 27300 | 0 | 27300
|  | Crew will paint and install the pipes |  | 0 |  | 0 | 0 | 0 | 0 | 0
1112 |  | Machining of small shaft for PS stabilizer
|  | feedback cylinder. |  | 1 | 12340 | 0 | 0 | 12340 | 0 | 12340
1114 |  | Cherry pickers used by crew for paint work
|  | Each per day |  | 6 | 3500 | 0 | 0 | 21000 | 0 | 21000
|  |  | DKK |  |  | 6770585 | 151089 | 923382 | -205144 | 7639912 | 0