## Chapter 0
Ship name: |  | COTE D'OPALE
Case No.: |  | 231007
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-03-10 | 2023-03-16 | 2023-03-20 | 2025-05-06 | Total
1000 |  | Sag
1001 | 7304 | Docking / Undocking and stay in Dry dock
|  | Docking / undocking including first day | QUOTED | 1 | 80000 | 80000 | 0 | 0 | 0 | 80000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each following day | QUOTED | 15 | 35000 | 525000 | 0 | 0 | 0 | 525000
1003 |  | Earth connection
|  | Earth connection | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1004 | 7318 | Crane riggers (2 riggers each crane/hr) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Price per man, each normal hour | QUOTED | 30 | 400 | 12000 | 0 | 0 | 0 | 12000
1005 | 7306 | Fire Precautions
|  | Fire Line under pressure max. 5 bar, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 16 | 350 | 5600 | 0 | 0 | 0 | 5600
1006 |  | Blocking of CO2
|  | Blocking of CO2 | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 35000 | 40000 | 0 | -5000 | 0 | 35000
1008 |  | Isolation
|  | Isolation | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1011 | 7322 | Gangway
|  | Standard gangway, each | QUOTED | 1 | 4000 | 4000 | 0 | 0 | 0 | 4000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible gangway and tower for owners |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | subcontractors | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
1012 |  | Cooling water connection
|  | Cooling water connection, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Cooling out, each connection | QUOTED | 3 | 3000 | 6000 | 0 | 3000 | 0 | 9000
|  | Supply of SW / Maintenance per day | QUOTED | 64 | 500 | 24000 | 0 | 8000 | 0 | 32000
1013 | 7312 | Potable Fresh water
|  | Potable water connection, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Supply of FW per m³ | QUOTED | 690 | 40 | 20000 | 0 | 7600 | 0 | 27600
1014 | 7314 | Grey/Black water discharge to Yard facilities |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (mixed BW/GW) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mud truck per hour - per 15/3-23 | QUOTED | 11 | 1150 | 0 | 12650 | 0 | 0 | 12650
|  | Based on normal working hours |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal per m³ - per 15/3-23 | QUOTED | 18 | 95 | 0 | 1710 | 0 | 0 | 1710
|  | Mud truck per hour - per 19/3-23 | QUOTED | 10 | 1150 | 0 | 0 | 11500 | 0 | 11500
|  | Based on normal working hours |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal per m³ - per 19/3-23 | QUOTED | 18 | 95 | 0 | 0 | 1710 | 0 | 1710
1017 |  | Ballast water connection
|  | Ballast water connection, each hose | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Supply of ballast water, each m³ | QUOTED | 500 | 8 | 0 | 0 | 4000 | 0 | 4000
|  | Further assistance with ballasting: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1018 | 7326 | Gas free certificate
|  | First initial gas free certificate | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Additional gas free certificates, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1019 | 145 | Scaffolding installation and mounting
|  | Priced after more info or after inspection and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | determination of workscope | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1021 | 7324 | Access Ramp
|  | Access ramp to istall from Berth to main deck | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 25000
1022 | 63 | Stern door rail protection
|  | Doublers deck 3 aft at the stern doors 1500x9000 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Will be welded by sloths to existing deck | VOR 2 | 1 | 50700 | 50700 | 0 | 0 | 0 | 50700
|  | Fireguard | VOR 2 | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  | Material | VOR 2 | 1 | 9500 | 9500 | 0 | 0 | 0 | 9500
|  | Crane / Forklift | VOR 2 | 1 | 3500 | 3500 | 0 | 0 | 0 | 3500
|  | Scaffolding | VOR 2 | 1 | 4500 | 4500 | 0 | 0 | 0 | 4500
|  | Excl. paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
1023 | 117 | Rack A & B noise problem - Matrix noise problem
|  | Done by owners arranged service engineers |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from Gicom | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1024 | 5722 | Yearly Job S.G./B.T. NO.1 VFD
|  | Carried out by owners arranged service technicians | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Alternative: done by yard: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after more info |  | 0 |  | 0 | 0 | 0 | 0 | 0
1028 | 4974 | Inspect transformer Lighting transformer T1
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1029 | 5000 | Megger test transformer Lighting transformer T1
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1030 | 4976 | Inspect transformer Lighting transformer T2
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1031 | 5004 | Megger test transformer Lighting transformer T2
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1032 | 4978 | Inspect transformer Lighting transformer T3
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1033 | 5006 | Megger test transformer Lighting transformer T3
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1034 | 4980 | Inspect transformer Lighting transformer T4
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1035 | 5008 | Megger test transformer Lighting transformer T4
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1036 | 4982 | Inspect transformer Lighting transformer T5
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1037 | 5010 | Megger test transformer Lighting transformer T5
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1038 | 5014 | Megger test transformer Lighting transformer T6
|  | Inspection and cleaning, based max 690 V, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. Transformer | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  | Excl. Possible repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1039 | 5786 | Yearly inspection Main switchboard 1
|  | Cleaning and retigthening, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each switchboard section | QUOTED | 10 | 1830 | 18300 | 0 | 0 | 0 | 18300
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Thermo grafic inspection: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Measuring: 1 person per day | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Report and transport expenses |  | 0 |  | 0 | 0 | 0 | 0 | 0
1040 | 5788 | Yearly inspection Main switchboard 2
|  | Cleaning and retigthening, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each switchboard section | QUOTED | 12 | 1830 | 21960 | 0 | 0 | 0 | 21960
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Thermo grafic inspection: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Measuring: 1 person per day | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Report and transport expenses |  | 0 |  | 0 | 0 | 0 | 0 | 0
1045 | 5804 | Yearly inspection ESB switchboard 1
|  | Cleaning and retigthening, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each switchboard section | QUOTED | 7 | 1830 | 12810 | 0 | 0 | 0 | 12810
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Thermo grafic inspection: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Measuring: 1 person per day | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Report and transport expenses |  | 0 |  | 0 | 0 | 0 | 0 | 0
1048 | 151 | Anchor chain paint job
|  | Anchors and chains ranged in dock, HP-cleaned, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | measured and marked with SS bands | CANCELLED | 0 |  | 34000 | 0 | 0 | -34000 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of anchors with 1 coat | QUOTED | 1 | 7700 | 7700 | -7700 | 7700 | 0 | 7700
1049 | 7302 | Tailshaft Weardown
|  | Staging, ropeguard removed and refitted | QUOTED | 2 | 37900 | 75800 | 0 | 0 | 0 | 75800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tent, each |  | 2 | 15000 | 30000 | 0 | 0 | 0 | 30000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Draining of oil | QUOTED | 2 | 15300 | 30600 | 0 | 0 | 0 | 30600
|  | Refilled crew |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible disposal of oil, each m³ | QUOTED | 5 | 1200 | 2400 | 3000 | 0 | 0 | 5400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Weardown measurements with gauge, each side |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Done by service engineer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renewal of owners supplied anodes, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible further yard assistance to owners |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | service engineer: Each person per 12 hour shift |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | See job 1054 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1050 | 165 | Thrusters grids
|  | Repair of thruster grid BT2 PS | VOR 4 | 1 | 16500 | 16500 | 0 | 0 | 0 | 16500
|  | Cutting accesshole BT1 and BT3 will be closed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | after painting of thruster tunnel | VOR 4 | 1 | 14500 | 14500 | 0 | 0 | 0 | 14500
|  | Cherry picker | VOR 4 | 1 | 10500 | 10500 | 0 | 0 | 0 | 10500
|  | Excl. paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repair of thruster grid BT2 SB. | VOR 4.1 | 1 | 16500 | 16500 | 0 | 0 | 0 | 16500
|  | Cherry picker | VOR 4.1 | 1 | 8500 | 8500 | 0 | 0 | 0 | 8500
|  | Excl. paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
1052 | 7196 | Annual Job Stabilizer hydr. oil power pack SB
|  | Treatment stabilizer fins & housing: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hosing down |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Lift | QUOTED | 1 | 22200 | 22200 | 0 | 0 | 0 | 22200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further possible yard assistance to owners |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | service engineers: Each person per 12 hour shift | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1054 | 133 | SB + PS Sterntube seal check
|  | Possible yard assistance to owners service |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | engineers: Each person per 12 hour shift |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to timesheet per 7/3-23 | QUOTED | 1 | 9700 | 9700 | 0 | 0 | 0 | 9700
|  | According to timesheet per 8/3-23 | QUOTED | 1 | 9700 | 9700 | 0 | 0 | 0 | 9700
|  | According to timesheet per 9/3-23 | QUOTED | 1 | 8500 | 8500 | 0 | 0 | 0 | 8500
|  | According to timesheet per 10/3-23 | QUOTED | 1 | 8500 | 0 | 8500 | 0 | 0 | 8500
|  | According to timesheet per 11/3-23 | QUOTED | 1 | 16000 | 0 | 16000 | 0 | 0 | 16000
|  | According to timesheet per 12/3-23 | QUOTED | 1 | 8500 | 0 | 8500 | 0 | 0 | 8500
1055 | 6810 | Lubrication job PS Shaft Brake/Lock Disc
|  | Possible yard assistance to owners service |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | engineers: Each person per 12 hour shift | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1056 | 139 | SB Shaft brake disc machining
|  | Possible yard assistance to owners service |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | engineers: Each person per 12 hour shift |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to timesheet per 9/3-23 | QUOTED | 1 | 17000 | 17000 | 0 | 0 | 0 | 17000
|  | According to timesheet per 10/3-23 | QUOTED | 1 | 41500 | 0 | 41500 | 0 | 0 | 41500
|  | According to timesheet per 11/3-23 | QUOTED | 1 | 34100 | 0 | 34100 | 0 | 0 | 34100
|  | According to timesheet per 12/3-23 | QUOTED | 1 | 17000 | 0 | 17000 | 0 | 0 | 17000
|  | According to timesheet per 13/3-23 | QUOTED | 1 | 27500 | 0 | 27500 | 0 | 0 | 27500
1057 | 6812 | Lubrication job SB Shaft Brake/Lock Disc
|  | Possible yard assistance to owners service |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | engineers: Each person per 12 hour shift | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1058 | 7330 | Change of yard supplied Alu. anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AL 43 (4,3 kg.) each | QUOTED | 12 | 890 | 0 | 10680 | 0 | 0 | 10680
|  | AL 80 (8,0 kg.) each | QUOTED | 24 | 1345 | 0 | 32280 | 0 | 0 | 32280
|  | Incl. dismounting of old and mounting of new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | welded type anode |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker for zinc renewal, each per day | QUOTED | 6 | 3500 | 0 | 21000 | 0 | 0 | 21000
1059 | 73 | Side shell plating refit
|  | Renewal of shell plating as spec. 8000 x 1500 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | incl. Structure | QUOTED | 1 | 174500 | 174500 | 0 | 0 | 0 | 174500
|  | Excl. Painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
1061 | 75 | Fender and escape vessel plating refit
|  | Refit fender and escape vessel as spec. incl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Insultion work for access | QUOTED | 1 | 192000 | 192000 | 0 | 0 | 0 | 192000
|  | Excl. Painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Exchanging of Shell plate because of deformation | VOR 5 | 1 | 32500 | 32500 | 0 | 0 | 0 | 32500
|  | Material | VOR 5 | 1 | 5500 | 5500 | 0 | 0 | 0 | 5500
|  | Cherry picker | VOR 5 | 1 | 7000 | 7000 | 0 | 0 | 0 | 7000
|  | NDT test by Force | VOR 5 | 1 | 12500 | 12500 | 0 | 0 | 0 | 12500
|  | Vaccum test | VOR 5 | 1 | 8500 | 8500 | 0 | 0 | 0 | 8500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work |  | 1 | 8450 | 0 | 0 | 8450 | 0 | 8450
1062 | 1710 | Drydock service ICCP
|  | ICCP: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of owner supplied ICCP referance |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | anodes, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based crew dis- and remount electrically |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of owner supplied ICCP main |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | anodes, each | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based crew dis- and remount electrically |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker for ICCP anodes, each per day | QUOTED | 2 | 3500 | 0 | 7000 | 0 | 0 | 7000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible epoxy/paint Repair: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1063 | 141 | Voids general inspection
|  | Job done by crew | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard assistance for inspection: As per account | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible cleaning/painting after inspection: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection and determination of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | workscope | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
1067 | 43 | Heeling tank S HBWS insert
|  | Repair by insert and new support incl. Access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from heeling tank | QUOTED | 1 | 56500 | 56500 | 0 | 0 | 0 | 56500
|  | Excl. Painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
1071 | 121 | Seawater strainer inside Coating
|  | Dismounting, transport and remounting of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | seafilter, each | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment of seawater strainers inside: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting 3 pcs. Seafilter. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 x Seafilter Washing - Cleaning, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scraping and Mud truck | VOR 6 | 1 | 32240 | 32240 | 0 | 0 | 0 | 32240
|  | Painting of 3 pcs. Seafilter inside engine room | VOR 6 | 1 | 42120 | 42120 | 0 | 0 | 0 | 42120
|  | Mechanical grinding |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Washing and cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal | VOR 6 | 1 | 3500 | 3500 | 0 | 0 | 0 | 3500
|  | Owner will deliver paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1076 | 149 | Safety cage ladder extension DK10-9
|  | Extension of safety cage as spec. | QUOTED | 1 | 54000 | 54000 | 0 | 0 | 0 | 54000
|  | Excl. Painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Back protection from 2 m and up |  | 1 | 26800 | 0 | 26800 | 0 | 0 | 26800
1077 | 71 | Bow door ladders
|  | Fit new ladders as spec. | QUOTED | 1 | 98000 | 98000 | 0 | 0 | 0 | 98000
|  | Excl. Painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
1078 | 89 | Ladder acces bow door in deck 5
|  | Fabrication and mounting of ladder incl. 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | guard rails on the roof on deck 5 | QUOTED | 1 | 66000 | 66000 | 0 | 0 | 0 | 66000
|  | Excl. Possible back supports on ladder, and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | painting of new and touched |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1079 | 119 | Cleaning deck window wing starboardside
|  | and portside |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard assistance with lift, each lift per day | QUOTED | 2 | 3500 | 7000 | 0 | 0 | 0 | 7000
|  | Cleaning and painting of windows under |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bridge wings |  | 1 | 4940 | 0 | 0 | 4940 | 0 | 4940
1083 | 143 | Monkey island rust removal and painting
|  | Priced after more info or after inspection and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | determination of workscope | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker, each per day | QUOTED | 5 | 3500 | 14000 | 3500 | 0 | 0 | 17500
1090 | New | Aft fender reinforcement:
|  | Steelwork | VOR 1 | 1 | 58500 | 58500 | 0 | 0 | 0 | 58500
|  | Cherry picker | VOR 1 | 1 | 18500 | 18500 | 0 | 0 | 0 | 18500
|  | Fireguard | VOR 1 | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  | Material | VOR 1 | 1 | 8500 | 8500 | 0 | 0 | 0 | 8500
|  | Excl. paint inside |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paintwork |  | 1 | 10400 | 0 | 0 | 10400 | 0 | 10400
1094 |  | Cleaning of ventilation ducting etc.
|  | Cleaning of ventilation ducting etc. | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1096 | ENG 055: | Water leakage due to a crack on GRP pipe
|  | on LT cooler 2 ME1 |  | 1 | 23550 | 0 | 23550 | 0 | 0 | 23550
|  | Incl. travel cost |  | 0 |  | 0 | 0 | 0 | 0 | 0
1097 |  | Ass. to owners service engineer “Becker”
|  | for measuring rudder clearance. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | SE will arrive 8/3-2023 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker |  | 1 | 3500 | 3500 | 0 | 0 | 0 | 3500
|  | Assistance |  | 1 | 8500 | 8500 | 0 | 0 | 0 | 8500
1098 |  | Bottom plugs in and out
|  | Each | QUOTED | 35 | 300 | 10500 | 0 | 0 | 0 | 10500
1099 |  | Pressure test Rudder
|  | Each rudder | QUOTED | 2 | 18500 | 37000 | 0 | 0 | 0 | 37000
|  | Demounting - mounting access hatch |  | 2 | 2500 | 0 | 5000 | 0 | 0 | 5000
1101 |  | Lower Keel block at echosounder fore.
|  | Lower Keel block at echosounder fore. |  | 1 | 4500 | 0 | 4500 | 0 | 0 | 4500
|  | 2 x crossover bottom plugs access |  | 2 | 4500 | 0 | 9000 | 0 | 0 | 9000
1102 |  | Cherry picker for Glass Service from
|  | 08.03.23 incl. banks man for safety. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Banks man | QUOTED | 8 | 8500 | 59500 | 8500 | 0 | 0 | 68000
|  | Crane assistance | QUOTED | 5 | 1500 | 7500 | 0 | 0 | 0 | 7500
|  | Cherry picker, each per day | QUOTED | 8 | 5500 | 38500 | 5500 | 0 | 0 | 44000
1103 |  | Rent of forklift for deck 5 from 08.03.23.
|  | Each per day |  | 3 | 3500 | 10500 | 0 | 0 | 0 | 10500
1104 |  | Rent of scissor lift for deck 7 in way of life
|  | boats from 08.03.23. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each per day | QUOTED | 10 | 3500 | 21000 | 14000 | 0 | 0 | 35000
1105 |  | Scaffolding for MAK in engine room 08.03.23.
|  | Scaffolding for MAK in engine room 08.03.23. | QUOTED | 1 | 8450 | 6000 | 2450 | 0 | 0 | 8450
1106 |  | Scaffolding for access to engine room from
|  | Deck 3. Vessel will keep scaffolding materials |  | 1 | 31980 | 0 | 31980 | 0 | 0 | 31980
1107 |  | Cleaning of cross over channels
|  | Cleaning and washing of 3 x crossover |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Manpower, 26 x 6.100 DKK | VOR 7 | 1 | 158600 | 0 | 158600 | 0 | 0 | 158600
|  | Mudtruck, 30 x 1.200 DKK | VOR 7 | 1 | 36000 | 0 | 36000 | 0 | 0 | 36000
|  | Disposal: 6x4 ton. Total 24 ton. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 16 m³ cleaning water | VOR 7 | 1 | 36500 | 0 | 36500 | 0 | 0 | 36500
|  | The prices is estimated |  | 0 |  | 0 | 0 | 0 | 0 | 0
1108 |  | Machining of STB liner for outer stuffing box.
|  | Machining of STB liner for outer stuffing box. |  | 1 | 12500 | 0 | 12500 | 0 | 0 | 12500
1112 |  | Doublers deck 3 aft at the stern doors
|  | 20x800x5200, will be welded to existing deck/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | dobling plate | VOR 8 | 1 | 51870 | 0 | 51870 | 0 | 0 | 51870
|  | SOW | VOR 8 | 1 | 6500 | 0 | 6500 | 0 | 0 | 6500
|  | Material | VOR 8 | 1 | 9500 | 0 | 9500 | 0 | 0 | 9500
|  | Crane / Forklift | VOR 8 | 1 | 5500 | 0 | 5500 | 0 | 0 | 5500
|  | Excl. paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting new steel aft deck and outside aft |  | 1 | 24440 | 0 | 0 | 24440 | 0 | 24440
1113 |  | Cherry picker deck 5 forward for owners
|  | used. Each per day | QUOTED | 4 | 3500 | 0 | 14000 | 0 | 0 | 14000
1114 |  | Templates for WELCOME ABOARD COTE
|  | D OPALE | VOR 9 | 1 | 15262 | 0 | 0 | 15262 | 0 | 15262
|  | The size of the letters will be 600 mm and 12500 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | mm long. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Font there will be used can be choose by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1115 |  | Sea filter PS Cavitation area to be filled by
|  | epoxy filler. |  | 1 | 10010 | 0 | 0 | 10010 | 0 | 10010
1116 |  | PS rudder securing of bolts for sliding
|  | bushing. |  | 1 | 3500 | 0 | 0 | 3500 | 0 | 3500
|  | Cherry picker |  | 1 | 3000 | 0 | 0 | 3000 | 0 | 3000
1117 |  | Adjustment and additional load test
|  | incl. certificate |  | 1 | 3700 | 0 | 0 | 2500 | 1200 | 3700
|  |  | DKK |  |  | 2378830 | 699470 | 121012 | -32800 | 3166512 | 0