## Chapter 0
Ship name: |  | CROWN SEAWAYS
Case No.: |  | 231086
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-05-10 | 2023-05-15 | 2025-05-06 | Total
1000 |  | Sag
1001 | 200.02 | Drydocking in/out
|  | Dry dock no. 3 from 7/5-11/5-2023 incl. docking |  | 0 |  | 0 | 0 | 0 | 0
|  | in/out | QUOTED | 1 | 350000 | 350000 | 0 | 0 | 350000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Tugs, pilot, channel fee and possible linesmen | VIA AGENT | 0 |  | 0 | 0 | 0 | 0
1003 | 500.01 | Earthing of vessel
|  | Included in docking | INCL. | 0 |  | 0 | 0 | 0 | 0
1004 | 500.30 | Crane assistance
|  | Each normal hour up to 45 t, each hour | QUOTED | 35 | 1500 | 30000 | 22500 | 0 | 52500
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Forklift 3/5 tons for Owner use, included driver: |  | 0 |  | 0 | 0 | 0 | 0
|  | Per normal hour | QUOTED | 20 | 1000 | 20000 | 0 | 0 | 20000
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Handling etc. | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 20000
1005 | 500.03 + 500.04 | Fire line pressure
|  | Fireline: Connecting of Fire Line, max 5 bar |  | 0 |  | 0 | 0 | 0 | 0
|  | Each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 4 | 1500 | 6000 | 0 | 0 | 6000
1006 | 500.02 | CO2 Plant
|  | CO2 Plant | QUOTED | 1 | 2000 | 2000 | 0 | 0 | 2000
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 8167 | 10000 | -1833 | 0 | 8167
1009 | 500.16 | Garbage disposal
|  | Garbage containers (4 m³) |  | 0 |  | 0 | 0 | 0 | 0
|  | Garbage container on the quay. |  | 0 |  | 0 | 0 | 0 | 0
|  | Each time emptied, incl. disposal | QUOTED | 8 | 5000 | 25000 | 15000 | 0 | 40000
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL. | 0 |  | 0 | 0 | 0 | 0
1011 | 500.08 | Gangways 2 pcs.
|  | Per installation/removal | QUOTED | 2 | 4000 | 8000 | 0 | 0 | 8000
1012 | 500.11 + 500.12 | Cooling for Aux. Engines
|  | Connection/disconnection, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Supply of Cooling water SW/maintenance, |  | 0 |  | 0 | 0 | 0 | 0
|  | per day | QUOTED | 4 | 1500 | 6000 | 0 | 0 | 6000
1019 | 200.01 | Wharfage
|  | Free of charge when yard works in progress |  | 0 |  | 0 | 0 | 0 | 0
|  | Subject to unsold capacity | INFO | 0 |  | 0 | 0 | 0 | 0
1020 | 200.04 | Agency
|  | Agency to be handled directly by Owner | OWNER | 0 |  | 0 | 0 | 0 | 0
1021 | 300.01 | Painting And Treatment
|  | Painting done according to paint specification |  | 0 |  | 0 | 0 | 0 | 0
|  | and agreement. | INFO | 0 |  | 0 | 0 | 0 | 0
1027 | 500.21 | Bottom plugs
|  | Price per plug off and on | QUOTED | 5 | 200 | 1000 | 0 | 0 | 1000
|  | Vacum test per plug | N/A | 0 |  | 0 | 0 | 0 | 0
1034 | 500.29 | Thickness measurements
|  | Ultrasonic thickness measurements |  | 0 |  | 0 | 0 | 0 | 0
|  | Minimum 350 shots, each shot | OWNER | 0 |  | 0 | 0 | 0 | 0
|  | Excl. Access, staging and lifts |  | 0 |  | 0 | 0 | 0 | 0
1038 | 1016.08 | Vertical bottom - red paint
|  | Ice braker belt 850 m² |  | 0 |  | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 420 | 11.5 | 4830 | 0 | 0 | 4830
|  | 1 x TU coat Antifouling, done with brush/roll | QUOTED | 420 | 30.5 | 12810 | 0 | 0 | 12810
|  | 1 x TU coat Antifouling, done with brush/roll | QUOTED | 420 | 30.5 | 12810 | 0 | 0 | 12810
|  | Painting of line | QUOTED | 185 | 12.75 | 2359 | 0 | 0 | 2359
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning and painting of windows | QUOTED | 1 | 43535 | 0 | 46315 | -2780 | 43535
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Painting and cleaning of Rudder & Ropeguard |  | 1 | 27300 | 0 | 27300 | 0 | 27300
1043 | 3338.03 | Scupper valves
|  | Scupper valve no. 22 overhauled |  | 1 | 6370 | 6370 | 0 | 0 | 6370
1044 | 3338.04 | Ship side valves
|  | 1 pc. Boiler blow down valve, dismounted and |  | 0 |  | 0 | 0 | 0 | 0
|  | overhauled |  | 1 | 4160 | 4160 | 0 | 0 | 4160
1046 | 3802.05 | Propeller shaft seal - renewal
|  | PS and SB outer sterntube seals to be changed |  | 0 |  | 0 | 0 | 0 | 0
|  | Draining and destruction of stern tupe, 2500 liter, |  | 0 |  | 0 | 0 | 0 | 0
|  | each stern tupe | QUOTED | 2 | 11750 | 23500 | 0 | 0 | 23500
|  | Refill stern tube with oil to be done by crew |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Assistance to owners specialist for changing of |  | 0 |  | 0 | 0 | 0 | 0
|  | propeller shaft seals: |  | 0 |  | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | QUOTED | 7 | 8500 | 59500 | 0 | 0 | 59500
|  | Materials | QUOTED | 1 | 4000 | 4000 | 0 | 0 | 4000
1047 | 3802.06 | Tail shaft wear down
|  | Staging by rope guards, each | QUOTED | 2 | 11200 | 22400 | 0 | 0 | 22400
1048 | 3811.01 | Bow Thruster AFT Main Overhaul
|  | Assistance to owners specialist: |  | 0 |  | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | QUOTED | 20 | 8500 | 170000 | 0 | 0 | 170000
|  | Materials | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 10000
|  | Scaffolding, assistance with anodes and lifting |  | 0 |  | 0 | 0 | 0 | 0
|  | lugs, cleaning etc. |  | 1 | 123300 | 0 | 123300 | 0 | 123300
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 10000
|  |  | DKK |  |  | 826739 | 232582 | -2780 | 1056541 | 0