## Chapter 0
Ship name: |  | FLANDRIA SEAWAYS
Case No.: |  | 231121
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2023-08-14 | 2025-05-06 | Total
1000 |  | Sag
1001 | 200.01 | Drydocking
|  | Dock/undock and dockdues, lumpsum | QUOTED | 1 | 300000 | 300000 | 0 | 300000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Movement of vessel, See item 500.22 |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Earthing of vessel, included in docking. |  | 0 |  | 0 | 0 | 0
1002 | 500.06 | Shore connection
|  | A. Connection/disconnection | CANCELLED | 0 | 16000 | 0 | 0 | 0
|  | Electric power supply: 400 V, 50Hz, 1000 Amp |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Maintenance per day | CANCELLED | 0 | 750 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | B. Kw-hour | CANCELLED | 0 | 4.2 | 0 | 0 | 0
1003 | 500.25 | Earthing of the vessel
|  | Earthing of vessel, included in docking. | INCL | 0 |  | 0 | 0 | 0
1004 | 500.01 | Crane assistance (max 45T)
|  | A. Hourly rate for dockside cranes (max 45T) , |  | 0 |  | 0 | 0 | 0
|  | Each normal hour | QUOTED | 1 | 60000 | 60000 | 0 | 60000
1005 | 500.10 + 500.28 | Temporary fire connections
|  | A. Temporary fire connections | QUOTED | 1 | 3000 | 3000 | 0 | 3000
|  | Maintenance per day | QUOTED | 9 | 500 | 4500 | 0 | 4500
|  | B. Additional fire/safety services required by the yard |  | 0 |  | 0 | 0 | 0
|  | or local regulations |  | 0 |  | 0 | 0 | 0
1006 | 500.21 | CO2 plant
|  | A. Isolation/reconnection of CO2 plant | CREW | 0 |  | 0 | 0 | 0
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 50000 | 50000 | 0 | 50000
1008 |  | Isolation
|  | Isolation |  | 0 |  | 0 | 0 | 0
1009 | 500.23 | Garbage disposal
|  | Garbage containers (4 m3) |  | 0 |  | 0 | 0 | 0
|  | Garbage container on the quay. |  | 0 |  | 0 | 0 | 0
|  | Each time emptied, incl. disposal: | QUOTED | 9 | 5000 | 45000 | 0 | 45000
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL | 0 |  | 0 | 0 | 0
1011 | 500.02 | Gangways
|  | A. Per installation/removal | QUOTED | 2 | 4000 | 8000 | 0 | 8000
1012 | 500.09 | Cooling water for auxilliary Engines
|  | A. Connection/disconnection | QUOTED | 1 | 3000 | 3000 | 0 | 3000
|  | B. Per day in service |  | 0 |  | 0 | 0 | 0
|  | Maintenance per day | QUOTED | 9 | 500 | 4500 | 0 | 4500
1013 | 500.26 | Water supply
|  | A. Connection/disconnection of hose | NA | 0 | 3000 | 0 | 0 | 0
|  | B. Fresh water per m³ | NA | 0 | 40 | 0 | 0 | 0
1014 | 500.16 + 500.31 | Grey water disposal
|  | A. Connection/disconnection | QUOTED | 1 | 4000 | 4000 | 0 | 4000
|  | B. Grey sewage water discharged and disposed per m³ | QUOTED | 10 | 95 | 950 | 0 | 950
1015 | 500.24 | Oily water disposal
|  | Mudtruck per hour, based on normal working hours | QUOTED | 10 | 1150 | 11500 | 0 | 11500
|  | Disposal of oily water per m3 | QUOTED | 43 | 1200 | 51600 | 0 | 51600
1016 |  | Internet Connection
|  | Internet Connection | CANCELLED | 0 | 3000 | 0 | 0 | 0
1017 | 500.18 | Ballast water supply
|  | Connection of Ballast water, each hose | CANCELLED | 0 | 4000 | 0 | 0 | 0
|  | Supply of ballast water, each m3 | CANCELLED | 0 | 8 | 0 | 0 | 0
|  | Further assistance with ballasting, as per account. | CANCELLED | 0 |  | 0 | 0 | 0
1018 | 500.11 | Gas free certificates
|  | A: For initial visit - Gasfri certificat | QUOTED | 1 | 3500 | 3500 | 0 | 3500
|  | B: For subsequent visit, Each |  | 0 | 3500 | 0 | 0 | 0
1019 | 300.01 | Paint Specification
|  | Paint Specification | INFO | 0 |  | 0 | 0 | 0
1020 | 500.03 | Cleaning fuel oil tanks
|  | Cleaning of tank, based empty tank, each tank: |  | 0 |  | 0 | 0 | 0
|  | Open/close, gasfreeing of tanks, as per account |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Based on suction of tank bottom incl. removal and disposal of max |  | 0 |  | 0 | 0 | 0
|  | 2 m3 of oily pumpable waste |  | 0 | 8840 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional suction, each hour |  | 0 | 1150 | 0 | 0 | 0
|  | Possible additional disposal, each m3 |  | 0 | 1200 | 0 | 0 | 0
|  | Possible additional cleaning: to be agreed upon |  | 0 |  | 0 | 0 | 0
1021 | 500.04 | Bottom plugs
|  | A. Price pr. plug off and on | QUOTED | 10 | 200 | 2000 | 0 | 2000
|  | B. Vacum test per plug | CANCELLED | 0 | 200 | 0 | 0 | 0
|  | Heating of 1 stucked bottom plug |  | 1 | 1000 | 1000 | 0 | 1000
1022 | 500.05 | Thickness measurements
|  | Minimum 350 shots, each shot | NA | 0 | 25 | 0 | 0 | 0
1023 | 500.07 | Cleaning ballast tanks
|  | Basis empty tank flush through bottom plug, min. 80m3 tank. |  | 0 |  | 0 | 0 | 0
|  | per m3 |  | 0 | 12800 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Disposal of mud per ton | QUOTED | 1 | 2500 | 2500 | 0 | 2500
1024 | 500.08 | Ventilation fans
|  | A. Connection/disconnection | CANCELLED | 0 | 500 | 0 | 0 | 0
|  | B. Fan per day including power | CANCELLED | 0 | 550 | 0 | 0 | 0
1025 | 500.12 | Compressed air supply
|  | A. Per connection/disconnection. | CANCELLED | 0 | 2000 | 0 | 0 | 0
|  | Supply of air, max 5 bar. |  | 0 |  | 0 | 0 | 0
|  | B. Per day: Maintenance per day | CANCELLED | 0 | 1500 | 0 | 0 | 0
1026 | 500.14 | Cleaning of diesel oil tanks
|  | Cleaning of tank, based empty tank, each tank: |  | 0 |  | 0 | 0 | 0
|  | Open/close, gasfreeing of tanks, as per account |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Based on suction of tank bottom incl. removal and disposal of max |  | 0 |  | 0 | 0 | 0
|  | 2 m3 of oily pumpable waste |  | 0 | 8840 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional suction, each hour |  | 0 | 1150 | 0 | 0 | 0
|  | Possible additional disposal, each m3 |  | 0 | 1200 | 0 | 0 | 0
|  | Possible additional cleaning: to be agreed upon |  | 0 |  | 0 | 0 | 0
1027 | 500.15 | Cleaning sludge oil tanks
|  | Cleaning of tank, based empty tank, each tank: |  | 0 |  | 0 | 0 | 0
|  | Open/close, gasfreeing of tanks, as per account |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Based on suction of tank bottom incl. removal and disposal of max |  | 0 |  | 0 | 0 | 0
|  | 2 m3 of oily pumpable waste |  | 0 | 8840 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional suction, each hour |  | 0 | 1150 | 0 | 0 | 0
|  | Possible additional disposal, each m3 |  | 0 | 1200 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional cleaning: to be agreed upon |  | 0 |  | 0 | 0 | 0
|  | Disposal of unpumpable per ton |  | 0 | 7500 | 0 | 0 | 0
1028 | 500.17 | Steel prices
|  | Steel prices | INFO | 0 |  | 0 | 0 | 0
1029 | 500.19 | Corroded Welding seams
|  | Guaging out and rewelding with 4 welding strings |  | 0 |  | 0 | 0 | 0
|  | Each spot/meter,min. 1 meter: | CANCELLED | 0 | 800 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Each additional welding string. Each spot/meter, |  | 0 |  | 0 | 0 | 0
|  | min. 1 meter: | CANCELLED | 0 | 125 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Cherry picker for access to welding repairs, |  | 0 |  | 0 | 0 | 0
|  | Each cherry picker per day | CANCELLED | 0 | 3500 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | All damaged coatings on hull to be made good. |  | 0 |  | 0 | 0 | 0
|  | Hull painting as per hull paint specification. To be priced after |  | 0 |  | 0 | 0 | 0
|  | welding repairs are known | CANCELLED | 0 |  | 0 | 0 | 0
1030 | 500.20 | Securing of Stern Ramp
|  | 1: Preventer arrangement to be fixed by crew. |  | 0 |  | 0 | 0 | 0
|  | 2: Potection of hydraulic cylinder for all stern ramps | CANCELLED | 0 | 5500 | 0 | 0 | 0
1031 | 500.22 | Movement of vessel
|  | A. Tugs for movement of vessel |  | 0 |  | 0 | 0 | 0
|  | B. Line handlers for movement of vessel |  | 0 |  | 0 | 0 | 0
|  | C. Pilot for movement of vessel |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Tugboat, pilotassistance and line handlers: |  | 0 |  | 0 | 0 | 0
|  | As per account according to valid harbour tariffs | CANCELLED | 0 |  | 0 | 0 | 0
1032 | 500.27 | Cherry picker
|  | A. Rental per hour including driver (if needed) | CANCELLED | 0 | 1000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | B. Rental per day including driver (if needed) | CANCELLED | 0 | 6500 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | C. Rental of scissorlift | CANCELLED | 0 | 3500 | 0 | 0 | 0
|  | Per day, excl driver |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Driver based on normal working hours |  | 0 |  | 0 | 0 | 0
1033 | 500.29 | Man hole covers
|  | A. Per manhole incl. Cover incl. new gasket. | CREW | 0 | 950 | 0 | 0 | 0
|  | Based on MAX size 600*800mm |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Renovation of manhole studs: |  | 0 |  | 0 | 0 | 0
|  | by turning out, min. 5 pcs per manhole, each |  | 0 | 85 | 0 | 0 | 0
|  | by drilling out, min. 5 pcs per manhole, each |  | 0 | 275 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | B. Protection on opened manhole, per manhole |  | 0 |  | 0 | 0 | 0
|  | Installation of protection bars around manhole, per location |  | 0 | 1500 | 0 | 0 | 0
1034 | 500.30 | Watch keeping
|  | To be agreed upon if needed |  | 0 |  | 0 | 0 | 0
1035 | 500.32 | Wharfage fee
|  | Repair berth / wharfage, each day | NA | 0 | 23950 | 0 | 0 | 0
|  | Price valid for first 9 days alongside |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Repair berth / wharfage after 9 days, each day | NA | 0 | 27300 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Rental of alongside area space, per started week | NA | 0 | 4600 | 0 | 0 | 0
1036 | 500.33 | Hull preparation
|  | HP-washing with 100 (500) bar (Silicone paint system): |  | 0 |  | 0 | 0 | 0
|  | Flatbottom, each m2 |  | 0 | 19 | 0 | 0 | 0
|  | Sidebottom, each m2 | QUOTED | 2890 | 21 | 60690 | 0 | 60690
|  | Topside, each m2 |  | 0 | 21 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Painting existing name and homeport | QUOTED | 1 | 6170 | 6170 | 0 | 6170
|  |  |  | 0 |  | 0 | 0 | 0
|  | Painting existing Cargo and plimsol, thruster and bulp |  | 0 |  | 0 | 0 | 0
|  | markingsmarks | QUOTED | 1 | 5665 | 5665 | 0 | 5665
|  |  |  | 0 |  | 0 | 0 | 0
|  | Markup existing waterline per meter |  | 0 | 11.5 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Drains and Scuppers: |  | 0 |  | 0 | 0 | 0
|  | Drainplugs fitted/removed, each |  | 0 | 135 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Covering of: |  | 0 |  | 0 | 0 | 0
|  | Anodes and sensors, each |  | 0 | 21 | 0 | 0 | 0
|  | ICCP anodes, each |  | 0 | 925 | 0 | 0 | 0
|  | Propellers, each |  | 0 | 580 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Cleaning of dock bottom before and after Hull Treatment | QUOTED | 1 | 100000 | 100000 | 0 | 100000
1037 | 1001.01 | Bilge Keels crack
|  | Rewelding of all cracks: Priced after inspection | QUOTED | 1 | 240000 | 240000 | 0 | 240000
|  | Paint outside and in void spaces | QUOTED | 1 | 65000 | 65000 | 0 | 65000
1038 | 1001.03 | Cracks on flaps for stern ramps to be welded
|  | Cracks on flaps for stern ramps to be welded |  | 1 | 43300 | 43300 | 0 | 43300
|  | Job to be discussed during yard time. |  | 0 |  | 0 | 0 | 0
|  | Lift |  | 1 | 10500 | 10500 | 0 | 10500
|  |  |  | 0 |  | 0 | 0 | 0
|  | Rewelding of all cracks: Paint work |  | 1 | 8700 | 8700 | 0 | 8700
1039 | 1001.04 | Overboard valve for grey water damaged by TUG
|  | During Tug asssistance in ZEE the tugboat missed the |  | 0 |  | 0 | 0 | 0
|  | PUSH MARK on PS aft, and damaged the structure and |  | 0 |  | 0 | 0 | 0
|  | overboard valve for grey water on deck 2 level." |  | 1 | 25800 | 25800 | 0 | 25800
|  | To be discussed at yard. |  | 0 |  | 0 | 0 | 0
1040 | 1018.01 | Bridge outside treatment
|  | Maintenance of sprinkler nozzles, wiper |  | 0 |  | 0 | 0 | 0
|  | casettes and painting jobs on "bridge wings". |  | 0 |  | 0 | 0 | 0
|  | Assistance from crane + basket is needed for this. |  | 1 | 56400 | 56400 | 0 | 56400
|  | Cherry picker / crane |  | 1 | 15300 | 15300 | 0 | 15300
|  | Job to be discussed. |  | 0 |  | 0 | 0 | 0
1041 | 1041.01 | Becker Rudder clearence
|  | Measuring of rudder clearances with gauge | QUOTED | 1 | 7000 | 7000 | 0 | 7000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Rudder plugs removed/refitted, each | NA | 0 | 2000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Rudder access plates removed/refitted, each | NA | 0 | 25000 | 0 | 0 | 0
1042 | 1108.01 | Insulation on upper decks
|  | Insulation on deck 5 and Deck 7 are very damp |  | 0 |  | 0 | 0 | 0
|  | and rust have started on the washers and nails that |  | 0 |  | 0 | 0 | 0
|  | hold the material up. |  | 0 |  | 0 | 0 | 0
|  | Job to be discused with Yard. |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Demount existing insulation and insulation pins, delivery |  | 0 |  | 0 | 0 | 0
|  | and installation of new insulation pines and |  | 0 |  | 0 | 0 | 0
|  | insulation finished with aluminum foil. Total of 50m2. | QUOTED | 1 | 93750 | 93750 | 0 | 93750
|  |  |  | 0 |  | 0 | 0 | 0
|  | Mobile staging 3w x 3D x 3,5H, Rental per staging |  | 0 | 10000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Rental of small scissorlift, per piece | QUOTED | 6 | 2500 | 15000 | 0 | 15000
1043 | 1108.02 | Change of insulation material
|  | Isolation material on pipe work in separator room |  | 0 |  | 0 | 0 | 0
|  | is to be replaced according to Engine crews instruction. |  | 1 | 48490 | 48490 | 0 | 48490
|  | Priced after joint inspection with crew to agree SOW |  | 0 |  | 0 | 0 | 0
1044 | 1108.03 | Isolation for ME2 preheat piping
|  | Isolation for ME2 preheat piping: |  | 0 |  | 0 | 0 | 0
|  | ME2 Preheat piping to be isolated. Isolating missing |  | 0 |  | 0 | 0 | 0
|  | from suction line at HT pumps to inlet of Main Engine |  | 1 | 38610 | 38610 | 0 | 38610
|  | Priced after joint inspection with crew to agree SOW |  | 0 |  | 0 | 0 | 0
1045 | 1111.01 | Fuel Oil leak
|  | Fuel leaking into void tank 16PS. |  | 0 |  | 0 | 0 | 0
|  | Hole to be welded and repaired according Class. |  | 1 | 28200 | 28200 | 0 | 28200
|  |  |  | 0 |  | 0 | 0 | 0
|  | Cleaning of tank, based empty tank, each tank: |  | 0 |  | 0 | 0 | 0
|  | Open/close, gasfreeing of tanks, as per account |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Based on suction of tank bottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0
|  | of max 2 m3 of oily pumpable waste | QUOTED | 2 | 8840 | 17680 | 0 | 17680
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional suction, each hour | QUOTED | 4 | 1150 | 4600 | 0 | 4600
|  | Possible additional disposal, each m3 | QUOTED | 4 | 1200 | 4800 | 0 | 4800
|  | Possible additional cleaning: to be agreed upon |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Disposal of unpumpable per ton | QUOTED | 2 | 7500 | 15000 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Steel and paint repair priced after joint inspection |  | 0 |  | 0 | 0 | 0
|  | to agree SOW |  | 0 |  | 0 | 0 | 0
1046 | 1111.02 | Fuel return valves on both main engines
|  | Replacement of owner supplied fuel return valve, each | QUOTED | 4 | 6000 | 24000 | 0 | 24000
|  | Based on free access and drained system, excl insulation |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Draining of fuel system incl vacuum truck |  | 1 | 46300 | 46300 | 0 | 46300
|  |  |  | 0 |  | 0 | 0 | 0
|  | De- and remount insulation matt on valve for access. |  | 0 |  | 0 | 0 | 0
|  | Each valve | QUOTED | 4 | 1060 | 4240 | 0 | 4240
|  | based on reuse of existing materials. |  | 0 |  | 0 | 0 | 0
1047 | 1111.03 | Change valve for transfer line HFO
|  | Replacement of owner supplied filling valve, each | QUOTED | 1 | 8000 | 8000 | 0 | 8000
|  | Based on free access and drained system, excl insulation |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Draining of fuel oil system incl vacuum truck |  | 1 | 26700 | 26700 | 0 | 26700
|  |  |  | 0 |  | 0 | 0 | 0
|  | De- and remount insulation matt on valve for access. |  | 0 |  | 0 | 0 | 0
|  | Each valve | QUOTED | 1 | 1060 | 1060 | 0 | 1060
|  | based on reuse of existing materials. |  | 0 |  | 0 | 0 | 0
1048 | 1111.04 | Cleaning of sludge tank (HFO)
|  | No.1 Sludge sett. 32,4 m2 |  | 0 |  | 0 | 0 | 0
|  | No.2 Sludge tank 51 m3 |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Cleaning of tank, based empty tank, each tank: |  | 0 |  | 0 | 0 | 0
|  | Open/close, gasfreeing of tanks, as per account | CREW | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Based on suction of tank bottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0
|  | of max 2 m3 of oily pumpable waste | QUOTED | 2 | 8840 | 17680 | 0 | 17680
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional suction, each hour | QUOTED | 10 | 1150 | 11500 | 0 | 11500
|  | Possible additional disposal, each m3 | QUOTED | 9 | 1200 | 10800 | 0 | 10800
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional cleaning: to be agreed upon | QUOTED | 1 | 141000 | 141000 | 0 | 141000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Disposal of unpumpable per ton | QUOTED | 4 | 7500 | 30000 | 0 | 30000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Staging |  | 1 | 14300 | 14300 | 0 | 14300
1049 | 1111.05 | Scrubber sluge tank (37,7 m3)
|  | Cleaning of tank, based empty tank, each tank: |  | 0 |  | 0 | 0 | 0
|  | Open/close, gasfreeing of tanks, as per account |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Based on suction of tank bottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0
|  | of max 2 m3 of oily pumpable waste | QUOTED | 1 | 8840 | 8840 | 0 | 8840
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible additional suction, each hour | QUOTED | 26 | 1150 | 29900 | 0 | 29900
|  | Possible additional disposal, each m3 | QUOTED | 8 | 1200 | 9600 | 0 | 9600
|  | Possible additional cleaning: to be agreed upon |  | 1 | 76000 | 76000 | 0 | 76000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Disposal of unpumpable per ton | QUOTED | 2 | 7500 | 15000 | 0 | 15000
1050 | 1114.01 | Collision valve exchange
|  | Replacement of owner supplied collision valve, each | QUOTED | 1 | 24750 | 24750 | 0 | 24750
|  | Based on free access and drained system, excl insulation |  | 0 |  | 0 | 0 | 0
|  | Hydraulic connection, electrical installation and fiber |  | 0 |  | 0 | 0 | 0
|  | piping |  | 1 | 46800 | 46800 | 0 | 46800
|  |  |  | 0 |  | 0 | 0 | 0
|  | Draining of system incl vacuum truck |  | 1 | 13700 | 13700 | 0 | 13700
1051 | 1120.01 | Welding of cleat sockets for bulkehead doors deck 5 SB+PS
|  | Priced after joint inspection to agree SOW |  | 1 | 43700 | 43700 | 0 | 43700
1052 | 1120.02 | Bulkhead door D5 PS bended
|  | Bulkhead door (Ramp way door) on deck 5 PS |  | 0 |  | 0 | 0 | 0
|  | has been bended by forklift. Door has been bended |  | 0 |  | 0 | 0 | 0
|  | in bottom part |  | 0 |  | 0 | 0 | 0
|  | + 3 frames. |  | 0 |  | 0 | 0 | 0
|  | No watertight in bottom, gap 1cm or more. |  | 0 |  | 0 | 0 | 0
|  | Door is categorized as “GASTIGHT” |  | 0 |  | 0 | 0 | 0
|  | Incl insulation |  | 1 | 74200 | 74200 | 0 | 74200
|  | Priced after joint inspection to agree SOW |  | 0 |  | 0 | 0 | 0
1053 | 1121.01 | Replace rubber sealing for hatch to B/T room
|  | Dis-mounting of hatch, replacement of owner supplied gasket |  | 0 |  | 0 | 0 | 0
|  | Each hatch | QUOTED | 1 | 37250 | 37250 | 0 | 37250
|  | excl repaires and painting |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Cleaning and painting of gasket channel |  | 0 |  | 0 | 0 | 0
|  | Each hatch | QUOTED | 1 | 6000 | 6000 | 0 | 6000
1054 | 1121.02 | Renewal of gaskets for Pilot door PS
|  | Replacement of owner supplied gasket in Pilot door without |  | 0 |  | 0 | 0 | 0
|  | dismounting of door, each door |  | 0 | 18500 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Dis-mounting of door for access, each door |  | 0 | 28500 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Cleaning and painting of gasket channel |  | 0 |  | 0 | 0 | 0
|  | Each door |  | 0 | 21600 | 0 | 0 | 0
|  | Materials only |  | 1 | 19500 | 19500 | 0 | 19500
1055 | 1201.01 | Redesign Anchor Recess
|  | Doubler plate to be welded outside "anchor recess". PS & SB. |  | 1 | 143700 | 143700 | 0 | 143700
|  | To be discused during inspection. |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Priced after joint inspection to agree SOW |  | 0 |  | 0 | 0 | 0
1056 | 1225.01 | Modification drain deck 8 PS
|  | Drain from grey water pipe pouring water out |  | 0 |  | 0 | 0 | 0
|  | on deck 8 at assembly station, therefore at lot of dirt is |  | 0 |  | 0 | 0 | 0
|  | collected in this area. |  | 0 |  | 0 | 0 | 0
|  | Modification needed for grey water drain pipe to either |  | 0 |  | 0 | 0 | 0
|  | be extended or connected with other pipe for grey water |  | 0 |  | 0 | 0 | 0
|  | running in the area "next to". |  | 1 | 61100 | 61100 | 0 | 61100
|  | Priced after joint inspection to agree SOW |  | 0 |  | 0 | 0 | 0
1057 | 1250.01 | New cabinet for 230V to be installed
|  | New cabinet for 230V to be installed: |  | 0 |  | 0 | 0 | 0
|  | Yard to instal 230V cabinet in Engine room. |  | 0 |  | 0 | 0 | 0
|  | Estimate 50m of cabel and cabinet to be installed |  | 1 | 63400 | 63400 | 0 | 63400
|  | More specified is necessar for pricing |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Size / type of cabinet, type of cables required, location |  | 0 |  | 0 | 0 | 0
|  | of installation and where power supply can be taken from. |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Supply of equipment: Owner or Yard |  | 0 |  | 0 | 0 | 0
1058 | 2701.01 | New bearings in AHU 1 fan
|  | Electro motor to be overhauled with new bearings. |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Norm. Elmotor overhaul in workshop. Disconnect/connect |  | 0 |  | 0 | 0 | 0
|  | onboard & rigging |  | 0 |  | 0 | 0 | 0
|  | Disassemble. Wash & drying. Assemble with new owner |  | 0 |  | 0 | 0 | 0
|  | supplied bearings. |  | 0 |  | 0 | 0 | 0
|  | Testrun & report, estimated size max 50kw | QUOTED | 1 | 29500 | 29500 | 0 | 29500
|  | Price based on free access onboard. |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Replacement of bearings in fan priced after inspection |  | 1 | 6800 | 6800 | 0 | 6800
|  | Delivery of bearing |  | 1 | 4600 | 4600 | 0 | 4600
1059 | 2701.02 | Filter AHU 1 & 2
|  | New holder to be mounted inside AHU 1 + 2 |  | 0 |  | 0 | 0 | 0
|  | (Air handling unit), to make room for new filter type. |  | 0 |  | 0 | 0 | 0
|  | Old construction to be removed first. |  | 1 | 22300 | 22300 | 0 | 22300
|  | Vessel will supply new filters and material for holders |  | 0 |  | 0 | 0 | 0
|  | Priced after inspection |  | 0 |  | 0 | 0 | 0
1060 | 3127.01 | Overhaul of both main engine turbocharger
|  | Owner have arrange service engineers from ABB |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Assistance from yard 2 mechanics |  | 0 |  | 0 | 0 | 0
|  | Yard assistance to owners service engineers: |  | 0 |  | 0 | 0 | 0
|  | Each person per 12 hour shift - Cleaning | QUOTED | 1 | 8500 | 8500 | 0 | 8500
|  | New gaskets |  | 1 | 19830 | 19830 | 0 | 19830
1061 | 3138.01 | Compensator to be changed
|  | Exhaust gas Compensator under exhaust gas boiler |  | 0 |  | 0 | 0 | 0
|  | Port Side to be changed. DN 1300. |  | 0 |  | 0 | 0 | 0
|  | Compensator is owner supply |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Replacement of owner supplied compensator included gasket |  | 0 |  | 0 | 0 | 0
|  | each | QUOTED | 1 | 20700 | 20700 | 0 | 20700
|  | Insulation |  | 1 | 13200 | 13200 | 0 | 13200
|  |  |  | 0 |  | 0 | 0 | 0
|  | Staging if necessary priced after inspection |  | 1 | 11200 | 11200 | 0 | 11200
1062 | 3150.01 | Cable penetrations Main Engines
|  | All cable penetrations for sensor inside Main Engines |  | 0 |  | 0 | 0 | 0
|  | have to be changed. All cables have to be removed and |  | 0 |  | 0 | 0 | 0
|  | new penetrations installed. |  | 0 |  | 0 | 0 | 0
|  | Rubber penetrations is owner supply. |  | 0 |  | 0 | 0 | 0
|  | In total 18 penetrations to be changed. Electrical job |  | 0 |  | 0 | 0 | 0
|  | Incl scaffolding |  | 1 | 83650 | 83650 | 0 | 83650
|  | Priced after inspection Incl |  | 0 |  | 0 | 0 | 0
1063 | 3302.01 | Cleaning FWD LT cooler
|  | Type NT 250S B-6. |  | 0 |  | 0 | 0 | 0
|  | Serial no. SG-140/10528 |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Dismantling, cleaning and reassembling with old gaskets, |  | 0 |  | 0 | 0 | 0
|  | each plate | QUOTED | 334 | 327 | 109218 | 0 | 109218
|  | Possible change of owners supplied gaskets, each gasket |  | 0 | 186 | 0 | 0 | 0
1064 | 3302.02 | Cleaning of closed loop Cooler
|  | 2 pcs closed loop Cooler´s to be cleaned. |  | 0 |  | 0 | 0 | 0
|  | Type T20-PFG (AlfaLaval)Serial no. 30110 37239 |  | 0 |  | 0 | 0 | 0
|  | Serial no. 30110 37239 |  | 0 |  | 0 | 0 | 0
|  | Dismantling, cleaning and reassembling with old gaskets, |  | 0 |  | 0 | 0 | 0
|  | each plate | QUOTED | 480 | 327 | 156960 | 0 | 156960
|  | Possible change of owners supplied gaskets, each gasket |  | 0 | 186 | 0 | 0 | 0
1065 | 3336.01 | New Bilge Pump Bowthruster room
|  | Preparation for new Bilge Pump to be installed in Bow |  | 0 |  | 0 | 0 | 0
|  | Thruster room. |  | 0 |  | 0 | 0 | 0
|  | Yard to prepare pipes for new bilge pump. |  | 1 | 70700 | 70700 | 0 | 70700
|  | New Bilge pump will not be delivered before dock time |  | 0 |  | 0 | 0 | 0
|  | Scope of work to be discused upon arrival. |  | 0 |  | 0 | 0 | 0
1066 | 3338.01 | Renewal of overboard valves for draft sensors
|  | Replacement of owner supplied draft valve, each | QUOTED | 4 | 9500 | 38000 | 0 | 38000
|  | Based on plug and play |  | 0 |  | 0 | 0 | 0
|  | Adjustment of actuator for valves |  | 2 | 3380 | 6760 | 0 | 6760
|  |  |  | 0 |  | 0 | 0 | 0
|  | Replacement of owner supplied sensor: |  | 0 |  | 0 | 0 | 0
|  | More specified information is necessary |  | 0 |  | 0 | 0 | 0
1067 | 3338.02 | New Drencher Valve
|  | Replacement of owner supplied drencher valve, each | QUOTED | 1 | 15750 | 15750 | 0 | 15750
|  | Based on free access and drained system, excl insulation |  | 0 |  | 0 | 0 | 0
1068 | 3338.03 | Change non return valve FWG
|  | Replacement of owner supplied non return valve, each | QUOTED | 3 | 6000 | 18000 | 0 | 18000
|  | Based on free access and drained system, excl insulation |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Draining of system to be discussed for pricing |  | 0 |  | 0 | 0 | 0
1069 | 3339.01 | Scupper valves
|  | Scupper valves not working sufficiently. |  | 0 |  | 0 | 0 | 0
|  | Assume total 22 pcs needs attention. |  | 0 |  | 0 | 0 | 0
|  | All from handles broken, valve stuck, not water |  | 0 |  | 0 | 0 | 0
|  | tight and not closing. |  | 0 |  | 0 | 0 | 0
|  | Final job to be discussed with vessels Chief Officer |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Overhauling of 25 pcs scubber valves without mounting |  | 0 |  | 0 | 0 | 0
|  | of valve houses |  | 1 | 159250 | 159250 | 0 | 159250
|  |  |  | 0 |  | 0 | 0 | 0
|  | Repair of 18 pcs actuators |  | 1 | 74880 | 74880 | 0 | 74880
|  |  |  | 0 |  | 0 | 0 | 0
|  | Access in tanks for overhauling of valves + reapir |  | 0 |  | 0 | 0 | 0
|  | of actuators |  | 1 | 54600 | 54600 | 0 | 54600
1070 | 3801.01 | WPS I-strut
|  | Welding repairs: |  | 0 |  | 0 | 0 | 0
|  | Estimated cost basedon same SOW as done |  | 0 |  | 0 | 0 | 0
|  | on Humbria Seaways in Januar 2023 |  | 1 | 180000 | 180000 | 0 | 180000
|  | Fixed price after joint inspection and agreed SOW |  | 0 |  | 0 | 0 | 0
1071 | 3801.02 | Test of propeller movement
|  | Done by crew: Yard info only | INFO | 0 |  | 0 | 0 | 0
1072 | 3802.01 | Wear down
|  | Staging, ropeguard removed/refitted and oil drained, |  | 0 |  | 0 | 0 | 0
|  | each side | QUOTED | 2 | 25000 | 50000 | 0 | 50000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Tail shaft wear down measurement by gauge, each side | QUOTED | 2 | 8000 | 16000 | 0 | 16000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Further yard assistance to owners service engineers: |  | 0 |  | 0 | 0 | 0
|  | Each person per 12 hour shift |  | 6 | 8500 | 51000 | 0 | 51000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Change of 8 pcs Bera 35 |  | 8 | 680 | 5440 | 0 | 5440
1073 | 3802.02 | Sterntube seal
|  | See item 3802.01 |  | 0 |  | 0 | 0 | 0
1074 | 3802.03 | Bulkhead seal size 440
|  | Owner have arrange SKF service engineer |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Yard assistance to owners service engineers: |  | 0 |  | 0 | 0 | 0
|  | Each person per 12 hour shift |  | 6 | 8500 | 51000 | 0 | 51000
1075 | 3802.04 | Stern tube conversion Airspace
|  | Owner have arrange Simplex service Technician |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Yard assistance to owners service engineers: |  | 0 |  | 0 | 0 | 0
|  | Each person per 12 hour shift | CANCELLED | 0 |  | 0 | 0 | 0
1076 | 3805.01 | Propellershaft withdrawal
|  | Propeller shaft withdrawal, each | CANCELLED | 0 | 180000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Propellershaft transported to wotkshop and back, each | CANCELLED | 0 | 50000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Propeller blades dis- and remounted, each | CANCELLED | 0 | 11000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Transport to and from workshop, each | CANCELLED | 0 | 2000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Dis-mounting of Rudder Blade and lifted aside | CANCELLED | 0 | 150000 | 0 | 0 | 0
|  | Based on free access |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Possible installation of padeyes, excl possible internal |  | 0 |  | 0 | 0 | 0
|  | painting, each | CANCELLED | 0 | 10000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | SKF coupling dis- and remounted incl. Cleaning/overhaul, |  | 0 |  | 0 | 0 | 0
|  | each | CANCELLED | 0 | 50000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Access plate, each | CANCELLED | 0 | 25000 | 0 | 0 | 0
|  | Top plate removed for access, each | CANCELLED | 0 | 40000 | 0 | 0 | 0
|  | Rudder transported to and from workshop, each | CANCELLED | 0 | 35000 | 0 | 0 | 0
|  | Rudder stock protected for underring, each | CANCELLED | 0 | 15000 | 0 | 0 | 0
|  | Exchange of zinc, Bera 20 (2,0 kg), each | CANCELLED | 0 | 450 | 0 | 0 | 0
1077 |  | Dismounting, disassembling, cleaning and reinstallation of
|  | cylinder heads for M.E. |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Dismounting, disassembling, cleaning and reinstallation of cylinder |  | 0 |  | 0 | 0 | 0
|  | heads main engine. 7 pcs |  | 1 | 134680 | 134680 | 0 | 134680
|  |  |  | 0 |  | 0 | 0 | 0
|  | Disassembling all valves, stud taps – cleaning all parts, grinding of |  | 0 |  | 0 | 0 | 0
|  | seats and reassembling - 7 pcs |  | 1 | 138775 | 138775 | 0 | 138775
|  |  |  | 0 |  | 0 | 0 | 0
|  | 2 Spare cylinder heads |  | 0 |  | 0 | 0 | 0
|  | Cleaning and grinding of seats - 2 pcs |  | 1 | 14560 | 14560 | 0 | 14560
|  | Insulation + transport |  | 1 | 26800 | 26800 | 0 | 26800
1078 |  | Prepare 5 boiler´s for class.
|  | 1 x Oil fired boiler Aalborg OS-TCi. |  | 0 |  | 0 | 0 | 0
|  | 2 x Exhaust gas boiler Aalborg XS-2V Main Engine |  | 0 |  | 0 | 0 | 0
|  | 2x Exhaust gas boiler Aalborg XS-TC7A AUX |  | 0 |  | 0 | 0 | 0
|  | Boilers opened/closed for inspection |  | 1 | 26200 | 26200 | 0 | 26200
1079 |  | Repair of Bima Grip (Safe Grip) on Decks –
|  | small spots on Decks | QUOTED | 104 | 520 | 54080 | 0 | 54080
1080 |  | Cross over inspection.
|  | We are having a lot of scallops in our sea water system. |  | 0 |  | 0 | 0 | 0
|  | We see them in our SW system and scrubber system. |  | 0 |  | 0 | 0 | 0
|  | We need to check cross over and properly have it cleaned. |  | 1 | 210350 | 210350 | 0 | 210350
|  | (see pictures attached) |  | 0 |  | 0 | 0 | 0
|  | Disposal |  | 25 | 7500 | 187500 | 0 | 187500
1081 |  | Change of all valves on our boilers
|  | (except safety valves, they have been changed by crew). |  | 0 |  | 0 | 0 | 0
|  | Valves are onboard. |  | 0 |  | 0 | 0 | 0
|  | Exchange of old valves with new valves + adjustememt of |  | 0 |  | 0 | 0 | 0
|  | pressure for new safety valves + renovation of 6 pcs water |  | 0 |  | 0 | 0 | 0
|  | level |  | 1 | 143000 | 143000 | 0 | 143000
|  |  |  | 0 |  | 0 | 0 | 0
|  | Renovation of 100 pcs old DN 25 valves and delivered |  | 0 |  | 0 | 0 | 0
|  | back to ship |  | 1 | 84500 | 84500 | 0 | 84500
1082 |  | Both our seawater filter in the intake line, has broken the
|  | lifting hinges off. |  | 1 | 21100 | 21100 | 0 | 21100
|  | New once needs to be welded on. |  | 0 |  | 0 | 0 | 0
|  | It is stainless steel |  | 0 |  | 0 | 0 | 0
1083 |  | -After heavy leak on our Naoh system, most of the pipe
|  | isolation is broken. |  | 1 | 28080 | 28080 | 0 | 28080
|  | It needs to be repaired |  | 0 |  | 0 | 0 | 0
1084 |  | We have 2 fire dampers for the engine room that are
|  | not able to close. |  | 0 |  | 0 | 0 | 0
|  | This is due to corrosion. |  | 0 |  | 0 | 0 | 0
|  | They need to be overhauled. (see pictures attached) |  | 0 |  | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0
|  | Repair of 2 pcs fire dampers + mounting for greasing |  | 2 | 24240 | 48480 | 0 | 48480
|  |  |  | 0 |  | 0 | 0 | 0
|  | Silencers dismount/mounted for access |  | 2 | 6500 | 13000 | 0 | 13000
1085 |  | We have already order cleaning for the fwd LT cooler, but we
|  | would also like the aft LT cooler to be cleaned. |  | 0 |  | 0 | 0 | 0
1086 |  | We need to make railings on top of each casing (PS +SB).
|  | Ivan has pictures of this, but maybe put it on Humbrias |  | 0 |  | 0 | 0 | 0
|  | dock plan. |  | 2 | 64800 | 129600 | 0 | 129600
1088 |  | Faultfinding on control box for filter on Main engine
|  | Faultfinding on control box for filter on Main engine |  | 1 | 5300 | 5300 | 0 | 5300
1089 |  | Repair of hole between VOID11P & 1WWBPS
|  | Repair needed for hole between above mentioned tanks. |  | 1 | 52800 | 52800 | 0 | 52800
1090 |  | Silencer for AHU 2
|  | New silencer for AHU 2 has to be constructed and mounted. |  | 1 | 18460 | 18460 | 0 | 18460
1091 |  | Oil storage on MD
|  | Modification of oil storage on main deck to be welded |  | 0 |  | 0 | 0 | 0
|  | above existing storage. | CANCELLED | 0 |  | 0 | 0 | 0
|  | Vessel will supply spilltray |  | 0 |  | 0 | 0 | 0
|  | ard will supply material for bracket, welding equipment etc. |  | 0 |  | 0 | 0 | 0
1092 |  | HFO Service & Settling valves.
|  | Change valves for HFO service & settling delivery/suction valves. |  | 0 |  | 0 | 0 | 0
|  | Vessel will supply valves |  | 0 |  | 0 | 0 | 0
|  | Yard will supply bolts, gasket etc. |  | 0 |  | 0 | 0 | 0
|  | Pipingarrangement full of HSFO so shipyard have to protect |  | 0 |  | 0 | 0 | 0
|  | the area to avoid contamination in the engine room. |  | 0 |  | 0 | 0 | 0
|  | After job completion, the area must be cleaned. |  | 0 |  | 0 | 0 | 0
|  | Replacement of owner supplied filling valve, each | QUOTED | 12 | 8000 | 96000 | 0 | 96000
1093 |  | Modification and installation of new compensators for
|  | A/C & Prov. Compressor cooling system |  | 0 |  | 0 | 0 | 0
|  | Piping arrangement to be modified and new compensators |  | 0 |  | 0 | 0 | 0
|  | to be installed. |  | 1 | 47400 | 47400 | 0 | 47400
|  | Vessel will supply new compensators. |  | 0 |  | 0 | 0 | 0
|  | Ship yard will supply rest. |  | 0 |  | 0 | 0 | 0
1094 |  | Assistance to C.S. Electric related to refer system etc.
|  | Assistance to C.S. Electric related to refer system etc. |  | 0 |  | 0 | 0 | 0
|  | Incl lift/scaffolding |  | 1 | 528200 | 528200 | 0 | 528200
1095 |  | Food in yard canteen for owners sub-contractors.
|  | Food in yard canteen for owners sub-contractors. |  | 1 | 15100 | 15100 | 0 | 15100
1096 |  | Job 1063 Cont.
|  | Cleaning of aft LT cooler. |  | 0 |  | 0 | 0 | 0
|  | Dismantling, cleaning and reassembling with old gaskets, |  | 0 |  | 0 | 0 | 0
|  | Each plate | QUOTED | 334 | 327 | 109218 | 0 | 109218
1097 |  | Cleaning of scrubber overboard butterfly valve.
|  | Inspection with camera. |  | 1 | 21700 | 21700 | 0 | 21700
1098 |  | Painting of new and touched steel.
|  | Painting of new and touched steel. |  | 1 | 132255 | 132255 | 0 | 132255
1099 |  | Paintwork aft of funnels and in bow arear incl. cherry pickers.
|  | Paintwork aft of funnels and in bow arear incl. cherry pickers. |  | 1 | 41860 | 41860 | 0 | 41860
1100 |  | Hp-wash of side bottom PS+STB.
|  | Hp-wash of side bottom PS+STB. | JOB 1036 | 0 |  | 0 | 0 | 0
1101 |  | Job 1042 cont.
|  | Scallops to be cut in vertical stiffeners for drain of |  | 0 |  | 0 | 0 | 0
|  | water behind insulation materials |  | 1 | 16300 | 16300 | 0 | 16300
1102 |  | Cleaning of bilge water tank.
|  | Cleaning of bilge water tank. |  | 1 | 27250 | 27250 | 0 | 27250
|  | vacuum truck + disposal |  | 1 | 21800 | 21800 | 0 | 21800
1103 |  | 2 Pcs. windows in accommodation to be dismantled,
|  | frames to be cleaned and painted, glass to be reinstalled |  | 0 |  | 0 | 0 | 0
|  | with new gaskets. |  | 1 | 26000 | 26000 | 0 | 26000
1104 | VOR 1 | Grease pipes deck 7
|  | Renewal of grease pipes for door to upper ramp deck 7 |  | 0 |  | 0 | 0 | 0
|  | New pipes will be stainless, valve blocks will be reused | VOR 1 | 1 | 74750 | 74750 | 0 | 74750
|  | Cherry picker 3 days | VOR 1 | 1 | 10500 | 10500 | 0 | 10500
1105 |  | Control of high voltage installation and megger test
|  | of trafo + bow thruster motor |  | 1 | 32500 | 32500 | 0 | 32500
1106 |  | Pressure test of boiler pipe to (9 bar, to be confirmed by C.E.)
|  | Pressure test of boiler pipe to (9 bar, to be confirmed by C.E.) |  | 1 | 8500 | 8500 | 0 | 8500
1107 |  | Installation of 2 pcs. search lights on Monkey Island
|  | Installation of 2 pcs. search lights on Monkey Island |  | 1 | 14300 | 14300 | 0 | 14300
1108 |  | Grids for bow thruster to be inspected for loose bolts and
|  | tightened/renewed as needed. |  | 0 |  | 0 | 0 | 0
|  | Inspection only and lift |  | 1 | 7000 | 7000 | 0 | 7000
1109 |  | Cracked supports in STB+PS scrubber to be repaired by
|  | welding. |  | 1 | 27600 | 27600 | 0 | 27600
1110 |  | Cleaning of wing tanks no. 1+2 STB+PS.
|  | Cleaning of wing tanks no. 1+2 STB+PS. | CANCELLED | 0 |  | 0 | 0 | 0
1111 |  | Inspection of grids in STB ship side above pilot door.
|  | Inspection of grids in STB ship side above pilot door. |  | 1 | 26500 | 26500 | 0 | 26500
1112 |  | 2" fire line to be replaced on deck 9
|  | 2" fire line to be replaced on deck 9 |  | 1 | 16400 | 16400 | 0 | 16400
1113 |  | Rejects bracket for hydraulic cylinder on ramp.
|  | Rejects bracket for hydraulic cylinder on ramp. | VOR 2 | 1 | 35100 | 35100 | 0 | 35100
1114 |  | 1 pc. piston to be lifted on STB M.E.
|  | 1 pc. piston to be lifted on STB M.E. |  | 1 | 29380 | 29380 | 0 | 29380
1115 |  | Repair/change 2 pcs Eex start/stop box paint store
|  | Repair/change 2 pcs Eex start/stop box paint store |  | 1 | 21900 | 21900 | 0 | 21900
1116 |  | Delivery and installation of new self-closing valves in
|  | sounding pipes. - 4 pcs |  | 1 | 7280 | 7280 | 0 | 7280
1117 |  | Sea chests to be opened and cleaned.
|  | Sea chests to be opened and cleaned. |  | 1 | 22100 | 22100 | 0 | 22100
|  | Disposal |  | 2 | 7500 | 15000 | 0 | 15000
1118 |  | Cleaning of engine room / technical arears before departure.
|  | Cleaning of engine room / technical arears before departure. |  | 1 | 338285 | 338285 | 0 | 338285
1119 |  | Test/calibration breakers in MSB ect.
|  | Test/calibration breakers in MSB ect. |  | 11 | 5200 | 57200 | 0 | 57200
1120 |  | Temporary repair of curent transformer.
|  | Temporary repair of curent transformer. |  | 1 | 7800 | 7800 | 0 | 7800
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation | QUOTED | 1 | 10000 | 10000 | 0 | 10000
9993 |  | Discount according to agreement
|  | Discount according to agreement | 10% | 1 | -693500.6 | -693501 | 0 | -693501
|  |  |  | 0 |  | 0 | 0 | 0
|  | Discount agreed with vessels superintendent, because of |  | 0 |  | 0 | 0 | 0
|  | leaking valves on M.E. |  | 1 | -30000 | 0 | -30000 | -30000
|  | Further is agreed, that Fayard will supply new insulation pillows |  | 0 |  | 0 | 0 | 0
|  | for above |  | 0 |  | 0 | 0 | 0
|  |  | DKK |  |  | 6241505 | -30000 | 6211505 | 0