## Chapter 0
Ship name: |  | CROWN SEAWAYS
Case No.: |  | 231174
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2024-01-12 | 2024-01-22 | 2024-01-30 | 2024-02-22 | 2024-02-23 | 2025-05-06 | Total
1000 |  | Sag
1001 | 200.02 | Drydocking in/out
|  | Docking / undocking including first day | QUOTED | 1 | 65000 | 65000 | 0 | 0 | 0 | 0 | 0 | 65000
|  | Dock dues: Each following day | QUOTED | 24 | 20000 | 480000 | 0 | 0 | 0 | 0 | 0 | 480000
|  | 5/1-2024 - 29/1-2024 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1003 | 500.01 | Earthing of vessel
|  | Earthing of vessel | FREE | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1004 | 500.30 | Crane assistance
|  | Crane ass. to vessel, each hour up to 45 ton | QUOTED | 45 | 1500 | 60000 | 0 | 7500 | 0 | 0 | 0 | 67500
|  | Forklift 3/5 tons for Owner use, included driver, per hour. | QUOTED | 90 | 1000 | 90000 | 0 | 0 | 0 | 0 | 0 | 90000
|  | Assistance, carpets, provision etc and unloading deliveries | QUOTED | 1 | 106700 | 0 | 80000 | 26700 | 0 | 0 | 0 | 106700
1005 | 500.03 + 500.04 | Fire line pressure
|  | Per connection/disconnection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
|  | Maintaining pressure/supply of SW, per day | QUOTED | 25 | 500 | 12000 | 500 | 0 | 0 | 0 | 0 | 12500
|  | Rental of fire extinguisher: As per account. | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Booster pump |  | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
1006 | 500.02 | CO2 Plant
|  | Isolation / reconnection | QUOTED | 1 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 166300 | 50000 | 50000 | 22300 | 44000 | 0 | 0 | 166300
1008 |  | Isolation
|  | Isolation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1011 | 500.08 | Gangways
|  | Gangways first, second by crane basket | QUOTED | 3 | 4000 | 8000 | 0 | 4000 | 0 | 0 | 0 | 12000
|  | Daily hire charge. If any: None |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ramp forward |  | 0 |  | 8000 | -8000 | 0 | 0 | 0 | 0 | 0
1012 | 500.11 + 500.12 | Cooling for Aux. Engines
|  | Cooling water connection for Aux. Engines, each connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
|  | Supply of Cooling sea water per day | QUOTED | 25 | 500 | 12500 | 0 | 0 | 0 | 0 | 0 | 12500
|  | Return hoses in dock |  | 3 | 3000 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000
|  | Valves for back flushing of cooler incl pump aft |  | 1 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000
|  | Arrangement of pump, pallet tank in way of dock gate |  | 1 | 16700 | 0 | 0 | 16700 | 0 | 0 | 0 | 16700
1013 | 500.10 | Potable water supply
|  | Potable water connection, each time | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
|  | Supply of FW per m3 | QUOTED | 1969 | 40 | 4000 | 0 | 680 | 74080 | 0 | 0 | 78760
1014 | 500.17 + 500.18 | Black water disposal
|  | Black water connection on/off to Yard facilities | QUOTED | 1 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal per m3 | QUOTED | 35 | 95 | 4750 | 0 | -1425 | 0 | 0 | 0 | 3325
|  | Possible use of mud truck, each hour | QUOTED | 11 | 1150 | 11500 | 0 | 575 | 0 | 0 | 0 | 12075
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grey water connection on/off to Yard facilities | QUOTED | 2 | 4000 | 8000 | 0 | 0 | 0 | 0 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal per m3 |  | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible use of mud truck, each hour |  | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1015 | 500.19 | Oily water disposal
|  | Mudtruck per hour |  | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal of pumpable oily water per m3 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1016 |  | Internet Connection
|  | Internet Connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
|  | Maintenance | QUOTED | 25 | 350 | 8750 | 0 | 0 | 0 | 0 | 0 | 8750
1017 | 500.14 | Ballast Water
|  | Per connection/disconnection, each hose | CREW | 0 | 4000 | 4000 | -4000 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Per ton supplied |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Further assistance with ballasting: as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1018 | 500.25 | Gas Free Certificates
|  | First initial gasfree certificate | QUOTED | 1 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500
|  | If needed further gasfree certificates are also | QUOTED | 5 | 3500 | 17500 | 0 | 0 | 0 | 0 | 0 | 17500
|  | Please note that 1 certificate can cover multible areas/ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | compartments |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1019 | 200.01 + 200.03 | Wharfage
|  | Free of charge, subject to unsold capacity | FREE | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1020 | 200.04 | Agency
|  | Agency to be handled directly by Owner |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1022 | 500.05 | Fire Watch
|  | Fire Watch | INCL | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1026 | 500.20 | Man hole covers
|  | Manhole covers of/ on incl new gasket, each standard cover | CREW | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1027 | 500.21 | Bottom plugs
|  | Bottom plugs out/ in, each | QUOTED | 9 | 300 | 2100 | 600 | 0 | 0 | 0 | 0 | 2700
1030 | 500.24 | Cleaning of Ballast water
|  | Cleaning of Ballast water tanks: | CREW | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Basis empty tank and based hosing down and flushing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | through bottom plug, min. 80m3 tank, per m3 tank |  | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal of mud per ton |  | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1034 | 500.29 | Thickness measurements
|  | Ultrasonic thickness measurements (UTM-based on 1000 spots) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Minimum 350 shots, each shot | OWNER | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. access, staging and lifts |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1035 | 500.31 | Cherry Picker rental
|  | Rental per. Day | QUOTED | 3 | 3500 | 10500 | 0 | 0 | 0 | 0 | 0 | 10500
1036 | 500.32 | Staging
|  | Staging | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1037 | 500.33 | NDT testing
|  | A. Ultrasonic testing (UT) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | B. Magnetic particle Inspection (MPI) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | C. Liquid penetrant inspection (LPI) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Done by 3rd party, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1038 | 1001.03 | Fender list - welding
|  | Rewelding of cracks in fender, per spot/meter, each | QUOTED | 2 | 1500 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
|  | Excl. possible crane and/or lift, internal access and painting. |  | 1 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500
|  | Additional inserts, 2 pcs incl cherry picker |  | 1 | 26200 | 0 | 26200 | 0 | 0 | 0 | 0 | 26200
|  | Paint work |  | 1 | 6110 | 0 | 0 | 0 | 6110 | 0 | 0 | 6110
1039 | 1001.04 | Shell Plating - anodes
|  | AL 90 (9,0 kg.) each |  | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 80 (8,0 kg) each |  | 3 | 685 | 0 | 2055 | 0 | 0 | 0 | 0 | 2055
|  | AL 60 (6,0 kg.) each |  | 0 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 43 (4,0 kg.) each |  | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 15 (1,5 kg.) each |  | 6 | 440 | 2640 | 0 | 0 | 0 | 0 | 0 | 2640
|  | AL 114 (11,4 kg.) each |  | 25 | 1680 | 28560 | 13440 | 0 | 0 | 0 | 0 | 42000
|  | AL 170 (17,0 kg.) each |  | 3 | 2495 | 7485 | 0 | 0 | 0 | 0 | 0 | 7485
|  | Grinding of anodes and installation of new |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | on ropeguards |  | 1 | 14700 | 0 | 0 | 0 | 14700 | 0 | 0 | 14700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry picker for anode renewal, each per day | QUOTED | 6 | 3500 | 21000 | 0 | 0 | 0 | 0 | 0 | 21000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Prices are incl. dismounting of old, mounting of new |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | welded type, basis min. 50 pcs total. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1047 | 1016.13 | MGPS Anodes change
|  | 16 pieces of anodes in total, 8 pce CU and 8 pce FE |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | anodes located in 4 sea chests to be replaced. | QUOTED | 1 | 86800 | 86800 | 0 | 0 | 0 | 0 | 0 | 86800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible opening and closing of gratings in seachest for |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | access, each | INCL | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Further possible assistance to service engineers and possible |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | epoxy treatment: As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051 | 1018.02 | Painting - Funnel - Logo
|  | Funnel Area (350 m2), |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-Wash, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 15% mech. cleaning, min 0,25 m2 per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 15% Tu 2 coat, min 0,25 m2 per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 15% mech. cleaning, min 0,25 m2 per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 15% Tu 2 coat, min 0,25 m2 per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x FC. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SB and PS side DFDS LOGO malteser cross to be painted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1FC in white colour |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry Picker for access | QUOTED | 1 | 191200 | 0 | 191200 | 0 | 0 | 0 | 0 | 191200
|  | Reduction |  | 1 | -6000 | 0 | 0 | 0 | 0 | -6000 | 0 | -6000
1052 | 1018.03 | Topsides white - painting
|  | White Topside Area (3000 m2) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP wash 300 bar | QUOTED | 3000 | 11.5 | 34500 | 0 | 0 | 0 | 0 | 0 | 34500
|  | Mechanichal cleaning based 4% | QUOTED | 120 | 113.5 | 13620 | 0 | 0 | 0 | 0 | 0 | 13620
|  | Hosing down with lowpressure FW | QUOTED | 3000 | 4 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000
|  | Tu 1 coat min. 0,25 m2/spot, with roller and brush, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 9%, 270 m2 | QUOTED | 270 | 46 | 12420 | 0 | 0 | 0 | 0 | 0 | 12420
|  | Tu 1 coat min. 0,25 m2/spot, with roller and brush, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 9%, 270 m2 | QUOTED | 270 | 46 | 12420 | 0 | 0 | 0 | 0 | 0 | 12420
|  | Tu 1 coat min. 0,25 m2/spot, with roller and brush, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 9%, 270 m2 | QUOTED | 270 | 46 | 12420 | 0 | 0 | 0 | 0 | 0 | 12420
|  | Fc 1 coat, with roller and brush, 3.000 m2 | QUOTED | 3000 | 31.5 | 94500 | 0 | 0 | 0 | 0 | 0 | 94500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering, cleaning and painting of windows frames. | QUOTED | 1 | 280500 | 280500 | 0 | 0 | 0 | 0 | 0 | 280500
|  | Marking up line between white and blue | QUOTED | 1 | 4610 | 4610 | 0 | 0 | 0 | 0 | 0 | 4610
|  | Possible additional covering off, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053 | 1018.04 | Topside Blue and White - Cleaning included in 1018.03
|  | Topside + aft ramps, Area 4000m2 + 3000m2 + 350m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP wash with 300 bar, 7350 m2 | CANCELLED | 0 | 53530 | 53530 | 0 | 0 | 0 | 0 | -53530 | 0
|  | Chemical cleaning. min. 0,25 m2 per spot, Each m2 |  | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055 | 1018.06 | Anchor Painting and chain markings
|  | Both port and starboard anchors and cables to be ranged |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | on the dock bottom for inspection, calibration and surveys |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cables to be re-stowed. | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WJ-2 and painting of Anchor. Area 80 m2, to be given 1 x FC | QUOTED | 1 | 28875 | 28875 | 0 | 0 | 0 | 0 | 0 | 28875
|  | Connection schackles to be marked with clearly white paint, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Inspection only of ss bands - missing added |  | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
1057 | 1018.09 | Topsides Blue -painting incl Logo
|  | Topside blue + aft rampes, Area 4000 m2 + 350 m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP wash 300bar | QUOTED | 4350 | 11.5 | 50025 | 0 | 0 | 0 | 0 | 0 | 50025
|  | Mechanichal cleaning based 4% | QUOTED | 174 | 113.5 | 19749 | 0 | 0 | 0 | 0 | 0 | 19749
|  | Wash down with FW. 4.350 m2. | QUOTED | 4350 | 4 | 17400 | 0 | 0 | 0 | 0 | 0 | 17400
|  | Tu 1 coat min. 0,25 m2/spot basis 9% .391,50 m2. | QUOTED | 392 | 23 | 9005 | 0 | 0 | 0 | 0 | 0 | 9005
|  | Tu 1 coat min. 0,25 m2/spot basis 9% .391,50 m2. | QUOTED | 392 | 23 | 9005 | 0 | 0 | 0 | 0 | 0 | 9005
|  | Fc 1 coat . 4.350 m2 | QUOTED | 4350 | 15.75 | 68513 | 0 | 0 | 0 | 0 | 0 | 68513
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of existing logo "DFDS" on port- and Sb- side | QUOTED | 1 | 39530 | 39530 | 0 | 0 | 0 | 0 | 0 | 39530
|  | Painting of name and home port | QUOTED | 1 | 6590 | 6590 | 0 | 0 | 0 | 0 | 0 | 6590
|  | Covering, cleaning and painting of windows frames, each | QUOTED | 87 | 930 | 80910 | 0 | 0 | 0 | 0 | 0 | 80910
|  | Covering, cleaning and painting of port holes frames, each | QUOTED | 18 | 675 | 12150 | 0 | 0 | 0 | 0 | 0 | 12150
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional covering off, as per account. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1058 | 1018.10 | Ventilation grids in ship side, overhaul/new design
|  | Delivery and installation of 2 pcs. Single-stage |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | separators in aluminimum |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | coated RAL5011. Incl. Steel job for cutting frame |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and mounting of new flatbar in bottom |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Staging for access and painting new/touched. | QUOTED | 1 | 147120 | 147120 | 0 | 0 | 0 | 0 | 0 | 147120
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible repair of inside ducting | QUOTED | 1 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000
1060 | 1041.08 | Rudder pressure test
|  | Pressure test rudder blades, each | QUOTED | 1 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 7000
1062 | 1041.12 | Rudder- bearing and jump stop clearance
|  | Rudder- bearing and jump stop clearance, each rudder | QUOTED | 2 | 7000 | 14000 | 0 | 0 | 0 | 0 | 0 | 14000
1063 | 1041.13 | Jastram rotor
|  | Jastram Rudder Rotors RR 04 - serial no.156& 157: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist, each person |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | per 12 hour day shift |  | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Crane and forklift assiastace, each normal hour |  | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Staging each side of rudder blade, each staging |  | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible cherry picker, each day |  | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal of oil, each m3 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vacuum truck for removal of oil, each hour |  | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheets: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheet 06-01-2024 |  | 1 | 22570 | 22570 | 0 | 0 | 0 | 0 | 0 | 22570
|  | Timesheet 07-01-2024 |  | 1 | 12880 | 12880 | 0 | 0 | 0 | 0 | 0 | 12880
|  | Timesheet 08-01-2024 |  | 1 | 12620 | 12620 | 0 | 0 | 0 | 0 | 0 | 12620
|  | Timesheet 09-01-2024 |  | 1 | 23370 | 23370 | 0 | 0 | 0 | 0 | 0 | 23370
|  | Timesheet 10-01-2024 |  | 1 | 14410 | 14410 | 0 | 0 | 0 | 0 | 0 | 14410
|  | Timesheet 11-01-2024 |  | 1 | 14860 | 14860 | 0 | 0 | 0 | 0 | 0 | 14860
|  | Timesheet 14-01-2024 |  | 1 | 24620 | 0 | 24620 | 0 | 0 | 0 | 0 | 24620
|  | Timesheet 15-01-2024 |  | 1 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000
1064 | 1108.05 | Cardeck, Ramps and Hatch Covers - overhaul
|  | Ramps, Hatch covers and FCD to be done by McGregor x persons |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance with Crane assistance and forklift assistance to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | coordinated with McGregor |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Crane, each hour |  | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forklift, each hour |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Working power + various consumption + |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | work shop facilities and crane + cherry picker 19/1 | QUOTED | 1 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
1067 | 1108.08 | Car deck - cleaning and painting
|  | leaning and Painting of cardeck and forward access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to bow ramp. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning. min. 0,25 m2/spot. 3.000 m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, min 0,25 m2 /spot pr m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | basis 20%. 600 m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wash with Fw. 3.000 m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat with roller and brush, min 0,25 m2 / |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | spot pr m2 basis 20%. 600 m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu 1 coat with roller and brush, min 0,25 m2 /spot |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pr m2 basis 20%. 600 m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc 1 coat. 3.000 m2 | QUOTED | 1 | 253455.12 | 253455 | 0 | 0 | 0 | 0 | 0 | 253455
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | All yellow lane stribes to be repainted. Based on 884 meter | QUOTED | 1 | 38594.5 | 38595 | 0 | 0 | 0 | 0 | 0 | 38595
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Marking up lane numbers | QUOTED | 1 | 11375 | 11375 | 0 | 0 | 0 | 0 | 0 | 11375
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Marking up drain covers, 16 pcs | QUOTED | 1 | 16186.4 | 16186 | 0 | 0 | 0 | 0 | 0 | 16186
1072 | 1111.12 | Bilge water holding tank-CTR cleaning
|  | Bilge water holding tank-CTR (Bottom tank) FR. 68 – 77, 81,7 m3. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of tank, based empty tank.: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Open/close of tank, 2 manholes. | CANCELLED | 0 | 1150 | 2300 | 0 | -2300 | 0 | 0 | 0 | 0
|  | Gasfreeing of tank, as per account | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on suction of tank bottom incl. removal and disposal of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | max 2 m3 of oily pumpable waste | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional suction, | QUOTED | 1 | 80075 | 22425 | 57650 | 0 | 0 | 0 | 0 | 80075
|  | Possible additional disposal, each m3 | QUOTED | 16 | 1200 | 2400 | 16800 | 0 | 0 | 0 | 0 | 19200
|  | Man power |  | 1 | 164100 | 37200 | 126900 | 0 | 0 | 0 | 0 | 164100
|  | Materials |  | 1 | 32935 | 8732 | 24203 | 0 | 0 | 0 | 0 | 32935
|  | Hp wash Equipment |  | 1 | 18600 | 0 | 18600 | 0 | 0 | 0 | 0 | 18600
|  | Additional cleaning: to be agreed upon | INCL | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1078 | 1123.01 | Pool area
|  | Dismounting of overflow grills, delivery and installation of 3 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New overflow grilles in AISI316 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Steelwork in 2 locations inside channel to block channel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Staging for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Treatment: Cleaning with chemicals, Covering, Mechanical cleaning, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x TU and 1 x FC | QUOTED | 1 | 201280 | 201280 | 0 | 0 | 0 | 0 | 0 | 201280
|  | Reduction do to less scope |  | 1 | -40000 | -40000 | 0 | 0 | 0 | 0 | 0 | -40000
1083 | 1205.01 | Painting of stairs deck 9 to deck 11
|  | Stairway: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The steps must be cleaned and painted with antiskid |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint system to be used 1*FC 250 micron DFT and add |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0,9-1,4mm stones/ sand in the wet paint and 1 FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | paint applied by roller |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The stairs are divided into 3 sections. | QUOTED | 1 | 75200 | 75200 | 0 | 0 | 0 | 0 | 0 | 75200
1085 | 1301.01 | Anchor meassurement
|  | Anchors and chains ranged in dock, hp, messured and marked |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | with steel band | JOB 1055 | 0 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of anchors and chains | JOB 1055 | 0 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible painting of chain length markings: as per account | JOB 1055 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of chainlocker: | JOB 1055 | 0 | 30320 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional cleaning for painting and painting: | JOB 1055 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | priced after inspection of chain lockers |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1086 | 1302.01 | Mooring Winch , overhaull INFO ONLY
|  | Mooring Winch , overhaull INFO ONLY | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance, oxygen/acetylene and power supply | QUOTED | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of IPI incl transport |  | 1 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000
1089 | 1303.01 | Steering Gear SB and PS
|  | Assistance to owners service engineers, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheets: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheet 07-01-2024 |  | 1 | 23010 | 23010 | 0 | 0 | 0 | 0 | 0 | 23010
|  | Timesheet 08-01-2024 |  | 1 | 10630 | 10630 | 0 | 0 | 0 | 0 | 0 | 10630
|  | Timesheet 09-01-2024 |  | 1 | 21110 | 21110 | 0 | 0 | 0 | 0 | 0 | 21110
|  | Timesheet 10-01-2024 |  | 1 | 22400 | 22400 | 0 | 0 | 0 | 0 | 0 | 22400
1091 | 1401.01 | Life Boat Davits
|  | Life Boat Davits - No yard assistane expected | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Removal and disposal of old wires | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
1092 | 1401.02 | PAINTING Lifeboat Davits
|  | Lifeboat davit treatment: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, spot. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each davit | QUOTED | 3 | 63280 | 0 | 379680 | 0 | 0 | -189840 | 0 | 189840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MOB boat davit treatment: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, spot. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each davit | CANCELLED | 0 | 55240 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1095 | 1502.01 | Deck Drencher system
|  | Changing of corroded Drencher main pipes according to spec. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Dis- and remounting of ceiling panels for access, 100 m2 | QUOTED | 1 | 357300 | 357300 | 0 | 0 | 0 | 0 | 0 | 357300
1096 | 1707.01 | Rardars
|  | Rardars - Yard info only | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1097 | 2201.03 | Refurbuisments jobs in Passenger areas - INFO ONLY
|  | Refurbuisments jobs in Passenger areas - INFO ONLY | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1098 | 2201.04 | Galley and otherproduction areas - INFO ONLY
|  | Galley and otherproduction areas - INFO ONLY | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1099 | 2701.05 | Ventilation cleaning of funnels
|  | Clanning of ventilation Cannels in accomondation.: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of ventilation exhaust duct's, by cleaning from existing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | access hatches and hoods on the exhaust system, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | from the following |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of ventilation exhaust from Hot and Cold galley | QUOTED | 1 | 89890 | 89890 | 0 | 0 | 0 | 0 | 0 | 89890
|  | Cleaning of ventilation exhaust from Pizza | QUOTED | 1 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 54000
|  | Cleaning of laundry exhaust | QUOTED | 1 | 46190 | 46190 | 0 | 0 | 0 | 0 | 0 | 46190
1100 | 3103.01 | Spiroflex coupling ME 4
|  | Main clutch on main engine 4. To be dismantled in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | order to change rubber elements ( spiroflex ) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Clutch to be taken out in order to get access to the rubber |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | elements.Rubber elements to be changed and clutch to be mounted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | back in to position |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flender service engineer to supervise the job. Each clutch | QUOTED | 1 | 153325 | 153325 | 0 | 0 | 0 | 0 | 0 | 153325
1101 | 3128.01 | Charge Air Cooler - cleaning 8 pce INFO ONLY
|  | Charge Air Cooler - cleaning 8 pce INFO ONLY | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1102 | 3150.01 | Bridge Manouvring System ( DEGO 4) INFO ONLY
|  | Bridge Manouvring System ( DEGO 4) INFO ONLY | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1103 | 3227.01 | Soundabsorbers for exhaust system
|  | Topplate on funnel to be doubled in the area from frame |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 56 and fwd: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New scope to be done in T/M | QUOTED | 1 | 101155 | 80000 | 0 | 12400 | 8755 | 0 | 0 | 101155
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Topplate treatment: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, spot |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x TU (roller/brush) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC | QUOTED | 1 | 40800 | 40800 | 0 | 0 | 0 | 0 | 0 | 40800
1104 | 3338.04 | Ship side pipe outlets cleaning
|  | Ship side under water pipe outlets to be cleaned for hard |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | marine fouling by scraping. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning to be done in pipe the hole way to the over board/ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | scupper valves. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pipes to be coated internally with two coats of anticorrosive/ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | anti fouling paint. | QUOTED | 1 | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 17600
1105 | 3338.05 | Scupper valves
|  | Valves to be opened up and cleaned for fouling, flapper to be made |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | free to operate and the sealing rubber is to be renewed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remote maneuvering system (spindle type) to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | greased and proven in good working condition. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total 27 Scrubber valves with remote maneuvering. | QUOTED | 27 | 7525 | 203175 | 0 | 0 | 0 | 0 | 0 | 203175
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Control, test, adjustment of actuators for valves | QUOTED | 27 | 3000 | 81000 | -81000 | 81000 | 0 | 0 | 0 | 81000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible watertest of valves, each | CANCELLED | 0 | 1430 | 38610 | -38610 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Access etc |  | 1 | 8800 | 0 | 0 | 8800 | 0 | 0 | 0 | 8800
1106 | 3338.06 | Ship side valves
|  | Shipside valves are to be opened/closed and standard overhauled |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | without dismounting of valve housings, all to the satisfaction |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | of DNV class surveyor. Butterfly valves to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | cleaned and inspected in place. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total 36 valves. | QUOTED | 1 | 73590 | 73590 | 0 | 0 | 0 | 0 | 0 | 73590
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional for ship side valves according to inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DN40 globe valve removed for access/rep | VOR 11 | 1 | 1430 | 1430 | 0 | 0 | 0 | 0 | 0 | 1430
|  | DN65 globe valve removed for access/rep | VOR 11 | 1 | 2080 | 2080 | 0 | 0 | 0 | 0 | 0 | 2080
|  | 2 pcs DN100 globe valves removed for access/rep | VOR 11 | 1 | 6240 | 6240 | 0 | 0 | 0 | 0 | 0 | 6240
|  | DN100 globe valve overhauled | VOR 11 | 1 | 2470 | 2470 | 0 | 0 | 0 | 0 | 0 | 2470
|  | DN100 non return valve overhauled (PS Sanitary room) | VOR 11 | 1 | 2470 | 2470 | 0 | 0 | 0 | 0 | 0 | 2470
|  | DN 500 butterfly valve cleaned in situ (Scupper inlet) | VOR 11 | 1 | 2340 | 2340 | 0 | 0 | 0 | 0 | 0 | 2340
|  | Pipes de- and remounted for access | VOR 11 | 1 | 8325 | 8325 | 0 | 0 | 0 | 0 | 0 | 8325
|  | Floor plates de- and remounted for access | VOR 11 | 1 | 5460 | 5460 | 0 | 0 | 0 | 0 | 0 | 5460
1107 | 3339.05 | Window wash system on Bridge
|  | Changing of pipes according to specification. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based job carried out in Pex-pipes w/condens caps |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Dis- and remounting of ceilings for access, 50 m2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Delivery and installation of insulatio of 40 meter pipe | QUOTED | 1 | 182500 | 182500 | 0 | 0 | 0 | 0 | 0 | 182500
1108 | 3339.06 | Sundry Pipes GW Pipes
|  | Renewal of pipe as spec, 4 meter incl. Insulation and 2" |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pipe removed/refitted for access | QUOTED | 1 | 63130 | 63130 | 0 | 0 | 0 | 0 | 0 | 63130
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establish temporary hose to dry dock |  | 1 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500
1109 | 3339.07 | Sewage plant.
|  | MODIFICATIONS TO THE MBR AND ANOXIC TANK. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 6 pce. Flanges DN 65 to be welded on top the MBR |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | as indicated on the picture below |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | (holes to be made in the topof the tank) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tank to be coated proper according to EVAC paint specification |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | min. 320 micron DFT after the instalation. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New inspection glass to be mounted in the MBR unit. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vi fjerner den del af casen og du får en ny pris på det på MBR tk. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New inspection glass to be mounted in the Anoxic tk. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Glass to be mounted on the aft of the tank in the middle. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Diameter of the inspection glasses to be approx. 400mm . |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tanks to be painted after the installation minimum 320 DFT |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation to be similar as the existing one on the MBR. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New price "MODIFICATIONS TO THE MBR AND ANOXIC TANK" | QUOTED | 1 | 169300 | 169300 | 0 | 0 | 0 | 0 | 0 | 169300
|  | excl. New inspection glass to be mounted in the MBR unit: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reduction for cancelled paint work |  | 1 | -15000 | -15000 | 0 | 0 | 0 | 0 | 0 | -15000
1110 | 3801.01 | Propeller - polish
|  | Normal polishing of main propeller, Total 2 main propeller | QUOTED | 2 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
1111 | 3801.02 | Propeller blades
|  | Dismantling of propeller blades, each | QUOTED | 4 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 80000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lifting/transport of propeller blade within the yard, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | each | CANCELLED | 0 | 4600 | 18400 | 0 | 0 | 0 | -18400 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible machining of blade foots if found necessasry, each | NA | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydraulic tools for tensioning | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning and change of blade seals |  | 0 |  | 20000 | -20000 | 0 | 0 | 0 | 0 | 0
1113 | 3802.05 | Propeller shaft seal - renewal
|  | PS and SB outer sterntube seals to be changed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Draining and destruction of stern tupe, 2500 liter, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | each stern tube (SB Only) | QUOTED | 1 | 11750 | 11750 | 0 | 0 | 0 | 0 | 0 | 11750
|  | Refill stern tube with oil to be done by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist for changing of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | propeller shaft seals: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift |  | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Spare parts |  | 1 | 45640 | 0 | 0 | 45640 | 0 | 0 | 0 | 45640
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheets: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheet 08-01-2024 |  | 1 | 16180 | 16180 | 0 | 0 | 0 | 0 | 0 | 16180
|  | Timesheet 09-01-2024 |  | 1 | 17410 | 17410 | 0 | 0 | 0 | 0 | 0 | 17410
|  | Timesheet 10-01-2024 |  | 1 | 16610 | 16610 | 0 | 0 | 0 | 0 | 0 | 16610
|  | Timesheet 12-01-2024 |  | 1 | 12320 | 0 | 12320 | 0 | 0 | 0 | 0 | 12320
|  | Timesheet 13-01-2024 |  | 1 | 12850 | 0 | 12850 | 0 | 0 | 0 | 0 | 12850
1114 | 3802.06 | Tail shaft wear down
|  | Measuring Tail shaft wear down with poker guage. Each | QUOTED | 2 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
|  | Included staging and dis- remount of rope guards |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Renew of owners delivered zink , each side | QUOTED | 2 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
1118 | 3805.08 | Propellershaft Withdrawal - partly
|  | Propellershaft Withdrawal - partly | JOB 1116 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1119 | 3811.01 | Bow & Stern Thrusters w/Motors & Fans
|  | Bow thrusters Kamewa no. 1 TT 2400 D/AS - CP: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Thruster gratings opened and closed (welded) 2 pcs. | CANCELLED | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rope guard to be removed and refitted, each | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
|  | Oil drained from thruster, per unit. | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
|  | Oil to be refilled by crew" |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scaffolding, 4 pcs |  | 4 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
|  | Disposal of oil |  | 1 | 1200 | 600 | 0 | 0 | 0 | 0 | 0 | 600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Complete underwater thruster dismounted and transportation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to and from yard workshop for overhaul and refittingafter |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | overhaul , per unit | CANCELLED | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible removal and refitting of el-motor,, per unit |  | 0 | 40000 | 40000 | -40000 | 0 | 0 | 0 | 0 | 0
|  | Further assistance to owners Kongsberg service engineer: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour shift |  | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhaul of el-motor: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismount/ remount motor incl. transport to/from workshop |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Motor is washed, oven dried and evt. varnished |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bearings renewed. (Ovner supply) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meggertest and report. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each e-motor | QUOTED | 1 | 106290 | 106290 | 0 | 0 | 0 | 0 | 0 | 106290
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible repairs and materials, as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of bearings |  | 1 | 49680 | 0 | 0 | 0 | 49680 | 0 | 0 | 49680
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheets: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheet 07-01-2024 |  | 1 | 16460 | 16460 | 0 | 0 | 0 | 0 | 0 | 16460
|  | Timesheet 08-01-2024 |  | 1 | 35200 | 35200 | 0 | 0 | 0 | 0 | 0 | 35200
|  | Timesheet 09-01-2024 |  | 1 | 45960 | 45960 | 0 | 0 | 0 | 0 | 0 | 45960
|  | Timesheet 10-01-2024 |  | 1 | 24420 | 24420 | 0 | 0 | 0 | 0 | 0 | 24420
|  | Timesheet 11-01-2024 |  | 1 | 47210 | 47210 | 0 | 0 | 0 | 0 | 0 | 47210
|  | Timesheet 12-01-2024 |  | 1 | 21760 | 0 | 21760 | 0 | 0 | 0 | 0 | 21760
|  | Timesheet 13-01-2024 |  | 1 | 26420 | 0 | 26420 | 0 | 0 | 0 | 0 | 26420
|  | Timesheet 14-01-2024 |  | 1 | 12780 | 0 | 12780 | 0 | 0 | 0 | 0 | 12780
|  | Timesheet 15-01-2024 |  | 1 | 46960 | 0 | 46960 | 0 | 0 | 0 | 0 | 46960
|  | Timesheet 17-01-2024 |  | 1 | 10500 | 0 | 10500 | 0 | 0 | 0 | 0 | 10500
|  | Timesheet 18-01-2024 |  | 1 | 24130 | 0 | 24130 | 0 | 0 | 0 | 0 | 24130
|  | Timesheet 19-01-2024 |  | 1 | 15180 | 0 | 15180 | 0 | 0 | 0 | 0 | 15180
1123 | New 1 | Additional job after onboard inspection
|  | Delivery and installation of new fiberglass lining inside Spa |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | incl. Filter and gelcoat | QUOTED | 1 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 150000
1124 |  | Additional paint work:
|  | Painting deck 7 forward |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Removal of old lose paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning of spot basis 5% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wash down with FW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu - 3 coats, with roller and brush, min 0,25 m2 per spot. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc – 1 coat with roller and brush. | CANCELLED | 0 | 43315 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting deck 10 PS + STB deck plates |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning of spot basis 60% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wash down with FW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tu - 3 coat, with roller and brush, min 0,25 m2 per spot. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fc – 1 coat with roller and brush | QUOTED | 1 | 95500 | 95500 | 0 | 0 | 0 | 0 | 0 | 95500
1129 | ADD 3 | Overhaul of 5 pcs electric motors for winches
|  | De- og genmontering af elmotorer, standart overhaling af |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | motorer incl. levering af lejer. Per stk / 5 stk | QUOTED | 1 | 55270 | 0 | 55270 | 0 | 0 | 0 | 0 | 55270
|  | Additonal shore / on board incl new bearings |  | 1 | 18700 | 0 | 0 | 37400 | 0 | -18700 | 0 | 18700
1130 | 1123.01A | Pool area - additional work in swimming pool drain box
|  | Additional work in swimming pool drain box: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Existing tiles on top of swimming pool drain box to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | removed, approx. 17 m2, benches and handrail in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | connection with drain box to be dis- and remounted for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | existing man holes in top of drain box to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | opened and closed with new gasket, steel top of drain box |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to be mechanical cleaned and thicknes |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | measured,after possible repair, drain box top to be treaded |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | with epoxy layer in and agreed color | QUOTED | 1 | 203850 | 203850 | 0 | 0 | 0 | 0 | 0 | 203850
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible repair of drain box top plate to be priced after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and agreement of work scope |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional painting of pool area (Bathing area) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional painting of pool area (Bathing area) according |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to inspection | VOR 7 | 1 | 29900 | 29900 | 0 | 0 | 0 | 0 | 0 | 29900
|  | Incl. Cleaning, covering, mechanical cleaning, 2xTU, 1xFC. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Delivery of paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional painting of pool |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional full coat in pool according to inspection | VOR 25 | 1 | 14985 | 0 | 14985 | 0 | 0 | 0 | 0 | 14985
|  | Excl. Delivery of paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1133 | 1401.03 | Life boats lift off
|  | Life boats taken ashore and back, each | QUOTED | 7 | 10000 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transported to inside workshop for painting, each | QUOTED | 7 | 8000 | 56000 | 0 | 0 | 0 | 0 | 0 | 56000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FRB taken ashore and back to vessel | QUOTED | 1 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional cost do to rearrange space etc |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl transport of trailer |  | 1 | 113800 | 0 | 0 | 0 | 113800 | 0 | 0 | 113800
1134 |  | Welding of 2 pcs. reducers on ship side for grey water.
|  | Welding of 2 pcs. reducers on ship side for grey water. | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
1136 |  | Cleaning of HFO tk. no. 5
|  | Mud truck | QUOTED | 1 | 1150 | 0 | 1150 | 0 | 0 | 0 | 0 | 1150
|  | Man power |  | 1 | 1600 | 0 | 1600 | 0 | 0 | 0 | 0 | 1600
|  | Disposal |  | 1 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200
1137 |  | Cleaning of DO tk. no. 5
|  | Mud truck |  | 10 | 1150 | 0 | 11500 | 0 | 0 | 0 | 0 | 11500
|  | Man power |  | 1 | 21400 | 0 | 21400 | 0 | 0 | 0 | 0 | 21400
|  | Disposal |  | 3 | 1200 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600
|  | Materials |  | 1 | 2730 | 0 | 2730 | 0 | 0 | 0 | 0 | 2730
1138 |  | Repair of damaged steel PS FWD
|  | Reparation af stålskade PS FWD efter inspektion |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Affugning af styretap + genmontering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Udskæring af krop, knæ, web mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fremstilling og montering af ny web. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Svejsning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Opretning af styr for rampe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Svejse af styr |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Materialer |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Drejning af ny dorn |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stillads | VOR 1 | 1 | 127500 | 127500 | 0 | 0 | 0 | 0 | 0 | 127500
|  | Excl. Maling |  | 1 | 23790 | 0 | 23790 | 0 | 0 | 0 | 0 | 23790
1139 |  | 2 pcs. steps on stairs between deck 9 and 11 to be repaired.
|  | 2 pcs. steps on stairs between deck 9 and 11 to be repaired. |  | 1 | 12800 | 12800 | 0 | 0 | 0 | 0 | 0 | 12800
1140 |  | Delivery and installation of black cover plate for bridge
|  | panel incl. openings for instruments. |  | 1 | 7100 | 7100 | 0 | 0 | 0 | 0 | 0 | 7100
|  | Additional mounting for screening as agreed with captain |  | 1 | 13400 | 0 | 0 | 13400 | 0 | 0 | 0 | 13400
1141 |  | Renewal of scupper pipe
|  | Renewal of 1 pcs. scupper pipe according to inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. De- remount, fabrication and galvanization |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price: | VOR 4 | 1 | 24200 | 24200 | 0 | 0 | 0 | 0 | 0 | 24200
1142 |  | Change of ball valve for trim system
|  | Replecement of ball valve for trim system | VOR 10 | 1 | 3770 | 3770 | 0 | 0 | 0 | 0 | 0 | 3770
|  | New valve delivered by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of new DN40 ball valve in stainless steel, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | incl transport |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication and installation installation of DN40 pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material: Cunifor |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Approximately length: 400mm | VOR 14 | 1 | 10940 | 10940 | 0 | 0 | 0 | 0 | 0 | 10940
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible NDT |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1143 |  | Renting of forklift
|  | Renting of forklift - 8/1 - 11/1 |  | 7 | 3500 | 14000 | 0 | 10500 | 0 | 0 | 0 | 24500
1144 | VOR 2 | Repair of firedamper AFT mooring deck PS
|  | Repair of firedamper AFT mooring deck PS according to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Demount of fire damper | VOR 2 | 1 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 3900
|  | Repair of old fire damper after blasting, estimated price: | VOR 2 | 1 | 17550 | 17550 | 0 | 0 | 0 | 0 | 0 | 17550
|  | Delivery and installation of new rubber sealing | VOR 2 | 1 | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 7800
|  | Materials | VOR 2 | 1 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 6500
|  | Remount of new grid | VOR 2 | 1 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500
|  | Fabrication and delivery of new grid app. 1100x600mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material: 5mm AISI316. | VOR 2 | 1 | 17420 | 17420 | 0 | 0 | 0 | 0 | 0 | 17420
|  | Firedamper cover: Sandblasting, cleaning, 1 strip coat, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3x FC, incl. Transport | VOR 2 | 1 | 9710 | 9710 | 0 | 0 | 0 | 0 | 0 | 9710
|  | Housing around grid: Mechanical cleaning, cleaning, 3x TU | VOR 2 | 1 | 4680 | 4680 | 0 | 0 | 0 | 0 | 0 | 4680
|  | Excl. Delivery of paint. Vessel to deliver paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1145 |  | Scaffolding in funnel forward as requested by C.E.
|  | Scaffolding in funnel forward as requested by C.E. |  | 1 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 11000
1146 |  | 220V shore power to be arranged in FRB and MOB-boat
|  | 220V shore power to be arranged in FRB and MOB-boat |  | 1 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500
|  | 08.01.24. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1147 |  | Rigging of hoovers etc. to deck no. 8 on 09.01.24.
|  | Rigging of hoovers etc. to deck no. 8 on 09.01.24. |  | 1 | 24600 | 24600 | 0 | 0 | 0 | 0 | 0 | 24600
1148 |  | Delivery of bronze and steel shaft material as requested
|  | Delivery of bronze and steel shaft material as requested |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | by 1. Engineer. |  | 1 | 8300 | 0 | 8300 | 0 | 0 | 0 | 0 | 8300
1149 | VOR 3 | Fabrication of flange for gear, 4 pcs
|  | Fabrication of 4 pcs. flanges for gear. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price each: DKK17.000 (Price is based on minimum 4 pcs.) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price for 4 pcs: | VOR 3 | 1 | 68000 | 68000 | 0 | 0 | 0 | 0 | 0 | 68000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication of less than 4 pcs. Flanges for gear | VOR 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price each: DKK21.000 | CANCELLED | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1150 |  | Cleaning sealing surface for cover above FWD bow thruster
|  | Cleaning sealing surface for cover above FWD bow thruster | CREW | 0 |  | 0 | 0 | 6730 | 0 | -6730 | 0 | 0
1151 | VOR 5 | Painting of deck 10, railing, pipe, bulkhead, stairs PS + SB
|  | Painting of deck 10, railing, pipe, bulkhead, stairs PS + |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SB according to inspection. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl.: covering, mech. Cleaning, washing, 3xTU, 1xFC | VOR 5 | 1 | 192400 | 192400 | 0 | 0 | 0 | 0 | 0 | 192400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scaffolding, total for PS and SB: | VOR 5 | 1 | 34840 | 34840 | 0 | 0 | 0 | 0 | 0 | 34840
1154 |  | Assistance to Glass service.
|  | Cherry picker - From 9/1 - | QUOTED | 1 | 62310 | 21000 | 14000 | 27310 | 0 | 0 | 0 | 62310
|  | 42 meter cherry picker from 22/1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1155 |  | Mechanical cleaning and painting of spots on life boat
|  | Timesheets: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timesheet 11-01-2024 |  | 1 | 5610 | 5610 | 0 | 0 | 0 | 0 | 0 | 5610
|  | Timesheet 13-01-2024 |  | 1 | 35305 | 0 | 35305 | 0 | 0 | 0 | 0 | 35305
|  | Timesheet 14-01-2024 |  | 1 | 44500 | 0 | 44500 | 0 | 0 | 0 | 0 | 44500
|  | Timesheet 15-01-2024 |  | 1 | 14805 | 0 | 14805 | 0 | 0 | 0 | 0 | 14805
|  | Timesheet 16-01-2024 |  | 1 | 9110 | 0 | 9110 | 0 | 0 | 0 | 0 | 9110
1156 | VOR 12 | Lifeboat davit winch
|  | Demount and disassembling of 1 pcs. Lifeboat davit winch |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disassembling and inspection with superintendent in workshop |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Crane and forklift | VOR 12 | 1 | 23020 | 23020 | 0 | 0 | 0 | 0 | 0 | 23020
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Viking to demount wire and foundation bolts. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Repairs, materials and installation. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Repairs of lifeboat davit winch |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Repairs of lifeboat davit winch after agreement with superintendent. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disassemble for change of bearings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Replacement of 4 pcs. Bearings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication & replacement of 2 pcs. Bushings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery of new sealings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning inside of tank. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assemble and lift to position on vessel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Materials |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Crane and forklift | VOR 17 | 1 | 112680 | 0 | 112680 | 0 | 0 | 0 | 0 | 112680
|  | Excl.: New Gear-oil, repair paint, mounting with bolts on-board. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Repair of gear-axle for davit winch |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Repair of gear-axle for winch according to inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding up axle to oversize and machine down to right diameter, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to make clean surface for new bearing. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Transport and materials |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price: | VOR 18 | 1 | 17780 | 0 | 17780 | 0 | 0 | 0 | 0 | 17780
1157 | VOR 8 | Painting around holes for FWD mooring winches
|  | Painting of around holes for FWD mooring winches according |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price for 4 holes: | VOR 8 | 1 | 15860 | 15860 | 0 | 0 | 0 | 0 | 0 | 15860
|  | Incl. Mechanical cleaning, cleaning, 2xTU, 1xFC, lift. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1159 | VOR 23 | Renewal of cover plates for insulation
|  | round exhaust pipes in funnel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Renewal of cover plates for insulation in top of funnel according |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to inspection | VOR 23 | 1 | 10800 | 0 | 10800 | 0 | 0 | 0 | 0 | 10800
|  | Excl. Change of insulation. Based on the insulation is in good condition. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional repair of cover plates |  | 1 | 12870 | 0 | 0 | 12870 | 0 | 0 | 0 | 12870
1160 |  | Assistance to repair of ships forklift
|  | Assistance to repair of ships forklift |  | 1 | 4900 | 4900 | 0 | 0 | 0 | 0 | 0 | 4900
1161 | VOR 15 | Fiber glass repair on lifeboats and MOB
|  | Lifeboat no. 14: Repair of 15 spots | VOR 15 | 1 | 21450 | 0 | 21450 | 0 | 0 | 0 | 0 | 21450
|  | Lifeboat no. 15: Repair of 17 spots | VOR 15 | 1 | 27300 | 0 | 27300 | 0 | 0 | 0 | 0 | 27300
|  | Lifeboat no. 16: Rapair of 11 spots | VOR 15 | 1 | 21450 | 0 | 21450 | 0 | 0 | 0 | 0 | 21450
|  | Lifeboat no. 17: Rapir of 11 spots | VOR 15 | 1 | 21450 | 0 | 21450 | 0 | 0 | 0 | 0 | 21450
|  | Lifeboat no. 18: Repair of 11 spots | VOR 15 | 1 | 21450 | 0 | 21450 | 0 | 0 | 0 | 0 | 21450
|  | Lifeboat no. 19: Repair of 19 spots | VOR 15 | 1 | 21450 | 0 | 21450 | 0 | 0 | 0 | 0 | 21450
|  | MOB: Repair of 5 spots + Replacement of support list above and below |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | fender (Stainless steel) | VOR 15 | 1 | 37700 | 0 | 37700 | 0 | 0 | 0 | 0 | 37700
|  | Topcoat to be delivered by vessel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Closing of drilled holes in bottom |  | 1 | 16200 | 0 | 0 | 16200 | 0 | 0 | 0 | 16200
1162 | VOR 16 | Painting top of funnel inside
|  | Painting top of funnel inside + |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | some spots inside according to inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Mechanical cleaning, cleaning, 2xTU and 1xFC | VOR 16 | 1 | 48620 | 0 | 48620 | 0 | 0 | 0 | 0 | 48620
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Staging i top of funnel |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. crane | VOR 16 | 1 | 23300 | 0 | 23300 | 0 | 0 | 0 | 0 | 23300
1163 | VOR 13 | Loadtest of lifeboat davits
|  | Loadtest of double leg lifeboat davit |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Loadtest will be performed with fixed weight 19,5T |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Certificate & documentation (To be delivered by Viking) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price each: DKK21.190 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price for 7 pcs davits | VOR 13 | 7 | 21190 | 0 | 148330 | 0 | 0 | 0 | 0 | 148330
|  | Incl. Crane and forklift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1164 |  | Repair steel damage PS hoisting car deck
|  | Repair steel damage PS hoisting car deck |  | 1 | 13200 | 0 | 13200 | 0 | 0 | 0 | 0 | 13200
|  | Lift |  | 1 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500
|  | Painting |  | 1 | 3215 | 0 | 0 | 3215 | 0 | 0 | 0 | 3215
1165 | VOR 22 | Painting of new aluminium ventilation channel
|  | Painting of new aluminium ventilation channel (Funnel FWD SB) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | according to inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Making new plates rye |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3xFC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price: | VOR 22 | 1 | 57240 | 0 | 57240 | 0 | 0 | 0 | 0 | 57240
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Scaffolding (Based on it is possible to paint from |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | existing scaffolding) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1166 | VOR 19 | Anchor winch axel
|  | Repair of 1 pcs anchor winch axel according to inspection to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | done in T&M. Machining wleding of shaft |  | 1 | 42130 | 0 | 42130 | 0 | 0 | 0 | 0 | 42130
|  | Transport to and from workshop incl. Mobilecrane | VOR 19 | 1 | 28680 | 0 | 28680 | 0 | 0 | 0 | 0 | 28680
|  | Welding up 2 pcs. Padeyes, each: DKK8.000 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price for 2 pcs. | VOR 19 | 1 | 16000 | 0 | 16000 | 0 | 0 | 0 | 0 | 16000
|  | Excl. Possible NDT, loadtest and removal of padeyes. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1167 |  | Welding of pittings in bilge tank.
|  | Welding of pittings in bilge tank. |  | 1 | 27300 | 0 | 27300 | 0 | 0 | 0 | 0 | 27300
|  | Coating with filler after repair |  | 1 | 5130 | 0 | 5130 | 0 | 0 | 0 | 0 | 5130
|  | Cleaning + filler |  | 1 | 3645 | 0 | 0 | 3645 | 0 | 0 | 0 | 3645
1168 |  | New drain pod in hydrophore room.
|  | New drain pod in hydrophore room. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint work only |  | 1 | 1850 | 0 | 0 | 1850 | 0 | 0 | 0 | 1850
1169 | VOR 20 | Static test of fast rescue boat
|  | Static test of Fast Rescue Boat, 1 pcs |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performed with fixed weight 925Kg |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl.: Certificate & Documentation (Viking to make certificate) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price incl. Crane and forklift: | VOR 20 | 1 | 16515 | 0 | 16515 | 0 | 0 | 0 | 0 | 16515
1170 | VOR 21 | Test weight of all boats.
|  | Test weight of all boats. 7 Lifeboats & 1 FRB |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Performed with calibrated load-cell. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl.: Documentation. (Viking to make certificate) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price incl. Crane and forklift: | VOR 21 | 1 | 35520 | 0 | 35520 | 0 | 0 | 0 | 0 | 35520
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional load tests |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test weight of all boats. 7 Lifeboats & 1 FRB | QUOTED | 1 | 35520 | 0 | 35520 | 0 | 0 | 0 | 0 | 35520
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Load test of MOB Boat |  | 1 | 15390 | 0 | 0 | 0 | 15390 | 0 | 0 | 15390
1171 |  | Grid blasting and painting of loose mountings for life boats.
|  | Grid blasting and painting of loose mountings for life boats. |  | 1 | 27900 | 0 | 0 | 27900 | 0 | 0 | 0 | 27900
1172 |  | Removal of old, and delivery of new stickers with name
|  | Chemichal cleaning |  | 1 | 73575 | 0 | 0 | 0 | 73575 | 0 | 0 | 73575
|  | Mechanichal cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ruggøre hele båden med sand papir |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Levering af nyt navn & reflex |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Montering af nyt navn og reflex |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1173 |  | Delivery of spare bearings for davit winch
|  | Delivery of spare bearings for davit winch |  | 1 | 9730 | 0 | 0 | 9730 | 0 | 0 | 0 | 9730
1174 |  | Change of 2 pcs. ventilation grids ship side PS FWD and
|  | FWD mooring deck |  | 1 | 58411 | 0 | 0 | 58411 | 0 | 0 | 0 | 58411
1175 |  | Welding and repair of stb. propeller
|  | Welding and repair of stb. propeller |  | 1 | 8300 | 0 | 8300 | 0 | 0 | 0 | 0 | 8300
1177 | VOR 24 | Painting of lifeboat davit on deck 10
|  | Painting of lifeboat davit on deck 10 according to inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP wash 500 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scraping to remove white top coat |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Make rye the grey primer |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3xFC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price for 1 pcs: | VOR 24 | 1 | 78030 | 0 | 78030 | 0 | 0 | 0 | 0 | 78030
|  | Excl. Scaffolding (Based on the job can be done from |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | existing scaffolding) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1178 |  | Repair of heating pipe in bilge tank
|  | Repair of heating pipe in bilge tank |  | 1 | 17680 | 0 | 0 | 17680 | 0 | 0 | 0 | 17680
1179 |  | Renewal of lower part of forward bulkhead in FV-tanks,
|  | Stb hydr. room. 300mm in full length. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure test of FV-tanks after completion. | CANCELLED | 0 | 132731 | 0 | 0 | 132731 | 0 | -132731 | 0 | 0
|  | Dye test only |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1180 |  | Painting of new and touched steel in FV-tanks after steel
|  | renewal. |  | 1 | 25800 | 0 | 0 | 25800 | 0 | 0 | 0 | 25800
1187 |  | Polishing of FRB.
|  | Polishing of FRB. |  | 1 | 18500 | 0 | 0 | 18500 | 0 | 0 | 0 | 18500
1188 |  | Cleaning / painting of arears below windows in white
|  | topside incl. window frames as needed. |  | 1 | 49800 | 0 | 0 | 49800 | 0 | 0 | 0 | 49800
1189 |  | Repair of bended angle bar after load test of davit Stb.
|  | Repair of bended angle bar after load test of davit Stb. |  | 1 | 3300 | 0 | 0 | 3300 | 0 | 0 | 0 | 3300
1194 |  | Thickness measurements on scrubber overboard pipe
|  | incl. report. |  | 1 | 8300 | 0 | 0 | 8300 | 0 | 0 | 0 | 8300
1195 |  | FW-hose in arear of life-boats, for crew to wash/hose
|  | down boats |  | 1 | 2210 | 0 | 0 | 2210 | 0 | 0 | 0 | 2210
1196 |  | Renewal of zinc anodes on rope-guards.
|  | Renewal of zinc anodes on rope-guards. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 66(6,6 kg) | JOB 1039 | 0 |  | 0 | 0 | 7020 | -7020 | 0 | 0 | 0
1197 |  | Ass. to HF-interior for shipping of materials etc.
|  | Ass. to HF-interior for shipping of materials etc. | VIA AGENT | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1198 |  | Delivery of hydr. hoses for emg. generator.
|  | Delivery of hydraulic hoses |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Max. Ø1/2" and/or length 1.500 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chromatized fittings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meassuring of hoses to be performed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hose list will be delivered |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price for 12 hoses | VOR 27 | 1 | 34695 | 0 | 0 | 34695 | 0 | 0 | 0 | 34695
|  | Assuming that fittings are std. European norm. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Installation of hose, pressure test & M.E.D certificate |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1199 |  | Dye-test of propeller blades, tips and root.
|  | Dye-test of propeller blades, tips and root. |  | 8 | 2000 | 0 | 0 | 16000 | 0 | 0 | 0 | 16000
1200 |  | Fresh water analysis
|  | Fresh water analysis |  | 1 | 4605 | 0 | 0 | 0 | 4605 | 0 | 0 | 4605
1201 |  | Rent of high-torgue tools for engine repair.
|  | Rent of high-torgue tools for engine repair. |  | 1 | 33750 | 0 | 0 | 33750 | 0 | 0 | 0 | 33750
1202 |  | Additional mechanical cleaning below AHU deck 10.
|  | Additional mechanical cleaning below AHU deck 10. |  | 1 | 18313 | 0 | 0 | 18313 | 0 | 0 | 0 | 18313
1203 |  | Plot of drawings as per Captains request.
|  | Plot of drawings as per Captains request. |  | 1 | 6500 | 0 | 0 | 6500 | 0 | 0 | 0 | 6500
1208 |  | Repair of studs for manhole cover inside duck-tail.
|  | Repair of studs for manhole cover inside duck-tail. | CANCELLED | 0 |  | 0 | 0 | 7400 | -7400 | 0 | 0 | 0
1209 |  | Car to be liftet on board 30.01.24
|  | Car to be liftet on board 30.01.24 | ++ | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9993 |  | Discount according to agreement
|  | Discount according to agreement | 12% | 1 | -3386709.2744 | -2812624 | -334764 | -222402 | -93988 | 70644 | 6424 | -3386709
|  |  | DKK |  |  | 4009766 | 1872044 | 611328 | 296287 | -301757 | -47106 | 6440563 | 0

## Chapter 1
Ship name: |  | CROWN SEAWAYS
Case No.: |  | 231174
Currency: | DKK | Chapter 1 |  |  |  | Estimate | New/changes | New/changes | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2024-01-12 | 2024-01-22 | 2024-01-30 | 2024-02-22 | 2024-02-23 | 2025-05-06 | Total
1009 | 500.16 | Garbage disposal
|  | Garbage containers (4 m3) : |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Garbage container placed on the quay. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each time emptied, incl. disposal: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | According to specification as per 31-01-2024 |  | 1 | 1261180 | 416900 | 476940 | 296330 | 71010 | 0 | 0 | 1261180
1054 | 1018.05 | Remove windows deck 8 for acces equipment to galley
|  | 3 pcs windows deck 8 around frame 112 incl. 2 frame |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to be dismantled and reassembled | QUOTED | 1 | 130800 | 130800 | 0 | 0 | 0 | 0 | 0 | 130800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional access, repair of broken bolts |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and cleaning and painting of window frames to be agreed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Windows cleaned + painted |  | 1 | 3025 | 0 | 0 | 3025 | 0 | 0 | 0 | 3025
1135 |  | Power supply for galley deck 7
|  | (Power supply 400V + N 32A sockets and 220V sockets) | QUOTED | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
|  | Consumption | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
|  | Delivery of Argon + materials for Lori parts | QUOTED | 1 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
|  |  | DKK |  |  | 562700 | 506940 | 299355 | 71010 | 0 | 0 | 1440005 | 0