## Chapter 0
Ship name: |  | ARK DANIA
Case No.: |  | 231218
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2024-06-14 | 2024-06-20 | 2024-06-24 | 2024-06-26 | 2024-06-27 | 2025-05-06 | Total
1000 |  | Sag
1001 | 200.01 | Drydocking
|  | DrydockingDock / undock and first day in drydock | QUOTED | 1 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 45000
|  | Cost for subsequent days, each | QUOTED | 16 | 25000 | 450000 | -25000 | -25000 | 0 | 0 | 0 | 400000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Habour dues ( if any) to local autorities for entering / leaving the port | CANCELLED | 0 | 32980.2 | 32980 | -32980 | 0 | 0 | 0 | 0 | 0
1002 |  | Shore power connection
|  | Each connection | CANCELLED | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply: Each kWh | CANCELLED | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Maintenance of shorepower connection, each day | CANCELLED | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1003 |  | Earth connection
|  | Earth connection | INCL | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1004 |  | Crane & Fork lift service
|  | Crane service, each hour - per 26/6-24 | QUOTED | 1 | 16450 | 35000 | 0 | -18550 | 0 | 0 | 0 | 16450
|  | Forklift service, each hour - per 26/6-24 | QUOTED | 1 | 58900 | 65000 | 0 | -10500 | 4400 | 0 | 0 | 58900
|  | Assistance - per 26/6-24 | QUOTED | 1 | 17850 | 20000 | 0 | -3850 | 1700 | 0 | 0 | 17850
|  | Car sling Scan Unit | QUOTED | 2 | 3000 | 0 | 0 | 3000 | 0 | 3000 | 0 | 6000
|  | Rest estimated | QUOTED | 1 | 10000 | 0 | 0 | 20000 | -10000 | 0 | 0 | 10000
1005 |  | Fire Line Connection
|  | Fire water connection / disconnection, each | QUOTED | 4 | 2000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 8000
|  | Fire water supply, each day | QUOTED | 17 | 350 | 6300 | -350 | 0 | 0 | 0 | 0 | 5950
1006 |  | Blocking of CO2
|  | Blocking of CO2 | CREW | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 44461.9 | 50000 | 0 | 0 | -5538 | 0 | 0 | 44462
|  | Meson, Butterfly ventil DN200 + DN250 | NET PRICE | 1 | 11551.1 | 11551 | 0 | 0 | 0 | 0 | 0 | 11551
|  | Transport of Flap valve DN 350 |  | 1 | 2850 | 0 | 0 | 0 | 2850 | 0 | 0 | 2850
1008 |  | Isolation
|  | Isolation | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1009 |  | Garbage
|  | Garbage disposal, each time emptied | QUOTED | 10 | 5000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
|  | Based 4m3 container incl disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Oil drums | QUOTED | 170 | 550 | 93500 | 0 | 0 | 0 | 0 | 0 | 93500
|  | Disposal BWT | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
|  | Oil rack | QUOTED | 2 | 7500 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
|  | Additional garbage steel | QUOTED | 3 | 250 | 250 | 0 | 0 | 0 | 500 | 0 | 750
|  | Disposal of grease | QUOTED | 1 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 12500
|  | Disposal of paint | QUOTED | 1 | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500
|  | Disposal of foam | QUOTED | 1 | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500
1010 |  | Cleaning of dock before departure
|  | Cleaning of dock before departure | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1011 |  | Gangway
|  | Each gangway | QUOTED | 2 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 8000
|  | Aft ramp |  | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
|  | Move ramp |  | 6 | 10000 | 40000 | 0 | 0 | 20000 | 0 | 0 | 60000
1012 |  | Cooling water connection
|  | Each | QUOTED | 2 | 2000 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
|  | Cooling water supply, each day, pump dock gate | QUOTED | 17 | 350 | 12600 | -700 | 0 | 0 | 0 | -5950 | 5950
1013 |  | Fresh water connection
|  | Each connection | QUOTED | 1 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000
|  | Supply, each m3 | QUOTED | 108 | 40 | 4000 | 0 | 0 | 320 | 0 | 0 | 4320
1014 |  | Sewage/Black water connection
|  | Each | QUOTED | 1 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000
|  | Mudtruck, each hour - per 20/6-24 | QUOTED | 19 | 1150 | 0 | 21850 | 0 | 0 | 0 | 0 | 21850
|  | Disposal, each m3 - per 20/6-24 | QUOTED | 25 | 95 | 0 | 2375 | 0 | 0 | 0 | 0 | 2375
|  | Sewage/Black water connection, each - 21/6-24 | QUOTED | 1 | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000
|  | Mudtruck, each hour - per 21/6-24 | QUOTED | 6 | 1150 | 0 | 0 | 6900 | 0 | 0 | 0 | 6900
|  | Disposal, each m3 - per 21/6-24 | CANCELLED | 0 | 95 | 0 | 0 | 1330 | 0 | 0 | -1330 | 0
|  | Disposal, each m3 - per 25/6 | QUOTED | 14 | 95 | 0 | 0 | 0 | 1330 | 0 | 0 | 1330
|  | Mudtruck, each hour - per 25/6 | QUOTED | 8 | 1150 | 0 | 0 | 0 | 9200 | 0 | 0 | 9200
1015 |  | Oily water connection
|  | Oily water hose connection / disconnection, each | QUOTED | 4 | 2000 | 8000 | 0 | 0 | 0 | 0 | 0 | 8000
|  | Mudtruck, each hour - 13/6-24 | QUOTED | 7 | 1150 | 23000 | 0 | -14950 | 0 | 0 | 0 | 8050
|  | Disposal, each m3 - 13/6-24 | QUOTED | 14 | 1200 | 48000 | 0 | -32160 | 960 | 0 | 0 | 16800
1016 |  | Internet Connection
|  | Internet Connection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1017 |  | Ballast water connection
|  | Ballast water connection, each | QUOTED | 1 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000
|  | Supply, each m3 | QUOTED | 1800 | 8 | 29600 | 0 | 0 | -15200 | 0 | 0 | 14400
1018 |  | Gas free certifikate
|  | First initial gas free certificate | CANCELLED | 0 | 3000 | 3000 | 0 | -3000 | 0 | 0 | 0 | 0
|  | If needed further gas free certificates are also, each | CANCELLED | 0 | 3000 | 9000 | 0 | -9000 | 0 | 0 | 0 | 0
1019 | 200.02 | Crankshaft deflection
|  | Main engine crankshaft deflections, each time per engine | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1020 | 300.01 | Paint Specification
|  | Paint Specification | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1021 | 1001.01 | Sea chest cleaning
|  | Sea chests cleaned and painted, minimum 1 m3/seachest: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As spec.: Sea chests opened, cleaned and painted, minimum 1 m³/seachest: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lower seachest, 17 m3, each m3 | QUOTED | 17 | 1529 | 25993 | 0 | 0 | 0 | 0 | 0 | 25993
|  | High seacheat, 14 m3, each m3 | QUOTED | 14 | 1529 | 21406 | 0 | 0 | 0 | 0 | 0 | 21406
|  | Fire fighting, 20 m3, each m3 | QUOTED | 20 | 1529 | 30580 | 0 | 0 | 0 | 0 | 0 | 30580
|  | Lower scrubber, 18 m3, each m3 | QUOTED | 18 | 1529 | 27522 | 0 | 0 | 0 | 0 | 0 | 27522
|  | Open/close welded type, each |  | 4 | 2000 | 8000 | 0 | 0 | 0 | 0 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on max 1 m³ disposal per sea chest | QUOTED | 3 | 7500 | 60000 | 0 | -37500 | 0 | 0 | 0 | 22500
|  | Additional cleaning |  | 1 | 10000 | 30000 | 0 | -20000 | 0 | 0 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 x stripe coats |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning and painting of seachest grits |  | 1 | 28990 | 0 | 28990 | 0 | 0 | 0 | 0 | 28990
1022 | 1001.02 | Sea chest painting
|  | Sea chest painting | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1023 | 1001.03 | Corrosion prevention anodes
|  | Change of owners supplied alu. anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 60 (6,0 kg), each | QUOTED | 28 | 645 | 0 | 18060 | 0 | 0 | 0 | 0 | 18060
|  | AL 80 (8,0 kg), each | QUOTED | 38 | 700 | 0 | 26600 | 0 | 0 | 0 | 0 | 26600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry picker for anode renewal, each per day | QUOTED | 2 | 3500 | 0 | 14000 | -8750 | 0 | 0 | 0 | 5250
1024 | 1001.04 | ICCP system
|  | Renewal of owners supplied ICCP zinc anodes, each | CANCELLED | 0 | 9630 | 38520 | -38520 | 0 | 0 | 0 | 0 | 0
|  | Renewal of owners supplied ICCP main anodes, each | CANCELLED | 0 | 17070 | 34140 | -34140 | 0 | 0 | 0 | 0 | 0
|  | Possible further yard assistance: |  | 2 | 8500 | 0 | 17000 | 0 | 0 | 0 | 0 | 17000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry picker assistance (excl. Driver), each per day | QUOTED | 4 | 3500 | 21000 | -7000 | 0 | 0 | 0 | 0 | 14000
1025 | 1001.05 | ICCP shields
|  | Full blasting and painting of ICCP area, 1 pcs. | CANCELLED | 0 | 32400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based paint/filler supplied by owners |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible spot repair: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning, light grinding and painting |  | 1 | 8420 | 0 | 8420 | 0 | 0 | 0 | 0 | 8420
1026 | 1001.06 | Cistern TK
|  | Cistern tank total 17,2 m3 located at frame 68 to 70.(Cross-over tank): |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Manhole covers removed and refitted with existing gaskets: | CREW | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on max size 600*800mm, each |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply of new yard standard rubber gaskets, each | CREW | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Suction of tank bottom incl. removal and disposal of max 2m3 of pumpable mud | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | Based on empty tank |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional suction, each hour | QUOTED | 18 | 1150 | 23000 | 3450 | -5750 | 0 | 0 | 0 | 20700
|  | Possible additional disposal, each ton | QUOTED | 7 | 3500 | 55000 | -16500 | -14000 | 0 | 0 | 0 | 24500
|  | Additional cleaning |  | 1 | 24300 | 0 | 24300 | 0 | 0 | 0 | 0 | 24300
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | If corroded area is found areas to be treated according PSPC. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | To be priced after cleaning and inspection of tank |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1027 | 1016.01 | Bottom treatment and paint
|  | In general: Cleaning of Boss pipes and cleaning under/ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | between docking blocks and on bilgekeel/stabil |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of dock before and after hull treatment due to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | environmental concerns | QUOTED | 1 | 100000 | 150000 | -50000 | 0 | 0 | 0 | 0 | 100000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Full blasting to WJ2 and new silicone applied: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flat bottom aft 4106 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing 500 bar, each m2 | QUOTED | 4106 | 22 | 90332 | 0 | 0 | 0 | 0 | 0 | 90332
|  | WJ2, 100 %, each m2 | QUOTED | 4106 | 175 | 776034 | -57484 | 0 | 0 | 0 | 0 | 718550
|  | HP-washing 500 bar for new rust, each m2 | QUOTED | 4106 | 22 | 90332 | 0 | 0 | 0 | 0 | 0 | 90332
|  | Hosing down with lowpressure FW, each m2 |  | 4106 | 3.75 | 15398 | 0 | 0 | 0 | 0 | 0 | 15398
|  | 1 x FC Easy, each m2 | QUOTED | 4106 | 7 | 28742 | 0 | 0 | 0 | 0 | 0 | 28742
|  | 1 x FC Easy, each m2 | QUOTED | 4106 | 7 | 28742 | 0 | 0 | 0 | 0 | 0 | 28742
|  | 1 x FC Nexus (silicone), each m2 | QUOTED | 4106 | 14 | 57484 | 0 | 0 | 0 | 0 | 0 | 57484
|  | 1 x FC X7 (silicone), each m2 | QUOTED | 4106 | 14 | 57484 | 0 | 0 | 0 | 0 | 0 | 57484
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom 2900 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Alternative: HP-washing 500 bar, each m2 |  | 2900 | 24 | 69600 | 0 | 0 | 0 | 0 | 0 | 69600
|  | WJ2, 100 %, each m2 | QUOTED | 2900 | 175 | 548100 | -40600 | 0 | 0 | 0 | 0 | 507500
|  | HP-washing 500 bar for new rust, each m2 | QUOTED | 2900 | 24 | 69600 | 0 | 0 | 0 | 0 | 0 | 69600
|  | Hosing down with lowpressure FW, each m2 |  | 2900 | 4 | 11600 | 0 | 0 | 0 | 0 | 0 | 11600
|  | 1 x FC Easy, each m2 | QUOTED | 2900 | 10.5 | 30450 | 0 | 0 | 0 | 0 | 0 | 30450
|  | 1 x FC Easy, each m2 | QUOTED | 2900 | 10.5 | 30450 | 0 | 0 | 0 | 0 | 0 | 30450
|  | 1 x FC Nexus (silicone), each m2 | QUOTED | 2900 | 21 | 60900 | 0 | 0 | 0 | 0 | 0 | 60900
|  | 1 x FC X7 (silicone), each m2 | QUOTED | 2900 | 21 | 60900 | 0 | 0 | 0 | 0 | 0 | 60900
|  | Cleaning of slinger keel with WJ gun |  | 1 | 33800 | 33800 | 0 | 0 | 0 | 0 | 0 | 33800
|  | Bottom marks |  | 1 | 20400 | 22100 | -1700 | 0 | 0 | 0 | 0 | 20400
|  | Covering of 2m for silicone painting |  | 1 | 16520 | 44200 | -27680 | 0 | 0 | 0 | 0 | 16520
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering etc.: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering of propellers, each | QUOTED | 2 | 638 | 1276 | 0 | 0 | 0 | 0 | 0 | 1276
|  | Marking of waterline | QUOTED | 1 | 4610 | 4610 | 0 | 0 | 0 | 0 | 0 | 4610
|  | Drain plugs in/out, each | QUOTED | 24 | 148.5 | 149 | 3416 | 0 | 0 | 0 | 0 | 3564
|  | Covering of anodes and sensors, each | QUOTED | 88 | 25 | 25 | 2175 | 0 | 0 | 0 | 0 | 2200
|  | Covering of ICCP, each | QUOTED | 4 | 1018 | 1018 | 3054 | 0 | 0 | 0 | 0 | 4072
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional regarding silicone treatment: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Destroyed paint hoses due to silicone paint | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
|  | Covering against topside to avoid overspray and side bottom | QUOTED | 1 | 30000 | 83600 | -53600 | 0 | 0 | 0 | 0 | 30000
|  | Paint repair after covering is removed | QUOTED | 1 | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 44000
|  | Bottommarks (with silicone tape) previously Hempel delivery | QUOTED | 1 | 20400 | 20400 | 0 | 0 | 0 | 0 | 0 | 20400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering bottom with staging and plastic for silicone: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based normal covering of bottom | CANCELLED | 0 | 1804000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible winter insulation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heating: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mobilization/demobilization | CANCELLED | 0 | 228000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heating, based on 10 pcs. 185 KW heat blowers in 7 days | CANCELLED | 0 | 237600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Supply of fuel for heaters |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The vessel to deliver DO fuel for heaters and do the DO tank filling. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Yard assistance to vessel with the DO tank filling | CANCELLED | 0 | 35000 | 35000 | -35000 | 0 | 0 | 0 | 0 | 0
1028 | 1016.02 | Bottom treatment and paint, area for traditional antifouling boot top
|  | Vertical bottom 182 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing 500 bar, each m2 |  | 182 | 24 | 4368 | 0 | 0 | 0 | 0 | 0 | 4368
|  | WJ2, 10 %, each m2 | QUOTED | 18 | 189 | 3402 | 0 | 0 | 0 | 0 | 0 | 3402
|  | Hosing down with lowpressure FW, each m2 | QUOTED | 182 | 4 | 728 | 0 | 0 | 0 | 0 | 0 | 728
|  | Mechanical cleaning, based 1%, each m2 | QUOTED | 2 | 113.5 | 227 | 0 | 0 | 0 | 0 | 0 | 227
|  | 1 x TU, based 15%, each m2 | QUOTED | 27 | 15.25 | 416 | 0 | 0 | 0 | 0 | 0 | 416
|  | 1 x TU, based 15%, each m2 | QUOTED | 27 | 15.25 | 416 | 0 | 0 | 0 | 0 | 0 | 416
|  | 1 x FC, each m2 | QUOTED | 182 | 10.5 | 1911 | 0 | 0 | 0 | 0 | 0 | 1911
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bottom cleaning (Hempel inspector) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning and scraping due to animals in paint |  | 1 | 24850 | 0 | 28600 | -3750 | 0 | 0 | 0 | 24850
1029 | 1016.03 | Marks on vessel
|  | Cargo, plimsoll, thruster and bulb markings | QUOTED | 1 | 6232 | 6232 | 0 | 0 | 0 | 0 | 0 | 6232
|  | Bottom marks | QUOTED | 1 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 8250
1030 | 1018.01 | White Topside cleaning and painting
|  | White topside, 2432 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning by high pressure fresh water (min. 300 bar), each m | QUOTED | 2300 | 11.5 | 35052 | 0 | -7084 | -1518 | 0 | 0 | 26450
|  | Mechanical cleaning, based 4%, each m2 | QUOTED | 97 | 113.5 | 13847 | 0 | -2806 | 0 | 0 | 0 | 11041
|  | Hosing down with FW, each m2 | QUOTED | 2300 | 4 | 12192 | 0 | -2992 | 0 | 0 | 0 | 9200
|  | 1 x TU, based 9%, each m2 | QUOTED | 274 | 23 | 6309 | 0 | 0 | 0 | 0 | 0 | 6309
|  | 1 x TU, based 9%, each m2 | QUOTED | 274 | 23 | 6309 | 0 | 0 | 0 | 0 | 0 | 6309
|  | 1 x TU, based 9%, each m2 |  | 274 | 23 | 0 | 6309 | 0 | 0 | 0 | 0 | 6309
|  | 1 x FC, applied with brush/roll, each m2 | QUOTED | 2300 | 31.5 | 48006 | 48006 | -23562 | 0 | 0 | 0 | 72450
|  | Painting of line | QUOTED | 1 | 4610 | 4610 | 0 | 0 | 0 | 0 | 0 | 4610
|  | Covering, cleaning and painting of windows, each | QUOTED | 63 | 840 | 840 | 52080 | 0 | 0 | 0 | 0 | 52920
|  | Cleaning and painting of big grates, 6 pcs |  | 6 | 3000 | 0 | 18000 | 0 | 0 | 0 | 0 | 18000
|  | Cleaning and painting of normal grates, 8 pcs |  | 8 | 2000 | 0 | 16000 | 0 | 0 | 0 | 0 | 16000
1031 | 1018.02 | Blue Topside cleaning and painting
|  | Blue topside, 3936 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning by high pressure fresh water (min. 300 bar), each m2 | QUOTED | 3936 | 11.5 | 45264 | 0 | 0 | 0 | 0 | 0 | 45264
|  | Mechanical cleaning, based 4%, each m2 | QUOTED | 157 | 113.5 | 17869 | 0 | 0 | 0 | 0 | 0 | 17869
|  | Hosing down with FW, each m2 | QUOTED | 3936 | 4 | 15744 | 0 | 0 | 0 | 0 | 0 | 15744
|  | 1 x TU, based 9%, each m2 | QUOTED | 354 | 23 | 8148 | 0 | 0 | 0 | 0 | 0 | 8148
|  | 1 x TU, based 9%, each m2 | QUOTED | 354 | 23 | 8148 | 0 | 0 | 0 | 0 | 0 | 8148
|  | 1 x FC, each m2 | QUOTED | 3936 | 15.75 | 61992 | 0 | 0 | 0 | 0 | 0 | 61992
|  | Painting of line | QUOTED | 1 | 4610 | 4610 | 0 | 0 | 0 | 0 | 0 | 4610
1032 | 1018.03 | Funnel cleaning and painting
|  | Cleaning by high pressure fresh water (min. 300 bar) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, based 5% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down with FW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU, based 5% (by roller/brush) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU, based 10% (by roller/brush) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC, (by roller/brush) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of line |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | QUOTED | 1 | 57600 | 57600 | 0 | 0 | 0 | 0 | 0 | 57600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Funnel top pipe construction |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning by high pressure fresh water (min. 300 bar) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, based 5% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down with FW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU, based 5% (by roller/brush) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU, based 10% (by roller/brush) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC, (by roller/brush) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of line |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift |  | 1 | 34170 | 0 | 34170 | 0 | 0 | 0 | 0 | 34170
1033 | 1018.04 | Stern ramp cleaning and painting
|  | Stern ramp, 1000 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning, each m2 | QUOTED | 588 | 27.5 | 16170 | 0 | 0 | 0 | 0 | 0 | 16170
|  | Cleaning by high pressure fresh water (min. 300 bar), each m2 | QUOTED | 1000 | 11.5 | 11500 | 0 | 0 | 0 | 0 | 0 | 11500
|  | Mechanical cleaning, based 17%, each m2 | QUOTED | 170 | 113.5 | 19295 | 0 | 0 | 0 | 0 | 0 | 19295
|  | Hosing down with FW, each m2 | QUOTED | 1000 | 4 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000
|  | 1 x TU, based 22% (by roller/brush), each m2 | QUOTED | 220 | 46 | 10120 | 0 | 0 | 0 | 0 | 0 | 10120
|  | 1 x TU, based 22% (by roller/brush), each m2 | QUOTED | 220 | 46 | 10120 | 0 | 0 | 0 | 0 | 0 | 10120
|  | 1 x FC, (by roller/brush), each m2 | QUOTED | 1000 | 30.5 | 31500 | -1000 | 0 | 0 | 0 | 0 | 30500
|  | Lift | QUOTED | 1 | 5500 | 11000 | -5500 | 0 | 0 | 0 | 0 | 5500
1034 | 1018.05 | Ship name, logo and funnel mark
|  | Painting of existing name and homeport | QUOTED | 1 | 6787 | 6787 | 0 | 0 | 0 | 0 | 0 | 6787
|  | Painting of existing logo "DFDS" | QUOTED | 1 | 19200 | 19200 | 0 | 0 | 0 | 0 | 0 | 19200
|  | Painting of IMO number | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200
|  | Painting og existing logo on funnel | QUOTED | 1 | 11520 | 11520 | 0 | 0 | 0 | 0 | 0 | 11520
1035 | 1018.06 | Brigde wings & windows
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, 10% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | QUOTED | 1 | 13200 | 17420 | -4220 | 0 | 0 | 0 | 0 | 13200
1036 | 1018.07 | Cargo Crane painting
|  | HP-washing with soap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | QUOTED | 1 | 67600 | 67600 | 0 | 0 | 0 | 0 | 0 | 67600
1037 | 1041.01 | Becker rudder clearence
|  | Maker: Becker - Type: TLFKSR-1-3610/890/5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rudder bearing clearances, with clock guage, each rudder, each time | QUOTED | 2 | 7000 | 14000 | 0 | 0 | 0 | 0 | 0 | 14000
|  | Access for lower pintle measurement to be cut out. Each plate | CANCELLED | 0 | 14100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rudder and Flap drain plugs to be removed to test for water ingress and re-fitted |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | after check by Owners Representative or Chief Engineer, each rudder | QUOTED | 2 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 2000
|  | Cleaning of dock (Bunker-nit) |  | 1 | 16800 | 16800 | 0 | 0 | 0 | 0 | 0 | 16800
1038 | 1041.02 | Becker rudder EAL upgrade
|  | Becker rudder PS & SB and rudder stock PS & SB are to be removed for EAL upgrade: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remove and refitting of promas part on propeller hub for dismantling of rudder. Each | ON HOLD | 0 | 35150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding up pad eyes for dismounting of rudder blade, each padeye | QUOTED | 16 | 10000 | 160000 | 0 | 0 | 0 | 0 | 0 | 160000
|  | Access for lower pintle, each access plate | CANCELLED | 0 | 14100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pintle nut access plate to be removed for dis- and remounting of nut. |  | 4 | 27700 | 110800 | 0 | 0 | 0 | 0 | 0 | 110800
|  | Dismantling and remounting of rudder blade, based on free access, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | each rudder blade | QUOTED | 2 | 102700 | 205400 | 0 | 0 | 0 | 0 | 0 | 205400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lowering and removing and refitting of rudder stock, each rudder stock | QUOTED | 2 | 97200 | 194400 | 0 | 0 | 0 | 0 | 0 | 194400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of rudder stock for old grease, each | QUOTED | 2 | 4300 | 8600 | 0 | 0 | 0 | 0 | 0 | 8600
|  | Cleaning of rudder trunk for old grease, each | QUOTED | 2 | 21080 | 42160 | 0 | 0 | 0 | 0 | 0 | 42160
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Filling of owners new EAL compliant grease in rudder trunk, each trunk | QUOTED | 2 | 8550 | 17100 | 0 | 0 | 0 | 0 | 0 | 17100
|  | Overhaul rudder nuts | NET PRICE | 1 | 15300 | 30600 | -15300 | 0 | 0 | 0 | 0 | 15300
1039 | 1041.04 | Rudder flap and link
|  | Overhaul of rudder flaps. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Both rudderflaps to be overhauled with new bushes and thrust rings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Link mechanism to be overhauled with new bushes. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each rudder | CANCELLED | 0 | 199900 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price include: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transport of rudder blade to and from work shop, each rudder |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismantling and refitting of rudder flap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Removing of old bushes and fitting of new for rudder and rudder flap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Removing of old bushes and fitting of new in rudder link system |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible machining/repair of new bushes, rudder blade links or flap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | links to be priced after dismantling and cleaning of link system |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1040 | 1041.05 | Becker Rudder coating
|  | Closed staging on the forward part | QUOTED | 1 | 58800 | 60800 | -2000 | 0 | 0 | 0 | 0 | 58800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing max 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Blasting forward part SA2½ |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Blasting aft part SA2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of aft part | QUOTED | 2 | 58840 | 117680 | 0 | 0 | 0 | 0 | 0 | 117680
|  | Add painting of forward (new scope) |  | 1 | 50400 | 0 | 50400 | 0 | 0 | 0 | 0 | 50400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible repairs or grinding of blasted rudder area: to be agreed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Owners subcontractor, Company MetaLine to coat the forward part of the rudder |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preparation | CANCELLED | 0 | 4000 | 4000 | 0 | -4000 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Services to be arranged by yard to Metaline: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1. Dehumidified compressed air (about 6 bars, max. 1 m³ per minute) | CANCELLED | 0 | 3500 | 7000 | 0 | -7000 | 0 | 0 | 0 | 0
|  | 2. Lightning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Electrical supply 230V | QUOTED | 1 | 10150 | 20300 | 0 | -10150 | 0 | 0 | 0 | 10150
|  | Possible further assistance to owners subcontractor to be agreed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1041 | 1102.01 | Blocked drain pipes
|  | 2 pcs blocked DIN 125 drain pipes at frame 221 PS & SB. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pipes to b flushed with high pressure felxible hose in order |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to remove the clogging. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | High pressure bach flush | QUOTED | 1 | 5750 | 30000 | -24250 | 0 | 0 | 0 | 0 | 5750
|  | Cutting of two pipes for add cleaning and galvanized. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mounted with new studs and straub coubling |  | 1 | 42300 | 0 | 42300 | 0 | 0 | 0 | 0 | 42300
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | In case that high pressure flushing can not loosen the clogging. The clogging |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | are to be loccated and pipe to be cut for easy cleaning or exchange. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1042 | 1108.01 | Deck painting
|  | Lower hold painting, 500 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with soap, each m2 | QUOTED | 500 | 25 | 15000 | -2500 | 0 | 0 | 0 | 0 | 12500
|  | Cleaning and suction of water, each m2 | QUOTED | 500 | 66 | 39600 | -6600 | 0 | 0 | 0 | 0 | 33000
|  | Mechanical cleaning, 8%, Each m2 | QUOTED | 40 | 180 | 96000 | -88800 | 0 | 0 | 0 | 0 | 7200
|  | Cleaning before painting, each m2 | QUOTED | 500 | 55 | 33000 | -5500 | 0 | 0 | 0 | 0 | 27500
|  | 1 x TU by roller/brush, 13%, each m2 |  | 65 | 36 | 0 | 2340 | 0 | 0 | 0 | 0 | 2340
|  | 1 x TU by roller/brush, 13%, each m2 |  | 65 | 36 | 0 | 2340 | 0 | 0 | 0 | 0 | 2340
|  | 1 x TU by roller/brush, 13%, each m2 |  | 65 | 36 | 0 | 2340 | 0 | 0 | 0 | 0 | 2340
|  | HP-washing with 170 bar after order from paint inspector, each m2 |  | 500 | 19.5 | 0 | 9750 | 0 | 0 | 0 | 0 | 9750
|  | Cleaning and suction of water, each m2 |  | 500 | 66 | 0 | 33000 | 0 | 0 | 0 | 0 | 33000
|  | 1 x FC applied with airless gun, each m2 | QUOTED | 500 | 13.5 | 8100 | -1350 | 0 | 0 | 0 | 0 | 6750
|  | Application of sand on deck, each m2 | QUOTED | 500 | 10 | 6000 | -1000 | 0 | 0 | 0 | 0 | 5000
|  | 1 x FC applied with airless gun, each m2 | QUOTED | 500 | 13.5 | 8100 | -1350 | 0 | 0 | 0 | 0 | 6750
|  | Covering against overspray, each m2 | QUOTED | 500 | 3.5 | 2100 | -350 | 0 | 0 | 0 | 0 | 1750
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Main deck hatch, 300m2 based 100%: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with soap, each m2 |  | 300 | 25 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500
|  | Cleaning and suction of water before cyclone cleaning, each m2 |  | 300 | 66 | 0 | 19800 | 0 | 0 | 0 | 0 | 19800
|  | Cyclone treatment of deck, each m2 |  | 300 | 160 | 0 | 48000 | 0 | 0 | 0 | 0 | 48000
|  | Cleaning before painting, each m2 |  | 300 | 55 | 0 | 16500 | 0 | 0 | 0 | 0 | 16500
|  | 1 x FC applied with airless gun, each m2 |  | 300 | 13.5 | 0 | 4050 | 0 | 0 | 0 | 0 | 4050
|  | 1 x FC applied with airless gun, each m2 |  | 300 | 13.5 | 0 | 4050 | 0 | 0 | 0 | 0 | 4050
|  | Application of sand on deck, each m2, |  | 300 | 10 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000
|  | 1 x FC applied with airless gun, each m2 |  | 300 | 13.5 | 0 | 4050 | 0 | 0 | 0 | 0 | 4050
|  | Covering against overspray, each m2 |  | 300 | 3.5 | 0 | 1050 | 0 | 0 | 0 | 0 | 1050
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Main deck hatch, 150m2 Mek. spot: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with soap, each m2 |  | 150 | 25 | 0 | 3750 | 0 | 0 | 0 | 0 | 3750
|  | Cleaning and suction of water, each m2 |  | 150 | 66 | 0 | 9900 | 0 | 0 | 0 | 0 | 9900
|  | Mechanical cleaning, 15%, Each m2 |  | 23 | 180 | 0 | 4050 | 0 | 0 | 0 | 0 | 4050
|  | Cleaning before painting, each m2 |  | 150 | 55 | 0 | 8250 | 0 | 0 | 0 | 0 | 8250
|  | 1 x TU by roller/brush, 20%, each m2 |  | 30 | 36 | 0 | 1080 | 0 | 0 | 0 | 0 | 1080
|  | 1 x TU by roller/brush, 20%, each m2 |  | 30 | 36 | 0 | 1080 | 0 | 0 | 0 | 0 | 1080
|  | 1 x TU by roller/brush, 20%, each m2 |  | 30 | 36 | 0 | 1080 | 0 | 0 | 0 | 0 | 1080
|  | HP-washing with 170 bar after order from paint inspector, each m2 |  | 150 | 19.5 | 0 | 2925 | 0 | 0 | 0 | 0 | 2925
|  | Cleaning and suction of water, each m2 |  | 150 | 66 | 0 | 9900 | 0 | 0 | 0 | 0 | 9900
|  | 1 x FC applied with airless gun, each m2 |  | 150 | 13.5 | 0 | 2025 | 0 | 0 | 0 | 0 | 2025
|  | Application of sand on deck, each m2, |  | 150 | 10 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500
|  | 1 x FC applied with airless gun, each m2 |  | 150 | 13.5 | 0 | 2025 | 0 | 0 | 0 | 0 | 2025
|  | Covering against overspray, each m2 |  | 150 | 3.5 | 0 | 525 | 0 | 0 | 0 | 0 | 525
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Main deck painting,1228 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with soap, each m2 | QUOTED | 1228 | 25 | 30000 | 700 | 0 | 0 | 0 | 0 | 30700
|  | Cleaning and suction of water, each m2 | QUOTED | 1228 | 66 | 79200 | 1848 | 0 | 0 | 0 | 0 | 81048
|  | Mechanical cleaning, 7%, Each m2 | QUOTED | 86 | 180 | 192000 | -176527 | 0 | 0 | 0 | 0 | 15473
|  | Cleaning before painting, each m2 | QUOTED | 1228 | 55 | 66000 | 1540 | 0 | 0 | 0 | 0 | 67540
|  | 1 x TU by roller/brush, 12%, each m2 |  | 147 | 36 | 0 | 5305 | 0 | 0 | 0 | 0 | 5305
|  | 1 x TU by roller/brush, 12%, each m2 |  | 147 | 36 | 0 | 5305 | 0 | 0 | 0 | 0 | 5305
|  | 1 x TU by roller/brush, 12%, each m2 |  | 147 | 36 | 0 | 5305 | 0 | 0 | 0 | 0 | 5305
|  | HP-washing with 170 bar after order from paint inspector, each m2 |  | 1228 | 19.5 | 16200 | 7746 | 0 | 0 | 0 | 0 | 23946
|  | Cleaning and suction of water, each m2 |  | 1228 | 66 | 0 | 81048 | 0 | 0 | 0 | 0 | 81048
|  | 1 x FC applied with airless gun, each m2 | QUOTED | 1228 | 13.5 | 16200 | 378 | 0 | 0 | 0 | 0 | 16578
|  | Application of sand on deck, each m2 | QUOTED | 1228 | 10 | 12000 | 280 | 0 | 0 | 0 | 0 | 12280
|  | 1 x FC applied with airless gun, each m2 | QUOTED | 1228 | 13.5 | 16200 | 378 | 0 | 0 | 0 | 0 | 16578
|  | Covering against overspray, each m2 | QUOTED | 1228 | 3.5 | 4200 | 98 | 0 | 0 | 0 | 0 | 4298
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Weather deck painting,1570 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with soap, each m2 | QUOTED | 1570 | 25 | 31250 | 8000 | 0 | 0 | 0 | 0 | 39250
|  | Cleaning and suction of water before cyclone treatment, each m2 | QUOTED | 1570 | 66 | 82500 | 21120 | 0 | 0 | 0 | 0 | 103620
|  | Cyclone treatment of deck, each m2 | QUOTED | 1570 | 160 | 200000 | 51200 | 0 | 0 | 0 | 0 | 251200
|  | Cleaning before painting, each m2 | QUOTED | 1570 | 55 | 68750 | 17600 | 0 | 0 | 0 | 0 | 86350
|  | 1 x FC applied with airless gun, each m2 | QUOTED | 1570 | 13.5 | 16875 | 4320 | 0 | 0 | 0 | 0 | 21195
|  | 1 x FC applied with airless gun, each m2 | QUOTED | 1570 | 13.5 | 16875 | 4320 | 0 | 0 | 0 | 0 | 21195
|  | Application of sand on deck, each m2 | QUOTED | 1570 | 10 | 12500 | 3200 | 0 | 0 | 0 | 0 | 15700
|  | 1 x FC applied with airless gun, each m2 | QUOTED | 1570 | 13.5 | 16875 | 4320 | 0 | 0 | 0 | 0 | 21195
|  | Covering against overspray, each m2 | QUOTED | 1570 | 3.5 | 4375 | 1120 | 0 | 0 | 0 | 0 | 5495
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional unitprices etc.: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of lane lines, based 4100 meter, each m | CANCELLED | 0 | 45 | 184500 | -184500 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each | QUOTED | 428 | 35 | 19250 | -4270 | 0 | 0 | 0 | 0 | 14980
|  | Covering of lashing pot tops before paint, each | QUOTED | 428 | 25 | 13750 | -3050 | 0 | 0 | 0 | 0 | 10700
|  | Cleaning and painting of lashing pots, based 550 pcs. | CANCELLED | 0 | 450 | 247500 | -247500 | 0 | 0 | 0 | 0 | 0
1043 | 1108.03 | Bimagrip
|  | Bimagrip application, 308m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with soap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cyclone treatment |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclone cleaning is not possible |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Application of Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Marking of edges |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each m2 | QUOTED | 308 | 575 | 457125 | -280025 | 0 | 0 | 0 | 0 | 177100
1044 | 1108.04 | Ceiling on weather deck
|  | Paint treatment, 485 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing 500 bar with soap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scraping of paint edges and loose paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift, m2 | QUOTED | 485 | 300 | 45000 | 100500 | 0 | 0 | 0 | 0 | 145500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Changing of rusty screws: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection and determination of workscope | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1045 | 1108.05 | Painting ceiling plates at MD to WD ramp
|  | Paint treatment, 250 m2: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scraping of paint edges and loose paint |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | CANCELLED | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible staging in case lift can not be used |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1046 | 1111.01 | Tank cleaning
|  | Possible manhole covers removed and refitted with existing gaskets: | ON HOLD | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on max size 600*800mm, each |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply of new yard standard rubber gaskets, each | ON HOLD | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Suction tank bottom incl. Removal/disposal of max 2m3 of pumpable waste |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on empty tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bilge water tank 82D | CANCELLED | 0 | 8840 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bilge water tank 82C | CANCELLED | 0 | 8840 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sludge tank 87 | QUOTED | 1 | 8840 | 0 | 8840 | 0 | 0 | 0 | 0 | 8840
|  | Sludge tank 83 | QUOTED | 1 | 8840 | 0 | 8840 | 0 | 0 | 0 | 0 | 8840
|  | Scrubber sludge tank | QUOTED | 1 | 8840 | 0 | 8840 | 0 | 0 | 0 | 0 | 8840
|  | HFO settling tank 33 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | HFO service tank 35 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | HFO service tank 37 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | HFO settling tank 39 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional suction, each hour | QUOTED | 20 | 1150 | 23000 | 16675 | -16675 | 0 | 0 | 0 | 23000
|  | Possible additional disposal, each m3 | QUOTED | 9 | 1200 | 12000 | 82800 | -84000 | 0 | 0 | 0 | 10800
|  | Possible additional cleaning: | QUOTED | 1 | 125556 | 0 | 125556 | 0 | 0 | 0 | 0 | 125556
1047 | 1111.02 | Tank cleaning for EAL conversion.
|  | Possible manhole covers removed and refitted with existing gaskets: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on max size 600*800mm, each | CREW | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply of new yard standard rubber gaskets, each | CREW | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Suction tank bottom incl. Removal/disposal of max 2m3 of pumpable waste |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on empty tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LO cleaning tank | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | CPP drain tank 90 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | CPP drain tank 91 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | Sterntube drain tank 84 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | Sterntube drain tank 85 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | Hy. Unit for CPP PS | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | Hy. Unit for CPP SB | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 0 | 0 | 8840
|  | CPP storage tank | QUOTED | 1 | 8840 | 0 | 8840 | 0 | 0 | 0 | 0 | 8840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional suction, each hour |  | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional disposal, each m3 |  | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional cleaning | QUOTED | 1 | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 38500
|  | Possible additional cleaning: to be agreed upon |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1048 | 1111.03 | Cleaning FW tank 60+61.
|  | Possible manhole covers removed and refitted with existing gaskets: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on max size 600*800mm, each | CANCELLED | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply of new yard standard rubber gaskets, each | CANCELLED | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of following FW tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FW tank 60, 61,3 m3 | CANCELLED | 0 | 61.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FW tank 61, 86,2 m3 | CANCELLED | 0 | 86.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049 | 1114.01 | Ballast tanks
|  | Ballast tanks, heeling tanks and cofferdams: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The vessel's crew will open and close manholes to the tanks. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible protection of manhole by yard, per pcs. | CANCELLED | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Below prices are based on empty, clean tanks ready for hot-work. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | In general: excl. Possible access holes cut/closed for access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible hosing down tanks and flushing through bottomplugs, each m3 tank | CANCELLED | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning and painting: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible oil and grease is removed by emulsifier, followed by HPFW hosing |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | (min. 300 bar) to remove salts and other impurities and painting: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | To be priced after inspection of ballast tanks and agreement of work scope |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050 | 1120.01 | Securing of Stern ramp
|  | Preventer arrangement: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stern ramps to be opened and secured with owner supplied preventer wires. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wires to be dismounted prior to departure. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preventer wires/units 2 units pr. side each ramp. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total of 8 wires/units to be secured. | QUOTED | 1 | 32500 | 32500 | 0 | 0 | 0 | 0 | 0 | 32500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Protection of hydraulic cylinders for Stern Ramp: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydraulic cylinders for open/close, icebreaker, Locking/cleating hydraulic |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | cylinders for aft ramps to be protected before any sandblasting or spray painting | CREW | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051 | 1123.01 | Painting of A-mast
|  | Revised scope based Ark Germania: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, based 2% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down with FW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 x TU, based 7% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cost | QUOTED | 1 | 100800 | 100800 | 0 | 0 | 0 | 0 | 0 | 100800
1052 | 1123.02 | Painting of fore mast
|  | Revised scope based Ark Germania: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning, based 3% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hosing down with FW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 x TU, based 8% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cost | QUOTED | 1 | 34800 | 34800 | 0 | 0 | 0 | 0 | 0 | 34800
1053 | 1201.01 | Chain locker and eductors
|  | Cleaning of chainlocker: | CANCELLED | 0 | 32020 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional cleaning for painting and painting: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | priced after inspection of chain lockers |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhaul of 2 pcs. Valves for bilge suction from chain lockers | CANCELLED | 0 | 3860 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subject to free access |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible air blow test : as per account |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054 | 1201.02 | Anchors and chains
|  | Anchors and chains ranged in dock, HP-washed, measured and marked with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | stainless steel band | QUOTED | 1 | 34000 | 34000 | 0 | 0 | 0 | 0 | 0 | 34000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chain end-for-ended, each | CANCELLED | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Supply of shackles etc. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WJ2/blasting of anchors | QUOTED | 1 | 16800 | 16800 | 0 | 0 | 0 | 0 | 0 | 16800
|  | Painting of anchors | QUOTED | 1 | 9600 | 19200 | -9600 | 0 | 0 | 0 | 0 | 9600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Spraying of chains with fishoil in chain locker (owners supply) | CANCELLED | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible supply of fishoil by yard 200 liter - ESTIMATE subject actual type needed | CANCELLED | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chainlocker: see item 1201.01 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting of markings |  | 1 | 12800 | 0 | 12800 | 0 | 0 | 0 | 0 | 12800
1055 | 1225.01 | New bunker pipe for lube oil tk. 72
|  | Bunker pipe for Lube oil tk. 72 to be modified according to attached description |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and drawings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | All parts such as, pipes, valves, connections and bulkhead penetrations to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | delivered by ship yard. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | All touched steel to be painted according to paint specification. | QUOTED | 1 | 85500 | 85500 | 0 | 0 | 0 | 0 | 0 | 85500
1056 | 1301.01 | Anchor Winch - Pins for roller chain stopper
|  | Pins from roller chain stopper for chain 70-K3 ( starboard and portside) for |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | anchor winches, to be dismantled, cleaned measured, reasampled and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | greased | QUOTED | 1 | 26500 | 26500 | 0 | 0 | 0 | 0 | 0 | 26500
|  | Anchor chain PS & SB to be lifted and secured with the chain and turnbuckles |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | dedicated for securing on-site. | QUOTED | 1 | 9100 | 9100 | 0 | 0 | 0 | 0 | 0 | 9100
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible repairs to be priced after agrement of work scope |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057 | 1302.01 | Overhaul fairlead roller
|  | Dismounting, cleaning and remounting of fairlead rollers, each roller | CANCELLED | 0 | 6740 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rollers in fairleads loosened without dismounting, each roller | CANCELLED | 0 | 4040 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible cut-out in vessel for dismounting rollers, each roller | CANCELLED | 0 | 4340 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible renewal of bushing in rollers after rollers have been dismounted, each | CANCELLED | 0 | 1640 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible welding up wear and tear rollers, each | CANCELLED | 0 | 3020 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift for access, each per day | CANCELLED | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paint treatment: priced after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1058 | 1303.01 | Steering gear Major overhaul PS & SB
|  | Steering Gear: Frydenbo type RV 900-2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Major overhaul to be performed on both PS & SB steering gear. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Note. that there is no cover in the deck for access meaning that both steerinmg |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | gears are to be overhauled onsite. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Jumping clearance to be noted. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actuator to opened for complete removal and overhaul on-site. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Allow for replacement of liners, thrust rings, gland seals and internal seals and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | wear parts. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rudder stock lip seal rings to be replaced. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person in 12 hours day shift: |  | 0 |  | 320650 | -180650 | 0 | -140000 | 0 | 0 | 0
|  | According to timesheet 11-06-2024 |  | 1 | 19850 | 19850 | 0 | 0 | 0 | 0 | 0 | 19850
|  | According to timesheet 12-06-2024 |  | 1 | 25500 | 25500 | 0 | 0 | 0 | 0 | 0 | 25500
|  | According to timesheet 13-06-2024 |  | 1 | 34000 | 34000 | 0 | 0 | 0 | 0 | 0 | 34000
|  | According to timesheet 14-06-2024 |  | 1 | 34000 | 0 | 34000 | 0 | 0 | 0 | 0 | 34000
|  | According to timesheet 15-06-2024 |  | 1 | 34860 | 0 | 34860 | 0 | 0 | 0 | 0 | 34860
|  | According to timesheet 16-06-2024 |  | 1 | 34000 | 0 | 34000 | 0 | 0 | 0 | 0 | 34000
|  | According to timesheet 17-06-2024 |  | 1 | 41040 | 0 | 41040 | 0 | 0 | 0 | 0 | 41040
|  | According to timesheet 18-06-2024 |  | 1 | 35480 | 0 | 35480 | 0 | 0 | 0 | 0 | 35480
|  | According to timesheet 19-06-2024 |  | 1 | 27200 | 0 | 27200 | 0 | 0 | 0 | 0 | 27200
|  | According to timesheet 20-06-2024 |  | 1 | 34000 | 0 | 0 | 0 | 34000 | 0 | 0 | 34000
|  | According to timesheet 21-06-2024 |  | 1 | 34000 | 0 | 0 | 0 | 34000 | 0 | 0 | 34000
|  | According to timesheet 22-06-2024 |  | 1 | 34000 | 0 | 0 | 0 | 34000 | 0 | 0 | 34000
|  | According to timesheet 23-06-2024 |  | 1 | 34890 | 0 | 0 | 0 | 34890 | 0 | 0 | 34890
|  | According to timesheet 24-06-2024 |  | 1 | 34000 | 0 | 0 | 0 | 34000 | 0 | 0 | 34000
|  | According to timesheet 25-06-2024 |  | 1 | 17000 | 0 | 0 | 0 | 17000 | 0 | 0 | 17000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Before reinstallation is the old casting to removed and area cleaned. Upon |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | installation of the steering gear is new casting to be laid. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1059 | 1311.01 | Change of oil cooler Cargo Crane
|  | Removing "flange" to access cooler. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Replacing old cooler with new owner delivered cooler. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Densotape/Densyltape fitted back on hydraulic hoses after installing new cooler. | CANCELLED | 0 | 54400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure test of cooler and connections to be done by crane in operating oil |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | presussure |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1060 | 1317.01 | Repair of hydralic equipment (Macgregor)
|  | Hydraulic equipment to be repaired by Macgregor (owner arranged and paid). |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Yard to assist Macgregor per hourly basics if found necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist: Each person per 12 hour shift |  | 0 |  | 60000 | -10000 | 0 | -50000 | 0 | 0 | 0
|  | Cherry Picker, each day | QUOTED | 24 | 3500 | 84000 | 0 | 0 | 0 | 0 | 0 | 84000
|  | Welding machines, each day | QUOTED | 15 | 1500 | 0 | 22500 | 0 | 0 | 0 | 0 | 22500
|  | Welding gas, each | QUOTED | 5 | 700 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500
|  | Assistance: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | According to timesheet 14-06-2024 |  | 1 | 5100 | 0 | 5100 | 0 | 0 | 0 | 0 | 5100
|  | According to timesheet 15-06-2024 |  | 1 | 15290 | 0 | 15290 | 0 | 0 | 0 | 0 | 15290
|  | According to timesheet 17-06-2024 |  | 1 | 6235 | 0 | 6235 | 0 | 0 | 0 | 0 | 6235
|  | According to timesheet 19-06-2024 |  | 1 | 46750 | 0 | 46750 | 0 | 0 | 0 | 0 | 46750
|  | According to timesheet 24-06-2024 |  | 1 | 16065 | 0 | 0 | 0 | 16065 | 0 | 0 | 16065
1061 | 1317.02 | Greasing points for lower hold hinges
|  | Greasing nipples to be installed in 17 pcs. Guide hinges for lower hold cover. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preperation and removal of pin. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining of greasing channel, delivering and mounting of grease nippel in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stainless Steel for each pin. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mounting pin back in place | OWNER | 0 | 263360 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1062 | 1317.03 | Gasket for lower hold cover
|  | Gasket replacement |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gasket replacement per running meter. Seam for gasket mechanical cleaned |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and painted before the new gasket is installed. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each meter, | OWNER | 0 | 1815 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry picker per day | OWNER | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tightness test to be performed using hose with fresh water after the repair is |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | completed. Each test | OWNER | 0 | 4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1063 | 1401.01 | Freefall lifeboat (FFB)
|  | Freefall boat to be lifted down and taken to workshop and return after overhaul. | QUOTED | 1 | 16000 | 16000 | 0 | 0 | 0 | 0 | 0 | 16000
|  | Boat to be polished in order to remove gray layor |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | All markings are to be renewed. Markings are owners supply | CANCELLED | 0 | 34350 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Revised scope according to Ark Germania: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Davit is to be cleaned by high pressure fresh water (min. 300 bar) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Staging B6 | CANCELLED | 0 |  | 8000 | -8000 | 0 | 0 | 0 | 0 | 0
|  | Rusty spots (anticipate app. 2 %) are to be mechanical cleaned to St 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and afterwards painted according to paint specification |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power supply + rigging | CANCELLED | 0 |  | 4000 | -4000 | 0 | 0 | 0 | 0 | 0
|  | Touch up coat 125 µm - Hempadur Easy 47700 - 7% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Touch up coat 125 µm - Hempadur Easy 47000 - 7% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Touch up coat 50 µm - Hempathane topcoat 55210 - 7% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC | QUOTED | 1 | 71160 | 0 | 71160 | 0 | 0 | 0 | 0 | 71160
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Staging for polishing team (for FFB) in LB6 | VOR 2 | 1 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power Supply, rigging, consumption | VOR 2 | 1 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1401.01 Polishing of Free Fall Lifeboat (FFB) - underwater part |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Polishing of FFB under water part | VOR 8 | 1 | 24300 | 0 | 24300 | 0 | 0 | 0 | 0 | 24300
|  | Excl. possible markings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1064 | 1401.02 | MOB boat
|  | Boat to be lifted down and taken to workshop. | QUOTED | 1 | 8000 | 18000 | -10000 | 0 | 0 | 0 | 0 | 8000
|  | Boat to be cleaned and polished. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New markings to be installed. | QUOTED | 1 | 29700 | 29700 | 0 | 0 | 0 | 0 | 0 | 29700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Revised scope according to Ark Germania: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Davit is to be cleaned by high pressure fresh water (min. 300 bar) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rusty spots (anticipate app. 2 %) are to be mechanical cleaned to St 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and afterwards painted according to paint specification |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Touch up coat 125 µm - Hempadur Easy 47700 - 7% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Touch up coat 125 µm - Hempadur Easy 47000 - 7% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Touch up coat 50 µm - Hempathane topcoat 55210 - 7% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC | QUOTED | 1 | 32400 | 0 | 32400 | 0 | 0 | 0 | 0 | 32400
1065 | 2201.01 | Exhaust duct from galley
|  | Cleaning of galley exhaust ducting | QUOTED | 1 | 57680 | 57680 | 0 | 0 | 0 | 0 | 0 | 57680
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible cleaning of rotor "veksler" | CANCELLED | 0 | 23480 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible cleaning of accomodation rooms | CANCELLED | 0 | 100400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066 | 2701.01 | Refrigerant conversion AC & Provision cooling plant.
|  | No yard assistance expected | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067 | 3127.01 | Main engine AUX blowers
|  | Main Engine type: MAN B&W S40ME-B |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The 2 main engines are each fitted with 2 auxiliary blowers. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 pcs TAE-IL BLOWERS, model TBCS - 066C, type HM, weight 190 kg each |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The expected Yard scope is to renew the roller bearings in the electrical motors |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | for the blowers. 2 roller bearings are installed in each of the 2 electrical motors |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | for the auxiliary blowers. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Blowers must be dismounted completely in one assembly and brought to an |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ashore workshop. Electrical motors dismantled and fitted with new rolle |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | bearings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Once overhauled the blowers must be balanced and subsequntly re-installed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | onboard. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | It is possible to remove the floor plate above the blowers and use the engine |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | room crane to lower the blowers. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Vessels electrician will take care of electrical disconnection and re-connection. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Finally the blowers must be tested to the chief engineers satisfaction. | QUOTED | 4 | 28000 | 112000 | 0 | 0 | 0 | 0 | 0 | 112000
|  | Delivery of bearings |  | 1 | 3510 | 3510 | 0 | 0 | 0 | 0 | 0 | 3510
|  | Spraying maching of rings |  | 4 | 3300 | 13200 | 0 | 0 | 0 | 0 | 0 | 13200
|  | Spraying maching of 4 end covers |  | 4 | 6500 | 26000 | 0 | 0 | 0 | 0 | 0 | 26000
|  | Gaskets | QUOTED | 4 | 891 | 2000 | 1564 | 0 | 0 | 0 | 0 | 3564
1068 | 3227.01 | Installation of silencer on 3 pcs Aux Engines
|  | DFDS will deliver the following equipment: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - 3 pcs. New silencers. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Extension pipes. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Flanges. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Packings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Compensators. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Supports. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Yard scope: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Dismount 3 pcs. Existing outside exhaust pipes. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Installation of 3 pcs new silencers incl compensators and flanges. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Installation of foundation for new silencer |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Installation of supports for new silencers. 3 pcs on each silencer. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Staging and crane works. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Paint of all touched steel according to paint specification. | QUOTED | 1 | 333000 | 370000 | -37000 | 0 | 0 | 0 | 0 | 333000
|  | Delivery of flanges | CANCELLED | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shorten old exhaust pipe |  | 1 | 10300 | 0 | 10300 | 0 | 0 | 0 | 0 | 10300
1069 | 3302.02 | LT FW cooler
|  | Cleaning of 2 pcs. LT-coolers with 2x356 pcs. plates | QUOTED | 712 | 290 | 206480 | 0 | 0 | 0 | 0 | 0 | 206480
|  | Exchange of gaskets | QUOTED | 712 | 190 | 135280 | 0 | 0 | 0 | 0 | 0 | 135280
1070 | 3302.03 | Scrubber coolers
|  | Cleaning of 2 pcs. Scrubber water heat exchangers with 2x169 pcs. plates | QUOTED | 338 | 290 | 98020 | 0 | 0 | 0 | 0 | 0 | 98020
|  | Exchange of gaskets | QUOTED | 338 | 190 | 64220 | 0 | 0 | 0 | 0 | 0 | 64220
1071 | 3317.01 | ME LO PUMPS
|  | Overhaul of 4 pcs. Pumps | QUOTED | 4 | 34400 | 137600 | 0 | 0 | 0 | 0 | 0 | 137600
|  | Excl. Possible overhaul of el-motor |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Spare part kits, each | QUOTED | 4 | 10239 | 102390 | -61434 | 0 | 0 | 0 | 0 | 40956
|  | Gasket | QUOTED | 1 | 6160 | 24640 | 0 | -18480 | 0 | 0 | 0 | 6160
|  | Coublings |  | 1 | 3883 | 0 | 3883 | 0 | 0 | 0 | 0 | 3883
1072 | 3338.01 | Ship side valves
|  | Overhaul of sea connection valve according to list, 18 pcs | QUOTED | 1 | 42160 | 42160 | 0 | 0 | 0 | 0 | 0 | 42160
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhaul of speed log valve, 1 pcs | QUOTED | 1 | 3740 | 3740 | 0 | 0 | 0 | 0 | 0 | 3740
|  | Possible dismounting of speed log censor |  | 0 | 10340 | 10340 | 0 | -10340 | 0 | 0 | 0 | 0
|  | Possible dismounting of speed log valve house |  | 1 | 4180 | 4180 | 0 | 0 | 0 | 0 | 0 | 4180
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhaul of draft censor valves, 3 pcs in total | QUOTED | 1 | 11220 | 11220 | 0 | 0 | 0 | 0 | 0 | 11220
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scrubber valves to be opened and cleaned in place, 3 pcs | QUOTED | 1 | 8500 | 8500 | 0 | 0 | 0 | 0 | 0 | 8500
|  | Change DN 250 valves |  | 2 | 5160 | 0 | 10320 | 0 | 0 | 0 | 0 | 10320
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional for valves: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Various flooring and actuators off/on and work under flooring and in tanks |  | 1 | 7140 | 0 | 9520 | -2380 | 0 | 0 | 0 | 7140
|  | DN 65 pipe off/on for access |  | 1 | 840 | 0 | 1120 | -280 | 0 | 0 | 0 | 840
|  | DN 100 pipe off/on for access |  | 1 | 1260 | 0 | 1680 | -420 | 0 | 0 | 0 | 1260
|  | DN 125 pipe off/on for access, 2 pcs |  | 1 | 2835 | 0 | 3780 | -945 | 0 | 0 | 0 | 2835
|  | DN 350 B-fly valves off/on for access to cleaning and inspection, 2 pcs |  | 1 | 12810 | 0 | 17080 | -4270 | 0 | 0 | 0 | 12810
|  | DN 400 B-fly valve off/on for access to cleaning and inspection |  | 1 | 7245 | 0 | 9660 | -2415 | 0 | 0 | 0 | 7245
|  | DN 400 pipe off/on for access |  | 1 | 3622.5 | 0 | 4830 | -1208 | 0 | 0 | 0 | 3623
|  | DN 125 B-fly valve replaced |  | 1 | 3780 | 0 | 3780 | 0 | 0 | 0 | 0 | 3780
|  | DN 50 cone valve replaced |  | 1 | 1960 | 0 | 1960 | 0 | 0 | 0 | 0 | 1960
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining |  | 1 | 6850 | 0 | 6850 | 0 | 0 | 0 | 0 | 6850
|  | Delivery of new valves: DN125 butterfly valve + |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DN 50 Globe valve |  | 1 | 15600 | 0 | 15600 | 0 | 0 | 0 | 0 | 15600
|  | Flap valve DN350 |  | 1 | 16128 | 0 | 0 | 0 | 16128 | 0 | 0 | 16128
1073 | 3338.02 | Scrubber outlet ship bottom
|  | Full blasting and application of 1 x FC Vinyl Ester | CANCELLED | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Supplies |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible spot blasting/painting: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | priced after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074 | 3338.03 | Valves for high/low sea suction filters
|  | Exchange of hull side sea water DN600 valves (A824-001) at the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | low sea chest | QUOTED | 1 | 42520 | 0 | 42520 | 0 | 0 | 0 | 0 | 42520
|  | Exchange of hull side sea water DN600 valves (A824-002) at the |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | high sea chest | QUOTED | 1 | 31010 | 0 | 31010 | 0 | 0 | 0 | 0 | 31010
|  | Exchange of DN600 valves (A824-003 and A824-004) after |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | sea filters, Each valve | CANCELLED | 0 | 12460 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 pcs DN 600 internal valves to be cleaned and greased |  | 1 | 11450 | 0 | 11450 | 0 | 0 | 0 | 0 | 11450
|  | New bolts for seawater filter |  | 1 | 5860 | 0 | 5860 | 0 | 0 | 0 | 0 | 5860
1075 | 3339.01 | Scrubber powder vent pipe modification
|  | For yard info only | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1076 | 3339.02 | Outlet pipe for Drencher pump #1.
|  | Fabricating and mounting of new DN250 galvanized pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | for the pressure side of Drencher Pump no. 1. | QUOTED | 1 | 35500 | 35500 | 0 | 0 | 0 | 0 | 0 | 35500
|  | Coating of pipe is included in price |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1077 | 3339.03 | Ballast Water Treatment Plant
|  | Ballast Water Treatment Plant |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1. Mechanical works |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1 Transport and mounting of Owner supplied equipment | QUOTED | 1 | 75240 | 75240 | 0 | 0 | 0 | 0 | 0 | 75240
|  | 1.2 Filter Placement, based on new filter with in and out in same side | QUOTED | 1 | 225612 | 225612 | 0 | 0 | 0 | 0 | 0 | 225612
|  | 1.2 Additional price based on new received documentation 29.11.2023 | QUOTED | 1 | 29000 | 29000 | 0 | 0 | 0 | 0 | 0 | 29000
|  | 1.3 LDC placement | QUOTED | 1 | 69606 | 69606 | 0 | 0 | 0 | 0 | 0 | 69606
|  | 1.4 Controle Cabinet mounting-brackets | QUOTED | 1 | 22770 | 22770 | 0 | 0 | 0 | 0 | 0 | 22770
|  | 1.5 CIP unit | QUOTED | 1 | 36630 | 36630 | 0 | 0 | 0 | 0 | 0 | 36630
|  | 1.6 Flow meter | QUOTED | 1 | 5247 | 5247 | 0 | 0 | 0 | 0 | 0 | 5247
|  | 1.7 Floor plates removal | QUOTED | 1 | 18315 | 18315 | 0 | 0 | 0 | 0 | 0 | 18315
|  | 2. Pipe & Valve works |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.1 Pipe 309 - Backflush filter | QUOTED | 1 | 5346 | 5346 | 0 | 0 | 0 | 0 | 0 | 5346
|  | 2.2 Pipe 310.1 - Flushing inlet CIP | QUOTED | 1 | 1386 | 1386 | 0 | 0 | 0 | 0 | 0 | 1386
|  | 2.3 PIpe 310.2 - Flushing | QUOTED | 1 | 5445 | 5445 | 0 | 0 | 0 | 0 | 0 | 5445
|  | 2.3 Additional price based on new received documentation 29.11.2023 | QUOTED | 1 | 33200 | 33200 | 0 | 0 | 0 | 0 | 0 | 33200
|  | 2.4 Pipe 320 - CIP fluid inlet | QUOTED | 1 | 6336 | 6336 | 0 | 0 | 0 | 0 | 0 | 6336
|  | 2.5 Pipe 321 - CIP fluid outlet | QUOTED | 1 | 5742 | 5742 | 0 | 0 | 0 | 0 | 0 | 5742
|  | 2.6 Pipe 401 - Cooling water LDC inlet | QUOTED | 1 | 3861 | 3861 | 0 | 0 | 0 | 0 | 0 | 3861
|  | 2.7 Pipe 402 - Cooling water LDC outlet | QUOTED | 1 | 3168 | 3168 | 0 | 0 | 0 | 0 | 0 | 3168
|  | 2.8 Pipe 403 - SW cooling AOT inlet | QUOTED | 1 | 2574 | 2574 | 0 | 0 | 0 | 0 | 0 | 2574
|  | 2.9 Pipe 404 - SW cooling AOT outlet | QUOTED | 1 | 6336 | 6336 | 0 | 0 | 0 | 0 | 0 | 6336
|  | 2.10 Pipe 460 - Drain pipe filter | QUOTED | 1 | 7623 | 7623 | 0 | 0 | 0 | 0 | 0 | 7623
|  | 2.11 Pipe 460.1 - Drain reactor CIP unit | QUOTED | 1 | 1881 | 1881 | 0 | 0 | 0 | 0 | 0 | 1881
|  | 2.12 Pipe 460.2 - Drain CIP unit | QUOTED | 1 | 4455 | 4455 | 0 | 0 | 0 | 0 | 0 | 4455
|  | 2.13 Pipe 501 - Instrument air | QUOTED | 1 | 34848 | 34848 | 0 | 0 | 0 | 0 | 0 | 34848
|  | 2.14 Bilge pipe | QUOTED | 1 | 10791 | 10791 | 0 | 0 | 0 | 0 | 0 | 10791
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Electrical works: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | included: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivering and install new TMD 100 in MSB |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disconnect and remove existing not reused installation. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deliver and install new supply Cable . 3x50mm2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Internal cabling on new BWTS skid |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Modification on bridge panel to fit new screen and buttons |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional / modification of cable ways |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Extending bracket for control cabinet/ close penetration |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigging of electrical equipment | QUOTED | 1 | 298100 | 298100 | 0 | 0 | 0 | 0 | 0 | 298100
|  | 3. Additional price based on new received documentation 29.11.2023 | QUOTED | 1 | 17280 | 17280 | 0 | 0 | 0 | 0 | 0 | 17280
|  | Excluded in electrical work price: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible new cables to bridge |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sensors, transmitters etc. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. DN65 | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
|  | Painting of new and affected areas | QUOTED | 1 | 24500 | 24500 | 0 | 0 | 0 | 0 | 0 | 24500
|  | Delivery of 2 pcs valves | CANCELLED | 0 | 9714 | 9714 | 0 | -9714 | 0 | 0 | 0 | 0
|  | Additional: Installation of FW piping in steel instead of Mapress |  | 1 | 13360 | 13360 | 0 | 0 | 0 | 0 | 0 | 13360
|  | Additional: Gratings |  | 1 | 19320 | 19320 | 0 | 0 | 0 | 0 | 0 | 19320
|  | Delivery and install of extra cables | CANCELLED | 0 | 22185 | 22185 | 0 | -22185 | 0 | 0 | 0 | 0
1078 | 3401.01 | AUX boiler
|  | Boiler opened on water and smokeside and closed afte rinspection. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Valves according to list exchanged with renovated valves supplied by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismounted valves to be overhauled and returned to vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. 12 hours vacuum truck and disposal of max 2 m3 of pumpable waste | CANCELLED | 0 | 95650 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible supply of packings, bolts, nuts etc. For exchanging valves |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | only valves |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional vacuum truck, each hour | CANCELLED | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional disposal, each m3 | CANCELLED | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Replacement of 31 pcs valves on OFB and EGB |  | 1 | 53585 | 53585 | 0 | 0 | 0 | 0 | 0 | 53585
1079 | 3411.01 | Exh. Boiler
|  | Boiler opened on water and smokeside and closed afte rinspection. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Valves according to list exchanged with renovated valves supplied by owner. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dismounted valves to be overhauled and returned to vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. 12 hours vacuum truck and disposal of max 2 m3 of pumpable waste | CANCELLED | 0 | 101650 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible supply of packings, bolts, nuts etc. For exchanging valves |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional vacuum truck, each hour | CANCELLED | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible additional disposal, each m3 | CANCELLED | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Replacement of valves | ++ | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1080 | 3801.01 | Ropeguard
|  | To protect the aft seal against fishing nets and similar there is installed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Cutters. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Missing Net Cutters to be refitted by yard on each stuffing box close to rotating |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | shafts according to the superintendents instructions. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The total number of robe knives is 6 pcs/aft seal. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivering and fitting of missing rope guard knives, each |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Polish knives | QUOTED | 1 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 7000
1081 | 3801.02 | Test of propeller movement
|  | Test of propeller movement | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1082 | 3801.03 | Polishing of propeller blades
|  | Work order Polishing of propeller blades |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Normal polishing of propeller blades, each blade | QUOTED | 8 | 11900 | 95200 | 0 | 0 | 0 | 0 | 0 | 95200
|  | Dye check penetrant on blade root and blade edge, each blade |  | 8 | 4850 | 4850 | 33950 | 0 | 0 | 0 | 0 | 38800
|  | 3M Sponge polishing | CANCELLED | 0 | 25000 | 25000 | -25000 | 0 | 0 | 0 | 0 | 0
|  | Reduction - Less polishing |  | 1 | -9520 | 0 | 0 | 0 | 0 | 0 | -9520 | -9520
1083 | 3801.04 | Propeller, blade foot seal & EAL conversion.
|  | Propeller blade foot seals PS & SB to be changed and change of all |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CPP oil due to EAL conversion. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Type MAN VBS1350/Mk |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller blade foot seal to be changed on all 4 blades on both propellers. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each / 8 pcs | QUOTED | 8 | 18000 | 144000 | 0 | 0 | 0 | 0 | 0 | 144000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CPP oil to be drained of the propeller hubs and disposed. Total 1750 l |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New EAL oil will be supplied by owner and refilled by crew. Each / 2 pcs | QUOTED | 2 | 15300 | 30600 | 0 | 0 | 0 | 0 | 0 | 30600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Disposal of oil, each m3 | QUOTED | 2 | 1200 | 2100 | 0 | 0 | 0 | 0 | 0 | 2100
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8 pcs. blade foot and blade roots to be dye-checked in place. Each/8 blade roots. | QUOTED | 8 | 4850 | 38800 | 0 | 0 | 0 | 0 | 0 | 38800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Blade bolts to be cleaned and visual inspected, bolt to be NDT |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | penetrant tested. Each/64 | QUOTED | 64 | 1775 | 113600 | 0 | 0 | 0 | 0 | 0 | 113600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Blade boltes should be "baked" as a minimum 5 hours at 180-230 degrees C |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | in an oven before NDT. NB: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Blade screws marked/stamped "H" in the threaded end, do NOT need |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to be Heat treated as described before. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Based on min. 12 bolts to be heat treated. Each bolt | CANCELLED | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydraulic tools for total work scope. | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining of propeller blade foot, each |  | 8 | 20000 | 0 | 160000 | 0 | 0 | 0 | 0 | 160000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Further assistance to owners specialist: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | According to timesheet 17-06-2024 |  | 1 | 29240 | 0 | 29240 | 0 | 0 | 0 | 0 | 29240
|  | According to timesheet 18-06-2024 |  | 1 | 38250 | 0 | 38250 | 0 | 0 | 0 | 0 | 38250
|  | According to timesheet 19-06-2024 |  | 1 | 19040 | 0 | 19040 | 0 | 0 | 0 | 0 | 19040
|  | According to timesheet 20-06-2024 |  | 1 | 27040 | 0 | 0 | 0 | 27040 | 0 | 0 | 27040
|  | According to timesheet 21-06-2024 |  | 1 | 19455 | 0 | 0 | 0 | 19455 | 0 | 0 | 19455
|  | According to timesheet 24-06-2024 |  | 1 | 5765 | 0 | 0 | 0 | 5765 | 0 | 0 | 5765
|  | According to timesheet 26-06-2024 |  | 1 | 24600 | 0 | 0 | 0 | 24600 | 0 | 0 | 24600
1084 | 3802.01 | Tail shaft wear down
|  | Type: Aft Seal type/size: Simplex-compact SC2 B Size 480 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shaft Ø452The tail shaft wear down readings are to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | be taken before any dismantling as soon as possible after |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | docking and submitted to the Chief Engineer: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Staging, ropeguard removed/refitted and oil drained. Each | QUOTED | 2 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
|  | Oil refilled by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Measurements: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PS Aft Top and Bottom, Stbd Aft Top and Bottom. Each time | QUOTED | 3 | 3750 | 11250 | 0 | 0 | 0 | 0 | 0 | 11250
|  | PS Mid Top Stbd Mid Top. Each time | QUOTED | 1 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 10800
|  | Ps Fwd. Top Stbd Fwd. Top. Each time | QUOTED | 1 | 6150 | 6150 | 0 | 0 | 0 | 0 | 0 | 6150
1085 | 3802.02 | Stern tube seal & EAL conversion.
|  | Stern tube PS & SB is to be drained by ship yard, anticipate |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4400 Liters for each side. All sterntube oil to be disposed |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | due to EAL conversion: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Measuring of tail shaft wear down - See item 3802.01 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Draining of stern tupe oil (app. 2 x 4400 liters l) by yard |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and new oil refilled by crew | QUOTED | 2 | 16100 | 32200 | 0 | 0 | 0 | 0 | 0 | 32200
|  | Disposal of 2 x 4400 liters sterntube oil (each cbm) | QUOTED | 3 | 1200 | 3600 | 0 | 0 | 0 | 0 | 0 | 3600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forward seal: Simplex-Compact seal type SC2 Z |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PS & SB fwd seal to be disassembled and thoroughly cleaned. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Liner and old lip rings to be inspected and assessed by Service engineer and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | owners representative. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PS & SB fwd seal to be assembled with new sealing rings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Aft seal: Simplex-Compact seal type SC2 B |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PS Aft seal to be disassembled and thoroughly cleaned. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Liner and old lip rings to be inspected and assessed by Service engineer and |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | owners representative. Condition of |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | liner depends on whether distance rings are to be dismounted. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PS aft seal to be assembled with new sealing rings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SB: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller shaft to be withdrawed as per job 3805.01. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New owner supplied seal and Tungsten coated liner to be installed on the shaft. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour shift |  | 0 |  | 70250 | -20250 | 0 | -50000 | 0 | 0 | 0
|  | According to timesheet 11-06-2024 |  | 1 | 12750 | 12750 | 0 | 0 | 0 | 0 | 0 | 12750
|  | According to timesheet 12-06-2024 |  | 1 | 8500 | 8500 | 0 | 0 | 0 | 0 | 0 | 8500
|  | According to timesheet 13-06-2024 |  | 1 | 8500 | 8500 | 0 | 0 | 0 | 0 | 0 | 8500
|  | According to timesheet 14-06-2024 |  | 1 | 10175 | 0 | 10175 | 0 | 0 | 0 | 0 | 10175
|  | According to timesheet 15-06-2024 |  | 1 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500
|  | According to timesheet 16-06-2024 |  | 1 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 8500
|  | According to timesheet 18-06-2024 |  | 1 | 30100 | 0 | 30100 | 0 | 0 | 0 | 0 | 30100
|  | According to timesheet 19-06-2024 |  | 1 | 21550 | 0 | 21550 | 0 | 0 | 0 | 0 | 21550
|  | According to timesheet 20-06-2024 |  | 1 | 8500 | 0 | 0 | 0 | 8500 | 0 | 0 | 8500
|  | According to timesheet 21-06-2024 |  | 1 | 8500 | 0 | 0 | 0 | 8500 | 0 | 0 | 8500
|  | According to timesheet 22-06-2024 |  | 1 | 8500 | 0 | 0 | 0 | 8500 | 0 | 0 | 8500
|  | According to timesheet 23-06-2024 |  | 1 | 3400 | 0 | 0 | 0 | 3400 | 0 | 0 | 3400
|  | According to timesheet 24-06-2024 |  | 1 | 4250 | 0 | 0 | 0 | 4250 | 0 | 0 | 4250
|  | According to timesheet 26-06-2024 |  | 1 | 4250 | 0 | 0 | 0 | 4250 | 0 | 0 | 4250
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation of flushing pipe SB propellere stern tupe, including materials: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 12 mm Stainless steel pipe to be installed between fwd and aft |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | seal for flushing of chamber 0. Pipe to be supported every 2 meter. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Holes for pipe penetration to be drilled in fwd and aft flange and pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to be connected with stainlesssteel fittings. 3.2 certificate ball valve |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to be installed in engine room. Ball valve will be owners supply. Pipes and fittings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | are Yard supply.Before installation of propellershaft, Pressure |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test of pipe and fittings with 5,0 bar for at least 30 minutes to be carried out to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | the satisfaction of Class and owners representative. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sterntube to be thoroughly cleaned | CANCELLED | 0 | 86200 | 86200 | -86200 | 0 | 0 | 0 | 0 | 0
|  | Based on Propeller shaft to be withdrawed as per job 3805.01. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1086 | 3802.03 | Installation of ACU unit PS & SB sterntube seal
|  | ACU units will be ordered and paid by DFDS. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SKF service engineer wil be ordered by DFDS for supervision of the installation. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electrical switch board will be installed and connected prior to the docking by |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | vessels crew. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Yard scope: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Installation bracket for ACU unit PS & SB to be welded to the bulkhead in same |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | position as the pictures shows from the sister vessel. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Inlet & outlet pipe to be connected to the aft seal pipes (ø15 mm & ø18 mm SS |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pipes). SKF service engineer will appoint connection points. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each side/SB+Bb | QUOTED | 2 | 38600 | 77200 | 0 | 0 | 0 | 0 | 0 | 77200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | All touched steel to be painted according to paint specification. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each side/SB+Bb | QUOTED | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 11000
1087 | 3805.01 | Propellershaft withdrawal
|  | Propeller type: VBS1350/Mk.5/ODS400/FF |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller shaft total weight HUB, blades, coupling flange and shaft: 43200Kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller shaft total weight HUB, blades and Shaft: 36700Kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller shaft total weight HUB and Shaft: 33450Kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tail shaft including hub is 23100mm. See Drawing "Arrangement of shafting" |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Weight of hydraulic Coupling flange: 3250Kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller diameter: 4800 MM |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller Blade Weight (single blade) : 813 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller type: Variable Pitch Propeller |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Number of blades: 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BECKER RUDDER see job 1041.02 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rope guards. See job 3802.01 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stern tupe seals. See job 3802.02 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller blades. See job 3801.04 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding up pad eyes for dismounting of propeller shaft, each padeye | QUOTED | 2 | 10000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
|  | Staging for Propeller Shaft withdrawal, each side | CANCELLED | 0 | 18000 | 36000 | -36000 | 0 | 0 | 0 | 0 | 0
|  | Propeller Shaft withdrawal, each shaft | QUOTED | 2 | 180000 | 441400 | -81400 | 0 | 0 | 0 | 0 | 360000
|  | Transport |  | 2 | 30000 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000
1088 | 3811.01 | Oil change bow Thrusters
|  | Hydraulic oil from all thrusters to be drained in drums supplied by yard |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and oil to be disposed by yard. New oil to be filled by crew, each thruster |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each thruster / 2 pcs. thrusters | QUOTED | 2 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
|  | Destruction of oil, each 1 m3, assume 2 x 360 litre to be destructed | QUOTED | 1 | 1200 | 864 | 0 | 0 | 0 | 0 | 0 | 864
|  | Staging each side |  | 0 | 12500 | 50000 | 0 | -50000 | 0 | 0 | 0 | 0
1089 | 3811.02 | Bow thrusters No. 1 and No. 2
|  | Rolls Royce. KaMeWa Ulstein Tunnel Thruster Type: TT 2000 I CP |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Drive motor power: 1100 kW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Propeller diameter: 2000 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Important: Propeller tip clearances to be taken before and after work |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | is carried out and a record of these handed over to the Owners representative. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Thruster tunnel grits dis- and remounted for access, each | QUOTED | 2 | 15000 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
|  | Oil systems to be drained and flushed through and to be refilled |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and deaerated. Oil is owners supply. See job 3811.01 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Support NDE De/remount for access |  | 2 | 3000 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bow Thrusters to be dismantled and transported to workshop |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | for complete overhaul and EAL upgrade: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bow Thrusters under water part to be dismantled and transported |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to workshop for complete overhaul. Each thruster | QUOTED | 2 | 70000 | 160000 | -20000 | 0 | 0 | 0 | 0 | 140000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Further assistance to owners specialist and EAL upgrade: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour shift |  | 0 |  | 373000 | -153000 | 0 | -220000 | 0 | 0 | 0
|  | According to timesheet 11-06-2024 |  | 1 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 6750
|  | According to timesheet 12-06-2024 |  | 1 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0 | 4250
|  | According to timesheet 13-06-2024 |  | 1 | 46000 | 46000 | 0 | 0 | 0 | 0 | 0 | 46000
|  | According to timesheet 14-06-2024 |  | 1 | 20680 | 0 | 20680 | 0 | 0 | 0 | 0 | 20680
|  | According to timesheet 15-06-2024 |  | 1 | 27990 | 0 | 27990 | 0 | 0 | 0 | 0 | 27990
|  | According to timesheet 16-06-2024 |  | 1 | 35760 | 0 | 35760 | 0 | 0 | 0 | 0 | 35760
|  | According to timesheet 17-06-2024 |  | 1 | 45350 | 0 | 45350 | 0 | 0 | 0 | 0 | 45350
|  | According to timesheet 18-06-2024 |  | 1 | 38600 | 0 | 38600 | 0 | 0 | 0 | 0 | 38600
|  | According to timesheet 19-06-2024 |  | 1 | 17000 | 0 | 17000 | 0 | 0 | 0 | 0 | 17000
|  | According to timesheet 20-06-2024 |  | 1 | 22695 | 0 | 0 | 0 | 22695 | 0 | 0 | 22695
|  | According to timesheet 21-06-2024 |  | 1 | 23800 | 0 | 0 | 0 | 23800 | 0 | 0 | 23800
|  | According to timesheet 22-06-2024 |  | 1 | 37950 | 0 | 0 | 0 | 37950 | 0 | 0 | 37950
|  | According to timesheet 23-06-2024 |  | 1 | 17500 | 0 | 0 | 0 | 17500 | 0 | 0 | 17500
|  | According to timesheet 24-06-2024 |  | 1 | 13020 | 0 | 0 | 0 | 13020 | 0 | 0 | 13020
|  | According to timesheet 26-06-2024 |  | 1 | 6300 | 0 | 0 | 0 | 6300 | 0 | 0 | 6300
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining of thruster blade foot | QUOTED | 8 | 17000 | 136000 | 0 | 0 | 0 | 0 | 0 | 136000
|  | Shorten up propeller blades | ++ | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dye check of propeller blades |  | 8 | 2180 | 0 | 0 | 17440 | 0 | 0 | 0 | 17440
1090 | 3811.03 | Thruster grids
|  | Thruster grids to be carefully examined for cracks and other defects. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Amount of repair and repair method to be decided after this | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | investigation with superintendent. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1091 | 3811.04 | Thruster cavitation rings repair
|  | Stainless steel overlay weld (cavitation ring) in thruster tunnels to be |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | repaired by grinding and welding. Amount of repair to be decided |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | after the investigation with the Owner's Representative according to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | below specification: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1. Damaged areas to be detected by using ultrasonic test. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. The damaged material to be removed by grinding. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Check that all crevices are removed before start |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | welding according to PS 026.132 (attached). |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Cleaning and passivation of the stainless steel |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | according to ASTM A 380-99 and ASTM A 967-01. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New stainless liners in for and aft Bow Thruster. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New stainless steel liners |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Materials |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preparation for SOW |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fireguard |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Crane & forklift |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. NDT |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Paint works |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price, each thruster tunnel: DKK: 212.300,- | VOR 1 | 1 | 424600 | 424600 | 0 | 0 | 0 | 0 | 0 | 424600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Same work scope as Ark Germania VOR4. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add WJ2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepare Wencon, 17 sets |  | 1 | 49800 | 0 | 49800 | 0 | 0 | 0 | 0 | 49800
1092 | 3811.05 | Upgrade of obsolete thruster control system
|  | Assistance to service engineer, each day | INCL. 1106 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1093 | 4201.01 | External contractors - INFO ONLY
|  | External contractors - INFO ONLY | INFO | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1094 | 4201.02 | Renewal of mushrooms in scrubbers
|  | Possible assistance to owners specialist to be priced, TRANSPORT |  | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
|  | after agreement of work scope |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Powersupply |  | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
1095 | 2701.03A | Cargo Vent Room steel sheet renewal
|  | Cut out corroded plate at bottom of ventilation ducts in 3 locations. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation of 1,5 mm galv. Steel plating for same. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Approx. 2 m3 in each location | QUOTED | 1 | 25400 | 25400 | 0 | 0 | 0 | 0 | 0 | 25400
|  | Access | ++ | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1097 | 3339.05A | Overboard pipe for boiler blowdown
|  | Renewal of pipe based on pictures | QUOTED | 1 | 28740 | 28740 | 0 | 0 | 0 | 0 | 0 | 28740
1098 | 3341.01A | Engine Room Ventilation ME PS 1B
|  | Change of bearings in el-motor (Based max 25 KW) | QUOTED | 1 | 24200 | 24200 | 0 | 0 | 0 | 0 | 0 | 24200
|  | Subject to free access and excl. Possible staging |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scaffolding | CANCELLED | 0 | 10200 | 10200 | 0 | -10200 | 0 | 0 | 0 | 0
|  | Cherrypicker, each per day - 1/2 +1/2 day | QUOTED | 1 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 3500
|  | Forklift, each hour | QUOTED | 3 | 1000 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000
1099 | 3339.04A | Outlet pipe for Drencher pump #2
|  | New pipe as specified | QUOTED | 1 | 35760 | 35760 | 0 | 0 | 0 | 0 | 0 | 35760
1100 | # 1115 | Installation of tanks for bow thrusters
|  | Installation of 4 pcs. Tanks for bow thrusters |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Building of foundation for tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Installation of tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Pipework |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Materials | QUOTED | 1 | 71250 | 71250 | 0 | 0 | 0 | 0 | 0 | 71250
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Adjusting of pipe, installing additional supper and modification of floor plate | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting | QUOTED | 1 | 32175 | 32175 | 0 | 0 | 0 | 0 | 0 | 32175
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Delivery of tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1101 | # 1117 | Installation of CJC filters for bow thrusters
|  | Installation of 2 pcs. CJC filter for bow thruster |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Foundation |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Installation of filters |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Pipework |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Materials | QUOTED | 1 | 63750 | 63750 | 0 | 0 | 0 | 0 | 0 | 63750
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Installation of additional valves | QUOTED | 1 | 15600 | 15600 | 0 | 0 | 0 | 0 | 0 | 15600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. Delivery of filters |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Additional cost based experience from Ark Germania | QUOTED | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
|  | Credit due to crew work |  | 1 | -50000 | 0 | -50000 | 0 | 0 | 0 | 0 | -50000
1102 | # 1119 | Installation of CJC filters for sterntube
|  | Installation of CJC filters for PS and SB sterntube |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Piping and brackets |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Installation fo tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Materials | QUOTED | 1 | 58500 | 58500 | 0 | 0 | 0 | 0 | 0 | 58500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Painting | QUOTED | 1 | 14284 | 14284 | 0 | 0 | 0 | 0 | 0 | 14284
|  | Excl. Foundations for filters. To be installed at existing foundations |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add. Correction of in/out let |  | 1 | 2550 | 0 | 0 | 2550 | 0 | 0 | 0 | 2550
1103 | # 1125 | Painting of lanterns
|  | Painting of lanterns | QUOTED | 1 | 14000 | 14000 | 0 | 0 | 0 | 0 | 0 | 14000
1104 | # 1126 | Painting of ventilation grids
|  | Ventilation of ventilation grids, 12 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 x FC |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lift | CANCELLED | 0 | 46800 | 46800 | 0 | -46800 | 0 | 0 | 0 | 0
1105 | # 1128 | Loadtest of padeye BWTS
|  | Loadtest of padeye BWTS | QUOTED | 1 | 9100 | 9100 | 0 | 0 | 0 | 0 | 0 | 9100
1106 |  | El-works:
|  | We use existing cable trays and mounting 10m 400mm cable ladder according |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | to specification .And we expect that all existing cables is mounted according to |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Routing of cables general requirements Appendix B.2 chapter 2 in |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | specifications. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable type there is calculated in this is attach this offer | QUOTED | 1 | 251280 | 251280 | 0 | 0 | 0 | 0 | 0 | 251280
|  | Please note delivery time for cables: approx. 14 days from order |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dis- and remounting of ceiling for access, 51 m2 | QUOTED | 1 | 47750 | 47750 | 0 | 0 | 0 | 0 | 0 | 47750
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conversion of thruster switchboards 2 pcs. | QUOTED | 1 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 10800
|  | Correction of drawings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Kongsberg Delivers: pepperl + fuchs type kfa6-sr2-ex1.w.lb |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possible add net CAT cable | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Assistance, each man per 12 hour shift | QUOTED | 5 | 8500 | 0 | 42500 | 0 | 0 | 0 | 0 | 42500
1107 | 2701.02A | Ventilation duct - rope store fwd
|  | Dismounting of existing 400x400 mm ducting, delivery |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | and installation of 2 pcs. Straight sections, 1 pcs. Section with |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | outlet grid in bottom and 2 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | bends. All in 1 mm galv. Plating | QUOTED | 1 | 53750 | 53750 | 0 | 0 | 0 | 0 | 0 | 53750
1108 |  | Botton plug
|  | Bottom plugs removed/refitted, each |  | 33 | 1000 | 33000 | 0 | 0 | 0 | 0 | 0 | 33000
|  | Possible vaccumtest, each |  | 0 | 500 | 16500 | 0 | 0 | 0 | 0 | -16500 | 0
|  | Possible cement removal, each | CANCELLED | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Posible recementing, each | CANCELLED | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Possibel fabrication of new bottom plugs in SS material, each | CANCELLED | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1109 | 1317.04A | Change of bearings aft ramp PS & SB
|  | Crane assistance to MacGregor for removal/refitting ramps |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | each normal hour | ++ | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigger assistance and further assistance to MacGregor |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | each person per 12 hour shift |  | 0 |  | 223128 | -121047 | 0 | -102081 | 0 | 0 | 0
|  | According to timesheet 10-06-2024 |  | 1 | 21225 | 21225 | 0 | 0 | 0 | 0 | 0 | 21225
|  | According to timesheet 11-06-2024 |  | 1 | 20800 | 20800 | 0 | 0 | 0 | 0 | 0 | 20800
|  | According to timesheet 12-06-2024 |  | 1 | 109347 | 109347 | 0 | 0 | 0 | 0 | 0 | 109347
|  | According to timesheet 13-06-2024 |  | 1 | 25500 | 25500 | 0 | 0 | 0 | 0 | 0 | 25500
|  | According to timesheet 17-06-2024 |  | 1 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000
|  | According to timesheet 18-06-2024 |  | 1 | 48025 | 0 | 48025 | 0 | 0 | 0 | 0 | 48025
|  | According to timesheet 19-06-2024 |  | 1 | 70022 | 0 | 70022 | 0 | 0 | 0 | 0 | 70022
|  | According to timesheet 24-06-2024 |  | 1 | 39422 | 0 | 0 | 0 | 39422 | 0 | 0 | 39422
|  | According to timesheet 25-06-2024 |  | 1 | 2250 | 0 | 0 | 0 | 2250 | 0 | 0 | 2250
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication, delivery and installation of 7 pcs. Bushings for support hinges. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material JM 7/3. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Measurement accordin gto received spec.: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Inner diameter: 155 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Outer diameter: 175 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Length: 120 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl.: On-site measuring before fabrication and installation of bushings. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. liftrs for access | QUOTED | 1 | 184815 | 184815 | 0 | 0 | 0 | 0 | 0 | 184815
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excl. possible accesswork, possible fabrication of special tools, |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | possible "Line drilling", painting of new and touched and removal |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | of old bushings |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1110 |  | Canteen for crew Sunday 16-06. 10 persons
|  | Canteen for crew Sunday 16-06. 10 persons | QUOTED | 10 | 125 | 0 | 1250 | 0 | 0 | 0 | 0 | 1250
1111 |  | Installation of cable penetration for VDR
|  | Penetration and panel VDR |  | 1 | 13800 | 0 | 13800 | 0 | 0 | 0 | 0 | 13800
1112 |  | Arrange and rental of heating blowers 32kW
|  | Arrange and rental of heating blowers 32kW |  | 1 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000
1113 |  | Drilling holes in thruster housing
|  | Same scope as Ark Germanica | QUOTED | 1 | 119500 | 0 | 119500 | 0 | 0 | 0 | 0 | 119500
1114 | VOR 3 | Pins for Stern Ramps 11pcs.
|  | Machining of greasing resesses. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining for treading (M30/80mm) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | General alignment machining of pins. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transporting to and from ship toi workshop. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price: | VOR 3 | 1 | 56925 | 0 | 56925 | 0 | 0 | 0 | 0 | 56925
1115 |  | Assistance/scaffolding for ScanUnit.
|  | Assistance/scaffolding for ScanUnit. |  | 1 | 26800 | 0 | 26800 | 0 | 0 | 0 | 0 | 26800
1116 |  | Assistance for loosen of bitter-end SB/PS
|  | Assistance for loosen of bitter-end SB/PS |  | 1 | 23800 | 0 | 23800 | 0 | 0 | 0 | 0 | 23800
1117 |  | Repair of thruster blades – cavitation holes
|  | Repair of thruster blades – cavitation holes | NET PRICE | 1 | 131780 | 0 | 131780 | 0 | 0 | 0 | 0 | 131780
|  | Transport to/from Marine Shaft |  | 1 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 18000
1118 | VOR 7 | Ceiling plates 4 pcs
|  | Change of advised 4 plates | VOR 7 | 1 | 16000 | 0 | 16000 | 0 | 0 | 0 | 0 | 16000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cherry picker 1 day | VOR 7 | 1 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500
1119 | VOR 4 | Manhole for Ballast Water Tank 14. - 1 piece
|  | Prepare SOW | VOR 4 | 1 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 8000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation of manhole cover (600x800) | VOR 4 | 1 | 27800 | 0 | 27800 | 0 | 0 | 0 | 0 | 27800
|  | Based on Crew to stand fire watch in Ballast Tank. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excluding posssible supports, paint works and access. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1120 | VOR 6 | Machining of 17 pins for Lower Deck Ramp
|  | Including: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Materials for the pins. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining of greasing resesses. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machining of 1/4'' BSP for grease niples. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 17 pcs. grease niples. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price in total: | VOR 6 | 1 | 67575 | 0 | 67575 | 0 | 0 | 0 | 0 | 67575
1121 |  | Painting of marks on rudder stocks and rudder trunks
|  | Wash with soap |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chemical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 x TU coat |  | 1 | 13000 | 0 | 13000 | 0 | 0 | 0 | 0 | 13000
1122 | VOR 5 | Cleaning of vent. Pipes for Leak Oil Tank and Separators
|  | Job includes: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 openings/cuts for cleaning access. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Openings to be closed with Straub couplings. (x2) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of the pipes with sieving belt or similar. |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Price in total: | VOR 5 | 1 | 24040 | 0 | 24040 | 0 | 0 | 0 | 0 | 24040
|  | Excluding: |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Potential more drastic measures for unclogging the pipes! |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | (More openings, chemicals, suction etc.) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1123 |  | Cleaning of cylinder for FFB - old paint
|  | Cleaning of 2 pcs. cylinders |  | 1 | 12220 | 0 | 12220 | 0 | 0 | 0 | 0 | 12220
1124 |  | Installation of pipe between pump and
|  | scrupper pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material: Stainless steel pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Valve |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Incl. Pipe brackets |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total price | QUOTED | 1 | 18880 | 0 | 0 | 18880 | 0 | 0 | 0 | 18880
|  | Excl. Painting |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1125 |  | Insert in beam SB side on Main deck and
|  | 1 add. stiffner |  | 1 | 25720 | 0 | 0 | 25720 | 0 | 0 | 0 | 25720
1126 |  | Cleaning of Blue Top Side (overspray)
|  | Cleaning of Blue Top Side (overspray) |  | 1 | 11250 | 0 | 0 | 0 | 11250 | 0 | 0 | 11250
|  | Lift, each |  | 2 | 3500 | 0 | 0 | 0 | 7000 | 0 | 0 | 7000
1127 |  | Service boat
|  | Service boat - 27-06-2024 |  | 1 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 18000
1128 |  | Ropeguard + Bolts/nuts for Sea Chests + TU paint
|  | Ropeguard + Bolts/nuts for Sea Chests + TU paint |  | 1 | 23000 | 0 | 0 | 0 | 23000 | 0 | 0 | 23000
1132 |  | XX
|  | XX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1133 |  | XX
|  | XX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1134 |  | XX
|  | XX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000
9993 |  | Discount according to agreement
|  | Discount according to agreement | 15% | 1 | -2385841.362 | -2348185 | -105185 | 65752 | -3128 | -2775 | 7680 | -2385841
9995 |  | PO: ADAN24029301 - Down payment |  | 1 | -8688469 | 0 | 0 | -8688469 | 0 | 0 | 0 | -8688469
|  |  | DKK |  |  | 13303834 | 757229 | -9061063 | -175 | 15725 | -25620 | 4989930 | 0

## Chapter 50
Ship name: |  | ARK DANIA
Case No.: |  | 231218
Currency: | DKK | Chapter 50 |  |  |  | Estimate | New/changes | New/changes | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2024-06-14 | 2024-06-20 | 2024-06-24 | 2024-06-26 | 2024-06-27 | 2025-05-06 | Total
1023 | 1001.03 | AL 15 (1,5 kg), each |  | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 25 (2,5 kg), each |  | 0 | 430 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 43 (4,3 kg), each |  | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 114 (11,4 kg), each |  | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AL 170 (17,0 kg), each |  | 0 | 1295 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1042 | 1108.01 | Mechanical cleaning where cyclone cleaning is not possible, each m2 |  | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Marking of edges, each meter |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1096 | 3149.01A | Main Engine Top bracing
|  | Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129 |  | XX
|  | XX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1130 |  | XX
|  | XX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1131 |  | XX
|  | XX |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 |  | Repair of damaged propeller blade (KGN)
|  | Repair of damaged propeller blade (KGN) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8002 |  | Repair of electrical connection box in dock
|  | Repair of electrical connection box in dock |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
8003 |  | Repair of hand rails – PS Stern Ramp
|  | Repair of hand rails – PS Stern Ramp |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | DKK |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0