## Chapter 0
Ship name: |  | BEGONIA SEAWAYS
Case No.: |  | 241107
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2024-07-19 | 2024-07-24 | 2024-07-30 | 2025-05-06 | Total
1000 |  | Sag
1001 | 200.01 | Drydocking
|  | A. Dock/undock and first day dues | QUOTED | 1 | 55000 | 55000 | 0 | 0 | 0 | 55000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | B. Cost for subsequent days, each day 16/7-31/7 | QUOTED | 15 | 35000 | 630000 | 0 | -105000 | 0 | 525000
1003 | 500.12 | Earthing of the vessel
|  | Earthing of the vessel: Included in docking price | INCL. | 0 |  | 0 | 0 | 0 | 0 | 0
1004 | 500.34 | Crane assistance
|  | Handling of spares/parts before arrival | QUOTED | 1 | 55000 | 55000 | 0 | 0 | 0 | 55000
|  | Cranes assistance (Max 45 T), each normal hour |  | 0 |  | 170000 | -70000 | -100000 | 0 | 0
|  | According to timesheet per 17/7-24 | QUOTED | 1 | 7250 | 7250 | 0 | 0 | 0 | 7250
|  | According to timesheet per 18/7-24 | QUOTED | 1 | 3700 | 3700 | 0 | 0 | 0 | 3700
|  | According to timesheet per 21/7-24 | QUOTED | 1 | 6300 | 0 | 6300 | 0 | 0 | 6300
|  | According to timesheet per 24/7-24 | QUOTED | 1 | 4700 | 0 | 0 | 4700 | 0 | 4700
|  | According to timesheet per 26/7-24 | QUOTED | 1 | 6850 | 0 | 0 | 6850 | 0 | 6850
1005 | 500.04 + 500.07 | Temporary fire connections
|  | A. Temporary fire connections, each | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 16 | 1500 | 27000 | 0 | -3000 | 0 | 24000
1006 | 500.08 | CO2 plant
|  | Isolation/reconnection of CO2 plant | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1007 |  | Stock supply
|  | Stock supply | QUOTED | 1 | 30000 | 100000 | 0 | -70000 | 0 | 30000
1008 |  | Isolation
|  | Isolation | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
1009 | 500.23 | Garbage disposal
|  | Garbage containers (4 m³) on the quay |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each time emptied incl. disposal |  | 0 | 5000 | 125000 | -50000 | -75000 | 0 | 0
|  | 3 x container 17/7-24 | QUOTED | 3 | 5000 | 15000 | 0 | 0 | 0 | 15000
|  | 3 x container 24/7-24 | QUOTED | 3 | 5000 | 0 | 15000 | 0 | 0 | 15000
|  | 3 x steel container | QUOTED | 3 | 8000 | 0 | 40000 | -16000 | 0 | 24000
|  | 1 x container 28/7 | QUOTED | 1 | 5000 | 0 | 0 | 5000 | 0 | 5000
|  | 1 x container 30/7 | QUOTED | 1 | 5000 | 0 | 0 | 5000 | 0 | 5000
1010 |  | Cleaning of dock before departure
|  | See job 1052 |  | 0 |  | 0 | 0 | 0 | 0 | 0
1011 | 500.06 | Gangways
|  | A. Installation/removal, each | QUOTED | 2 | 4000 | 8000 | 0 | 0 | 0 | 8000
|  | B. Daily hire charge, included in installation price. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gangway after undocking | QUOTED | 2 | 4000 | 0 | 0 | 8000 | 0 | 8000
1012 | 500.09 | Cooling water for auxiliary engines
|  | Connection/disconnection, each | QUOTED | 2 | 3000 | 6000 | 0 | 0 | 0 | 6000
|  | Each line per day in service | QUOTED | 32 | 1500 | 54000 | 0 | -6000 | 0 | 48000
1013 | 500.26 | Water supply
|  | A. Connection/disconnection of hose, each | QUOTED | 2 | 3000 | 6000 | 0 | 0 | 0 | 6000
|  | B. Fresh water per m³ | QUOTED | 72 | 45 | 13500 | 0 | -6750 | -3510 | 3240
|  | C. Technical water for boilers per m³, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Estimated price per m³ as daily price will need |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to be aquired from supplier after information |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of total amount of m³ needed is known. | OWNER | 0 |  | 0 | 0 | 0 | 0 | 0
1014 | 500.20 + 500.21 | Black/grey water disposal
|  | A. Connection/disconnection, each | QUOTED | 4 | 4000 | 16000 | 0 | 0 | 0 | 16000
|  | B. Black/grey water disposed per m³ | QUOTED | 86 | 95 | 17100 | 0 | 0 | -8930 | 8170
|  | Mudtruck, each normal hour | QUOTED | 72 | 1150 | 82800 | 0 | 0 | 0 | 82800
|  | Placing of external collection tank in dry dock, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each tank | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  | Average 3-4 hours / 9-10 m³ per day |  | 0 |  | 0 | 0 | 0 | 0 | 0
1015 | 500.22 | Oily water disposal
|  | A. Connection/disconnection, each | JOB 1074 | 0 | 4000 | 8000 | 0 | -8000 | 0 | 0
|  | 17/7 x 2 for tk. 85 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | B. Oil/water mixture discharged and disposed: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vacuum truck, each hour - per 17/7-24 | JOB 1074 | 0 | 1150 | 13800 | 0 | -13800 | 0 | 0
|  | Disposal, each m³ - per 17/7-24 | JOB 1074 | 0 | 1200 | 22200 | 0 | -22200 | 0 | 0
1017 | 500.24 | Ballast water supply
|  | A. Connection/disconnection of Ballastwater, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each hose | CANCELLED | 0 | 2000 | 4000 | 0 | -4000 | 0 | 0
|  | B. Supply of sea ballast water, each m³ | QUOTED | 1000 | 8 | 16000 | 0 | -8000 | 0 | 8000
|  | Further assistance when ballasting: As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
1018 | 500.14 | Gas free certificates
|  | A. For initial visit - Gas free certificate | QUOTED | 1 | 3500 | 3500 | 0 | 0 | 0 | 3500
|  | B. For subsequent visit, each - Per 25/7 | QUOTED | 3 | 3500 | 52500 | 0 | -42000 | 0 | 10500
|  | Please note that 1 certificate can cover multible |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | areas/compartments |  | 0 |  | 0 | 0 | 0 | 0 | 0
1019 | 500.01 | Wharfage fee
|  | Each day - 31/7-6/8 | QUOTED | 7 | 16000 | 64000 | 0 | 48000 | 0 | 112000
1020 | 500.02 | Movement of vessel
|  | A. Tugs for movement of vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account according to valid harbour tariffs | VIA AGENT | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | B. Line handlers for movement of vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Included in docking price |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | C. Pilot for movement of vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account according to valid harbour tariffs | VIA AGENT | 0 |  | 0 | 0 | 0 | 0 | 0
1021 | 500.03 | Fire watch
|  | Normally incl. In jobs with hot-work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additional watchduty: To be agreed upon | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1022 | 500.05 | Watch keeping
|  | Not needed as yard is placed inside ISPS area |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with 24/7 manned gate |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additional watchduty: To be agreed upon | INFO | 0 |  | 0 | 0 | 0 | 0 | 0
1023 | 500.11 | Bottom plugs
|  | A. Plug off and on, each | QUOTED | 31 | 200 | 6200 | 0 | 0 | 0 | 6200
|  | B. Vacum test | QUOTED | 31 | 200 | 6200 | 0 | 0 | 0 | 6200
1024 | 500.13 | Man hole covers
|  | A. Manhole cover, each | BY CREW | 0 | 950 | 0 | 0 | 0 | 0 | 0
|  | Based on MAX size 600*800mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | B. Installation of protection on opened manhole, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per manhole | BY CREW | 0 | 1500 | 22500 | -22500 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | C. Renewal of gaskets, each | BY CREW | 0 | 300 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | D. Repair of studs: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | By drilling out, min. 5 pcs. per manhole, each | CANCELLED | 0 | 275 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renting barrier for covers | QUOTED | 40 | 200 | 8000 | 0 | 0 | 0 | 8000
1025 | 500.15 | Ventilation fans
|  | A. Connection/disconnection: As per account | CANCELLED | 0 | 20000 | 20000 | -20000 | 0 | 0 | 0
|  | B. Fan, including power, each fan per day | CANCELLED | 0 | 600 | 12000 | -12000 | 0 | 0 | 0
1037 | 500.33 | Cherry picker & scissorlift
|  | A+B+C. Rental Cherry picker or scissorlift per. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 12 hour shift, excl. driver, each per day | QUOTED | 1 | 3500 | 17500 | 0 | -14000 | 0 | 3500
|  | Driver, each normal hour | CANCELLED | 0 | 400 | 0 | 0 | 0 | 0 | 0
1041 | 500.40 | Securing of stern ramp
|  | Crane assistance to crew for securing of stern ramp, | QUOTED | 1 | 18900 | 18900 | 0 | 0 | 0 | 18900
|  | Assistance to crew additional to crane assistance, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | see hourly rates item 520,15 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Reduction (only preperation of gangside for ramp) |  | 1 | -8900 | 0 | 0 | -8900 | 0 | -8900
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Protection of 2 pcs. of hydraulic cylinders |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | including access | BY CREW | 0 | 5850 | 5850 | -5850 | 0 | 0 | 0
1043 | 1001.01 | Corrosion prevention anodes
|  | Work order Fitting of corrosion prevention |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | anodes (owner supplied) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Change of owner supplied Alu. anodes: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AL 15 (1,5 kg.), each | QUOTED | 57 | 320 | 18240 | 0 | 0 | 0 | 18240
|  | AL 60 (6,0 kg.), each | QUOTED | 18 | 645 | 28380 | -16770 | 0 | 0 | 11610
|  | AL 114 (11,4 kg.), each | QUOTED | 18 | 860 | 15480 | 0 | 0 | 0 | 15480
|  | Incl. cherry picker, demounting of old, mounting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of new, welded type, basis min. 50 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1044 | 1001.02 | ICCP system
|  | Asisstants to Owners service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rental of Cherry picker, each per day | CANCELLED | 0 | 3500 | 7000 | 0 | -7000 | 0 | 0
|  | Driver for cherry picker, each normal hour | CANCELLED | 0 | 400 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each man per 12 hour day shift | CANCELLED | 0 | 8500 | 17000 | -17000 | 0 | 0 | 0
|  | Change of ICCP ref. anodes, each | CANCELLED | 0 | 13090 | 26180 | -26180 | 0 | 0 | 0
|  | Change of ICCP main anodes, each | CANCELLED | 0 | 23980 | 47960 | -47960 | 0 | 0 | 0
1045 | 1001.03 | Antifouling anodes
|  | Work order Antifouling anodes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 6 pcs. Anodes in sea chest to be replaced. | QUOTED | 6 | 4937 | 29622 | 0 | 0 | 0 | 29622
|  | 1 pcs. Cu anod in seachest for emg. fire pump | QUOTED | 1 | 4937 | 4937 | 0 | 0 | 0 | 4937
|  | 1 pcs anodes to be de and remonted again |  | 1 | 4937 | 0 | 0 | 9874 | -4937 | 4937
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible opening/closing of gratings for access, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each | CANCELLED | 0 | 1980 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Supports for anodes fabricated and mounted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | upper/lower seachest, 2 pcs. | CANCELLED | 0 | 17180 | 34360 | 0 | -34360 | 0 | 0
1046 | 1001.05 | Heavy weather damage forward starboard side
|  | Work order Heavy weather damage forward |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | starboard side |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel damage in rope store forward starboard |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to be repaired. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for steel in 10mm thickness, steel type A36. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 261 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. insert 900x1700mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. insert 900x1500mm (deleted) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. triangle support 900x700mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 pcs. additional supports/reinforcements 620x140mm - |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (one more additional) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 265 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. insert 900x1100mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Up to 1484 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine, Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on cleaned & empty area ready for hot work | QUOTED | 1 | 151000 | 151000 | 0 | 0 | 0 | 151000
|  | Excl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs insert deleted, 1 pcs support added - Reduction |  | 1 | -10000 | 0 | -10000 | 0 | 0 | -10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & 4x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu with roller and brush. Of above steel repair | QUOTED | 1 | 24400 | 24400 | 0 | 0 | 0 | 24400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1047 | 1001.06 | Hull damage starboard frame 160
|  | Work order Hull damage starboard frame 160 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renewal of 3 m² shell plate. Plate thickness |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 12,5mm, steel AH36. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Budget cost: | QUOTED | 1 | 112000 | 112000 | 0 | 0 | 0 | 112000
|  | Shell plate approx. 1,5 x 2 x 12,5mm = 300kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of shell plate |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, cherry picker, fire guard, MPI & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vacuum test. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on cleaned and empty tanks ready for hotwork |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. painting & staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New scope: Welding up 3 areas - Reduction |  | 1 | -55000 | 0 | -55000 | 0 | 0 | -55000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
|  | TU painting after steel work outside | CANCELLED | 0 | 15000 | 0 | 15000 | -15000 | 0 | 0
1048 | 1001.07 | Crack in ramp structure from upper to weather deck
|  | Work order Crack in ramp structure from upper |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to weather deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cracks (2pcs) in structure below ramp from |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | upper deck to weather deck frame 153 in two |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | positions to be repaired. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 153 thickness: 10mm, steel A36 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crack repaired by inserts 300 x 300 mm | QUOTED | 2 | 15000 | 30000 | 0 | 0 | 0 | 30000
|  | Based on all area is ready for hot work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New brackets between upper deck and existing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | brackets to be fabricated and welded. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Approximately size 530 x 400 mm, thickness |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 10mm. (2pcs) | QUOTED | 2 | 20000 | 40000 | 0 | 0 | 0 | 40000
|  | Based on all area is ready for hot work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & 4x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu with roller and brush. Of above steel repair | QUOTED | 1 | 12500 | 12500 | 0 | 0 | 0 | 12500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mobile staging for access below weather deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for access | QUOTED | 1 | 5000 | 5000 | 0 | 0 | 0 | 5000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1049 | 1001.08 | Steel indent main deck at frame 193-197
|  | starboard side |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Work order Shell indent main deck frame 193-197 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | starboard side |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1. Shell plate size 3000 mm x 800 mm x 12,5 mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36TM |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2. Shell plate size 3000 mm x 800 mm x 12,5mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36TM |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3. Longitudinal stifner of 3000 mm x 250 mm x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 15 mm, steel A36TM |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, cherry picker, fire guard, MPI & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vacuum test. | CANCELLED | 0 | 147000 | 147000 | -147000 | 0 | 0 | 0
|  | Based on cleaned and empty tanks ready for hotwork |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. painting & staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | CANCELLED | 0 | 12500 | 12500 | -12500 | 0 | 0 | 0
1050 | 1001.09 | Cracks in shell and longitudinal reinforcement
|  | plates |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Work order Cracks in shell and longitudinal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reinforcement plates |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vertical welding to be cropped out and longitudinal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | welding’s (upper and lower) to be cropped out for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | about 1 meter on each side of the vertical welding. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each place | CANCELLED | 0 | 29500 | 29500 | -29500 | 0 | 0 | 0
|  | Subject to free access for hot work and excl. cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and painting of new and affected area. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional in shell acc. to steel foreman | CANCELLED | 0 | 75000 | 75000 | -75000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | CANCELLED | 0 | 12500 | 12500 | -12500 | 0 | 0 | 0
|  | Inspection of cracks |  | 1 | 4250 | 0 | 8500 | -4250 | 0 | 4250
1051 | 1001.10 | VS6 port side damage
|  | Work order VS6 port side damage |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 117 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. insert 2000x900mm, thickness 10mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 116.40 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. insert 1500x900mm, thickness 11,5mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. insert 1500x900mm, thickness 12,5mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. flatbar 250x1500, thickness 15mm, steel A36 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | QUOTED | 1 | 126900 | 126900 | 0 | 0 | 0 | 126900
|  | Based on cleaned and empty tanks ready for hotwork |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. painting & staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional due to larger scope | QUOTED | 1 | 150000 | 150000 | 0 | 0 | 0 | 150000
|  | 2 pcs 2400 x 900 inserts + 1500 mm bulb 280 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | +2550 + 1200 +1400 +250 + 6 x HP 2120+ 280 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & 4x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu with roller and brush. Of above steel repair | QUOTED | 1 | 24400 | 24400 | 0 | 0 | 0 | 24400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging for access | QUOTED | 1 | 22500 | 80000 | 0 | -57500 | 0 | 22500
|  | Fixed price after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1052 | 1002.01 | Bottom treatment and paint
|  | WJ-2 cleaning underwater hull of existing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | silicone paint system: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom area: 2900 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Flat bottom area: 4106 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Flat bottom area: 4106 m²: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP- wash of existing silicone paint | QUOTED | 4106 | 22 | 90332 | 0 | 0 | 0 | 90332
|  | Mechanical cleaning, based 10% | QUOTED | 411 | 106 | 43524 | 0 | 0 | 0 | 43524
|  | Hosing down with FW | QUOTED | 4106 | 3.75 | 15398 | 0 | 0 | 0 | 15398
|  | 1 x TU, based 15% | QUOTED | 616 | 11.5 | 7083 | 0 | 0 | 0 | 7083
|  | 1 x TU, based 15% (Silicone paint) | QUOTED | 616 | 23 | 14166 | 0 | 0 | 0 | 14166
|  | 1 x TU, based 15% (Silicone paint) | QUOTED | 616 | 23 | 14166 | 0 | 0 | 0 | 14166
|  | 1 x TU, based 15% (Silicone paint) | QUOTED | 616 | 23 | 14166 | 0 | 0 | 0 | 14166
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom area: 2750 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP- wash of existing silicone paint | QUOTED | 2750 | 24 | 69600 | -3600 | 0 | 0 | 66000
|  | Wj-2 cleaning, based 650 m² | QUOTED | 650 | 180 | 117000 | 0 | 0 | 0 | 117000
|  | Mechanical cleaning, min. 0,25 m² per spot |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | based 3% |  | 83 | 113.5 | 9875 | -511 | 0 | 0 | 9364
|  | Hosing down with FW | QUOTED | 2750 | 4 | 11600 | -600 | 0 | 0 | 11000
|  | 1 x TU, based 8% | QUOTED | 220 | 15.25 | 3538 | -183 | 0 | 0 | 3355
|  | 1 x TU, based 8% (Silicone paint) | QUOTED | 220 | 30.5 | 7076 | -366 | 0 | 0 | 6710
|  | 1 x TU, based 8% (Silicone paint) | QUOTED | 220 | 30.5 | 7076 | -366 | 0 | 0 | 6710
|  | 1 x TU, based 8% (Silicone paint) | QUOTED | 220 | 30.5 | 7076 | -366 | 0 | 0 | 6710
|  | 1 x FC | QUOTED | 650 | 10.5 | 0 | 0 | 6825 | 0 | 6825
|  | 1 x FC(Silicone paint) | QUOTED | 650 | 21 | 0 | 0 | 13650 | 0 | 13650
|  | 1 x FC(Silicone paint) | QUOTED | 650 | 21 | 0 | 0 | 13650 | 0 | 13650
|  | 1 x FC(Silicone paint) | QUOTED | 650 | 21 | 0 | 0 | 13650 | 0 | 13650
|  | Marking up water line, 492 meter | QUOTED | 391 | 12.75 | 6273 | -1288 | 0 | 0 | 4985
|  | Washdown of hull | ++ | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rudder area: 47 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 47 | 11.5 | 541 | 0 | 0 | 0 | 541
|  | Mechanical cleaning, min. 0,25 m² per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 9,4 m² | QUOTED | 9 | 113.5 | 1067 | 0 | 0 | 0 | 1067
|  | Wash down with FW | QUOTED | 47 | 4 | 188 | 0 | 0 | 0 | 188
|  | Tu 1 coat, min. 0,25 m²/spot, basis 20%, 9,4 m² | QUOTED | 9 | 15.25 | 143 | 0 | 0 | 0 | 143
|  | Tu 1 coat, min. 0,25 m²/spot, basis 20%, 9,4 m² | QUOTED | 9 | 15.25 | 143 | 0 | 0 | 0 | 143
|  | Full coat 100 µm - HEMPASIL NEXUS, Light |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | grey (silicone paint) | QUOTED | 47 | 21 | 987 | 0 | 0 | 0 | 987
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional costs for silicone treatment: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering of topside against overspray | QUOTED | 1 | 30000 | 30000 | 0 | 0 | 0 | 30000
|  | Destroyed paint hoses due to silicone paint | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vertical sides underneat the fender list and 1,8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | meters down and thruster tunnels are to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | repainted with HEMPELS ANTIFOULING |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | GLOBIC 9000 (traditional anti fouling). |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Vertical bottom area for traditional antifouling: 650 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 650 | 11.5 | 5750 | 1725 | 0 | 0 | 7475
|  | Wj-2 cleaning, based 150 m² | QUOTED | 150 | 180 | 27000 | 0 | 0 | 0 | 27000
|  | Mechanical cleaning, min. 0,25 m² per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 5%, 32,5 m² | QUOTED | 33 | 113.5 | 2838 | 851 | 0 | 0 | 3689
|  | Wash down with FW | QUOTED | 650 | 4 | 2000 | 600 | 0 | 0 | 2600
|  | Tu 1 coat, min. 0,25 m²/spot, basis 10% | QUOTED | 65 | 15.25 | 763 | 229 | 0 | 0 | 991
|  | Tu 1 coat, min. 0,25 m²/spot, basis 10% | QUOTED | 65 | 15.25 | 763 | 229 | 0 | 0 | 991
|  | Tu 1 coat, min. 0,25 m²/spot, basis 10% | QUOTED | 65 | 15.25 | 763 | 229 | 0 | 0 | 991
|  | Tu 1 coat, min. 0,25 m²/spot, basis 10% | QUOTED | 65 | 15.25 | 763 | 229 | 0 | 0 | 991
|  | 1 x FC | QUOTED | 150 | 10.5 | 0 | 0 | 1575 | 0 | 1575
|  | 1 x FC(Silicone paint) | QUOTED | 150 | 21 | 0 | 0 | 3150 | 0 | 3150
|  | 1 x FC(Silicone paint) | QUOTED | 150 | 21 | 0 | 0 | 3150 | 0 | 3150
|  | 1 x FC(Silicone paint) | QUOTED | 150 | 21 | 0 | 0 | 3150 | 0 | 3150
|  | Marking up line, 492 meter | QUOTED | 552 | 12.75 | 6273 | 765 | 0 | 0 | 7038
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Thruster tunnels area: 89 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hp wash with 300 bar | QUOTED | 89 | 11.5 | 1024 | 0 | 0 | 0 | 1024
|  | Mechanical cleaning, min. 0,25 m² per spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 50%, 44,5 m² | QUOTED | 45 | 113.5 | 5051 | 0 | 0 | 0 | 5051
|  | Wash down with FW | QUOTED | 89 | 4 | 356 | 0 | 0 | 0 | 356
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 15.25 | 679 | 0 | 0 | 0 | 679
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 15.25 | 679 | 0 | 0 | 0 | 679
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 15.25 | 679 | 0 | 0 | 0 | 679
|  | Tu 1 coat, min. 0,25 m²/spot, basis 50%, 44,5 m² | QUOTED | 45 | 15.25 | 679 | 0 | 0 | 0 | 679
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible Bilge keels blasting: Excl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering of: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Anodes and sensors, each | QUOTED | 96 | 23 | 2208 | 0 | 0 | 0 | 2208
|  | Propellers, each | QUOTED | 5 | 638 | 3190 | 0 | 0 | 0 | 3190
|  | ICCP anodes, each | QUOTED | 6 | 1018 | 6108 | 0 | 0 | 0 | 6108
|  | Drainplugs fitted/removed, each | QUOTED | 33 | 148.5 | 4901 | 0 | 0 | 0 | 4901
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting existing cargo and plimsol, thruster |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and bulp markings marks | QUOTED | 1 | 6232 | 6232 | 0 | 0 | 0 | 6232
|  | Markings for in water survey to be painted. | QUOTED | 1 | 7000 | 14000 | 0 | -7000 | 0 | 7000
|  | Special tape for silicone paint | QUOTED | 1 | 9500 | 9500 | 0 | 0 | 0 | 9500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of dock bottom after WJ, before |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | painting with silicone paint | QUOTED | 1 | 100000 | 100000 | 0 | 0 | 0 | 100000
1055 | 1004.01 | White Topside cleaning and painting
|  | White topside: 3301 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Front of accommodation: 224 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Turtle deck forward: 294 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total area: 3819 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 3525 m² | QUOTED | 3525 | 11.5 | 43919 | 0 | -3381 | 0 | 40538
|  | Mechanical cleaning, min. 0,25 m²/spot, basis |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 15%, 528,75 m² | QUOTED | 529 | 113.5 | 65018 | 0 | -5005 | 0 | 60013
|  | Hosing down with Fw, basis 3525m² | QUOTED | 3525 | 4 | 15276 | 0 | -1176 | 0 | 14100
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 705 m² | QUOTED | 705 | 51 | 38954 | 0 | -2999 | 0 | 35955
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 705 m² | QUOTED | 705 | 51 | 38954 | 0 | -2999 | 0 | 35955
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 705 m² | QUOTED | 705 | 51 | 38954 | 0 | -2999 | 0 | 35955
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 705 m² | QUOTED | 705 | 51 | 38954 | 0 | -2999 | 0 | 35955
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 705 m² | QUOTED | 705 | 51 | 38954 | 0 | -2999 | 0 | 35955
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 20%, 705 m² | QUOTED | 705 | 51 | 38954 | 0 | -2999 | 0 | 35955
|  | Up lining between blue and white area, each meter | QUOTED | 487 | 12.75 | 6209 | 0 | 0 | 0 | 6209
|  | Lift access for inside areas: | QUOTED | 1 | 19800 | 19800 | 0 | 0 | 0 | 19800
|  | Covering, cleaning and painting of windows |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | frames, each | CANCELLED | 0 | 775 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Front accomodation spots |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP wash 300 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanichal cleaning basis 3% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hose down with Fw |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4 x TU with brush and roller basis 10% |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total for above |  | 1 | 19200 | 0 | 0 | 19200 | 0 | 19200
1056 | 1004.02 | Blue Topside cleaning and painting
|  | Blue topside, excluding funnel, total areal: 3984 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 3984 m² | QUOTED | 3984 | 11.5 | 45816 | 0 | 0 | 0 | 45816
|  | Mechanical cleaning, min. 0,25 m²/spot, basis |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 7%, 278,88 m² | QUOTED | 279 | 113.5 | 31653 | 0 | 0 | 0 | 31653
|  | Hosing down with Fw, basis 3984 m² | QUOTED | 3984 | 4 | 15936 | 0 | 0 | 0 | 15936
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 12%, 478,08 m² | QUOTED | 478 | 51 | 24382 | 0 | 0 | 0 | 24382
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 12%, 478,08 m² | QUOTED | 478 | 51 | 24382 | 0 | 0 | 0 | 24382
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 12%, 478,08 m² | QUOTED | 478 | 51 | 24382 | 0 | 0 | 0 | 24382
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 12%, 478,08 m² | QUOTED | 478 | 51 | 24382 | 0 | 0 | 0 | 24382
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 12%, 478,08 m² | QUOTED | 478 | 51 | 24382 | 0 | 0 | 0 | 24382
|  | Up lining between blue and white area, each meter | QUOTED | 391 | 12.75 | 4985 | 0 | 0 | 0 | 4985
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Funnel cleaning and painting, area: 536 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 536 m² | QUOTED | 536 | 16.5 | 8844 | 0 | 0 | 0 | 8844
|  | Mechanical cleaning St3, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 25 m² | QUOTED | 25 | 159.5 | 3988 | 0 | 0 | 0 | 3988
|  | Hosing down with Fw, basis 536 m² | QUOTED | 536 | 4 | 2144 | 0 | 0 | 0 | 2144
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 30 m² | QUOTED | 30 | 51 | 1530 | 0 | 0 | 0 | 1530
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 30 m² | QUOTED | 30 | 51 | 1530 | 0 | 0 | 0 | 1530
|  | Tu 1 coat with roller and brush, min. 0,25 m²/spot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | basis 30 m² | QUOTED | 30 | 51 | 1530 | 0 | 0 | 0 | 1530
|  | Covering off. | QUOTED | 1 | 3900 | 3900 | 0 | 0 | 0 | 3900
|  | Access/staging | QUOTED | 1 | 21384 | 21384 | 0 | 0 | 0 | 21384
|  | Cleaning with chemicals, min. 0,25 m²/spot, each m² |  | 0 | 27.5 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Stern ramp cleaning and painting, area: 744 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Stern ramp total area (outside including all |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | edges): 744 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Anticipate 50% or 372 m² to be WJ-2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-washing with 300 bar, basis 744 m² | QUOTED | 744 | 16.5 | 12276 | 0 | 0 | 0 | 12276
|  | WJ2, min. 0,25 m²/spot, basis 50%, 372 m² | CANCELLED | 0 | 197 | 73284 | -73284 | 0 | 0 | 0
|  | Mechanical cleaning where Wj-2 not possible | QUOTED | 112 | 159.5 | 0 | 17800 | 0 | 0 | 17800
|  | Hosing down with Fw, basis 744 m² | QUOTED | 744 | 4 | 2976 | 0 | 0 | 0 | 2976
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 148,8 m² | QUOTED | 149 | 23 | 8556 | -5134 | 0 | 0 | 3422
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 148,8 m² | QUOTED | 149 | 23 | 8556 | -5134 | 0 | 0 | 3422
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 148,8 m² | QUOTED | 149 | 23 | 8556 | -5134 | 0 | 0 | 3422
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 148,8 m² | QUOTED | 149 | 23 | 0 | 3422 | 0 | 0 | 3422
|  | Touch up 1 coat - HEMPADUR EASY, min 0,25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per spot, based on 148,8 m² | QUOTED | 149 | 23 | 0 | 3422 | 0 | 0 | 3422
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Lift for access | QUOTED | 1 | 18700 | 18700 | 0 | 0 | 0 | 18700
1057 | 1004.03 | Ship name, logo and funnel mark
|  | Painting existing name and homeport | QUOTED | 1 | 6787 | 6787 | 0 | 0 | 0 | 6787
|  | Painting of existing Logo 6000 mm high "DFDS" |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | on port and starboard side | QUOTED | 1 | 39000 | 39000 | 0 | 0 | 0 | 39000
|  | Painting of IMO number | QUOTED | 1 | 970 | 970 | 0 | 0 | 0 | 970
|  | Painting of existing DFDS logo on funnel on |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | port and starboard side | QUOTED | 1 | 11550 | 11550 | 0 | 0 | 0 | 11550
1058 | 1004.04 | Ventilation grids
|  | Grids cleaning and painting: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ventilation grids for cargo fans on upper deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to be dismounted for blasting, galv. 5 pcs. and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | painting. Size: 1500 x 1350 mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bolts and nuts to be renewed where necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each grid: Incl. cherry picker for access. | QUOTED | 2 | 23126 | 46252 | 0 | 0 | 0 | 46252
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bolts and nuts to be renewed where necessary: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | CANCELLED | 0 | 5000 | 15000 | -10000 | -5000 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frames around the ventilation grids: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning and painting of frame in connection |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with removed ventilation grid. Each frame | QUOTED | 2 | 5020 | 10040 | 0 | 0 | 0 | 10040
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Prices based on min. 5 pcs. to be done |  | 0 |  | 0 | 0 | 0 | 0 | 0
1059 | 1004.05 | Bridge wings insulation
|  | Work order Bridge wings insulation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | On area below bridge wings, starboard and port, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | rusty spots are to be mechanical cleaned to St 3. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and afterwards painted according to paint specification |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Area below bridge wings 2 x 3 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 x 2 windows in bridge flooring to be covered |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for protection when cipping and painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access by means of cherry picker included. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treated areas on bridge wings to be coated |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | according to the paint specification: | QUOTED | 1 | 21510 | 21510 | 0 | 0 | 0 | 21510
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount existing insulation and cladding, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | delivery and installation on new insulation and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cladding in 1,5mm stainless steel plate. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Under both PS and SB bridge wing. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access by means of cherry picker included. | QUOTED | 1 | 27000 | 27000 | 0 | 0 | 0 | 27000
1060 | 1005.01 | Becker Rudder clearance
|  | Work order Becker rudder clearence |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access for lower pintle measurement to be cut |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | out. Each plate | CANCELLED | 0 | 14100 | 14100 | -14100 | 0 | 0 | 0
|  | Rudder bearing clearances, with clock guage, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each time | QUOTED | 1 | 7000 | 7000 | 0 | 0 | 0 | 7000
|  | Rudder and Rudder horn drain plugs to be removed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to test for water ingress and re-fitted after check |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | by Owners Representative., each plug | QUOTED | 2 | 1000 | 2000 | 0 | 0 | 0 | 2000
1066 | 1102.02 | Steel renewal Lower hold
|  | Work order Steel renewal Lower hold |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Corroded inner bottom plate between water |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ballast tank 17 and lower hold near longitudinal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | bulkhead to void space 6b to be replaced by |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | insert near frame 111. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Approximately size: 1000 x 500 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Plate thickness: 10,5, steel A36. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard - Incl in job 1140 | JOB 1140 | 0 | 39000 | 39000 | -39000 | 0 | 0 | 0
|  | Based on cleaned and empty tanks ready for hotwork |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. painting & staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for installation of 10 m³ staging | JOB 1140 | 0 | 15000 | 15000 | 0 | -15000 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & 4x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu with roller and brush. Of above steel repair | JOB 1140 | 0 | 6000 | 6000 | 0 | -6000 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | More info needed |  | 0 |  | 0 | 0 | 0 | 0 | 0
1067 | 1102.03 | Deck painting
|  | Lower hold |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total area of Lower hold deck: 1753 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 1440 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Main deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total area of Main deck: 4086 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 635 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Upper deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total area of Upper deck: 3851 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 794 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Weather deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total area of Weather deck: 4705 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Area to be blasted, treated and painted: 331 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total area: 3200 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning by chemical washing | QUOTED | 3200 | 24.5 | 78400 | 0 | 0 | 0 | 78400
|  | Cleaning for water before Cyclon cleaning | QUOTED | 3200 | 66 | 211200 | 0 | 0 | 0 | 211200
|  | Cyclone cleaning SA2 | QUOTED | 3200 | 130 | 416000 | 0 | 0 | 0 | 416000
|  | Cleaning after Cyclon cleaning, before painting | QUOTED | 3200 | 55 | 176000 | 0 | 0 | 0 | 176000
|  | Painting 1 Fc Hempadur Avantguard 750 – 80 µm DFT | QUOTED | 3200 | 13.25 | 42400 | 0 | 0 | 0 | 42400
|  | Painting 1 Fc Hempadur Mastic 45880 – 150 µm DFT | QUOTED | 3200 | 13.25 | 42400 | 0 | 0 | 0 | 42400
|  | HEMPEL'S ANTI-SLINT 67500, Antiskid | QUOTED | 3200 | 9.75 | 31200 | 0 | 0 | 0 | 31200
|  | Painting 1 Fc Hempadur Mastic 45880 – 125 µm DFT | QUOTED | 3200 | 13.25 | 42400 | 0 | 0 | 0 | 42400
|  | Covering off for paint spray | QUOTED | 3200 | 3.5 | 11200 | 0 | 0 | 0 | 11200
|  | Yellow stripes, each meter | CANCELLED | 0 | 44.5 | 0 | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each | QUOTED | 200 | 35 | 7000 | 0 | 0 | 0 | 7000
|  | Lashing pots protection and painting of deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | part of lashing pot, each | QUOTED | 200 | 22 | 4400 | 0 | 0 | 0 | 4400
|  | Lashing pots cleaning, blasting and painting, each | CANCELLED | 0 | 440 | 88000 | -88000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional unit prices: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where Cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible | CANCELLED | 0 | 145 | 14500 | -14500 | 0 | 0 | 0
|  | Hp wash with 300 bar, each m² | QUOTED | 100 | 15.4 | 1540 | 0 | 0 | 0 | 1540
|  | Marking up lines and edges, each meter | BY CREW | 0 | 4.75 | 0 | 0 | 0 | 0 | 0
1068 | 1102.04 | Bimagrip
|  | (HP-wash, covering, mech. Cleaning spot, 3 x TU) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Including: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Locations with 3-5 mm aggregate, each m² | QUOTED | 115 | 575 | 66125 | 0 | 0 | 0 | 66125
|  | Hoistable ramp to upper deck: 25 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ramp to lower hold: 20 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ramp to weather deck: 15 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Center ramp to upper deck: 55 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Locations with 1-3 mm aggregate, each m² | QUOTED | 375 | 575 | 250125 | -34500 | 0 | 0 | 215625
|  | Weather deck spot 100 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Stern ramp: 230 m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tracks from stern ramp to lower hold cover: 355m² |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each | QUOTED | 200 | 35 | 7000 | 0 | 0 | 0 | 7000
|  | Lashing pots protection and painting of deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | part of lashing pot, each | QUOTED | 200 | 22 | 4400 | 0 | 0 | 0 | 4400
|  | Lashing pots cleaning, blasting and painting, each | CANCELLED | 0 | 440 | 88000 | -88000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment Bimagrip, incl.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each m² | QUOTED | 50 | 575 | 0 | 0 | 28750 | 0 | 28750
|  | Owner supplies Acraprime SP, Bimagrip LS and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | aggregate |  | 0 |  | 0 | 0 | 0 | 0 | 0
1071 | 1108.02 | Lashing pots on upper deck
|  | Work order Lashing pots on upper deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation of SAT lashing pot by renewal of new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | owners supplied bottoms (per pcs.) incl. Lift |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for access: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Double type - 2 pcs. | QUOTED | 4 | 16500 | 33000 | 33000 | 0 | 0 | 66000
|  | In general: Subject to free access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. | BY CREW | 0 | 8400 | 16800 | -16800 | 0 | 0 | 0
|  | Subject to free access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | One fire hydrant to be moved so it is accessible |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from the top of the walkway. Allow for cut out |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | in the deck of the walkway | QUOTED | 1 | 28100 | 28100 | 0 | 0 | 0 | 28100
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Old steps to the walkway to be removed. New |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | countersunk steps to be installed according to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | attached drawing. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Handle to be moved. | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
|  | Excl. Painting and access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cherry picker for access, each per day | QUOTED | 3 | 3500 | 0 | 0 | 10500 | 0 | 10500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Owner delivered Control panel for the fire damper |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to be installed at the entrance to the fire station. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for installation of two new cable penetrations. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | More specified infomation is neccesary |  | 0 |  | 0 | 0 | 0 | 0 | 0
1074 | 1111.01 | Sludge and bilge tanks cleaning
|  | Work order Sludge tanks cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Open/cloose manholes including protection |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of manhole, each place | BY CREW | 0 | 2450 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: Each tank |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Sludge tank 81 | CANCELLED | 0 | 8840 | 0 | 0 | 0 | 0 | 0
|  | Dirty oil tank 85 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 8840
|  | Dirty oil Settling tank 87 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 8840
|  | Sludge tank 89 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 8840
|  | Dirty water collecting tank 61 | CANCELLED | 0 | 8840 | 0 | 0 | 0 | 0 | 0
|  | Drain tank 63 | CANCELLED | 0 | 8840 | 0 | 0 | 0 | 0 | 0
|  | Bilge water tank 66 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 8840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible ventilation and gasfreeing of tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account. | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
|  | Possible additional cleaning: To be agreed upon |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | sludge, per m³ | QUOTED | 42 | 1200 | 24000 | 3600 | 22200 | 0 | 49800
|  | Mudtruck, each normal hour | QUOTED | 50 | 1150 | 46000 | -2300 | 13800 | 0 | 57500
|  | Cleaning around manholes and walkways: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gas free certificate. See item 520.16 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional cleaning of tk. 85 agreed 19/7-24 | QUOTED | 1 | 96700 | 100000 | -3300 | 0 | 0 | 96700
1077 | 1111.04 | Vent pipe tank 87
|  | Work order Vent pipe tank 87 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipe be proven clear. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow to cut the pipe 3 places for cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipe to be reassembled with Owner supplied |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Straub couplings. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipe: Length approximately 30 meter, DN65 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | size 76,1x4,5mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dis-mounting of pipes for cleaning | QUOTED | 1 | 13500 | 13500 | 0 | 0 | 0 | 13500
|  | HP wash cleaning of pipes per day | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
|  | Excl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
1078 | 1111.05 | Vent pipes in VS7
|  | Pipes to be cut by the use of reciprocating saw |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | in 8 places and pipes checked. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipes to be reinstalled with Owner delivered |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | straub couplings. | QUOTED | 1 | 48000 | 48000 | 0 | 0 | 0 | 48000
|  | Excl. staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation of 30 meters of 30mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | rockwool pipe section insulation finished with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | aluminum foil. | QUOTED | 1 | 15600 | 15600 | 0 | 0 | 0 | 15600
|  | Reduction due to less meters |  | 1 | -4000 | 0 | 0 | -4000 | 0 | -4000
1079 | 1114.01 | Ballast tanks
|  | Work order ballast tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The vessel's crew will open and close manholes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to the tanks. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mud removal to be done by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible protection of manhole by yard, each | INFO | 0 | 1500 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Below prices are based on empty, clean tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ready for hot-work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In general: Excl. Possible access holes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cut/closed for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work tk 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: 10 spots to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 10 m². | QUOTED | 1 | 28400 | 28400 | 0 | 0 | 0 | 28400
|  | Scaffolding: No scaffolding needed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work tk 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mud removed by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: 10 spots to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4xTu with roller and brush. Allow for 10 m². | QUOTED | 1 | 28400 | 28400 | 0 | 0 | 0 | 28400
|  | Scaffolding: No scaffolding needed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel work: 2 cracks to be repaired: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1080 | 1201.01 | Anchors and chains
|  | Work order anchors and chains |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Anchors and chains ranged in dock, Hp cleaning, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | measured an marked with SS bands | QUOTED | 1 | 34000 | 34000 | 0 | 0 | 0 | 34000
|  | Painting of anchors with 1 coat | CANCELLED | 0 | 8800 | 17600 | 0 | -17600 | 0 | 0
|  | Painting of lenghts with red and white paint: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repair of gitter end | QUOTED | 1 | 22700 | 0 | 0 | 22700 | 0 | 22700
1085 | 1302.01 | Anchor mooring winches forward
|  | Work order Anchor mooring winches forward |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1. Gasket on the top cover to be replaced, each | QUOTED | 2 | 8500 | 17000 | 0 | 0 | 0 | 17000
|  | Possible drilling out broken bolts, each | CANCELLED | 0 | 200 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2. Oil leakage in the electrical box to be investigated |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3. Replacement of shaft seals (3 pcs. in total) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dis-mounting of 2 pcs. drums, 1 pcs. cabilar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Wheel, 1 pcs. Warping head + Support bearing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for replacement of 3 pcs. Shaft seals |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Per winch | QUOTED | 2 | 107760 | 215520 | 0 | 0 | 0 | 215520
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of shaft seals after dismantling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | drum and Cabilar, per seal | QUOTED | 14 | 8160 | 97920 | 16320 | 0 | 0 | 114240
|  | Counted 7 pcs per ancor winch |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dis-connect of anchor chain, each | QUOTED | 2 | 12000 | 24000 | 0 | 0 | 0 | 24000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible dis- and remounting of shaft from |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | gearbox, each | CANCELLED | 0 | 37250 | 74500 | -74500 | 0 | 0 | 0
|  | Excl. Chok fast |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Posible necessary installation of padeys for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | lifting, priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Beamclamp to be used / install where possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4. Replacement of worn bushes in the drums |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (6 pcs. in total), After dismantling, each | QUOTED | 28 | 3625 | 43500 | 58000 | 0 | 0 | 101500
|  | Counted 6 pcs bush bearings, 6 pcs slide bushes and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4 pcs roller bearings per winch |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement bushes in Cabilar after dismantling, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each | CANCELLED | 0 | 4450 | 17800 | -17800 | 0 | 0 | 0
|  | No bushings in cabilar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 5. Machining of the brake surface on the drums |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (3 pcs. in total), each surface | CANCELLED | 0 | 10000 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible mechanical cleaning of braking surface, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each | BY CREW | 0 | 3200 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 6. Replacement of shaft if found needed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Posible dis-mounting/replacement of shaft for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | drum in gearbox, each | QUOTED | 1 | 46560 | 46560 | -46560 | 46560 | 0 | 46560
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible dis-mounting/replacement of shaft |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for cabilar in gearbox, each | CANCELLED | 0 | 31920 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Anchor brake: Dis-mounting, dis-assembling, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaning, replacement of brakeband with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | submerged brass bolts, each | BY CREW | 0 | 27360 | 27360 | -27360 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mooring brake: Dis-mounting, dis-assembling, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaning, replacement of brakeband with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | submerged brass bolts, each | BY CREW | 0 | 12960 | 12960 | -12960 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All prices is excluded electrical work & bolts repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Draining of oil incl. sludge truck and disposal | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication of busings for anchor winches |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication of busings for axle 200x180x100 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assuming that shaft is removed for other jobs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Material: JM1 bronze |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total price for 2 pcs. Bushings | VOR 5 | 1 | 83490 | 0 | 83490 | 0 | 0 | 83490
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication of flange for sealing on SB anchor winch |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication of 1 pcs. Flange for sealing due to corrosion |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | on the old part |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total price for 1 pcs: | VOR 6 | 1 | 17860 | 0 | 17860 | 0 | 0 | 17860
|  | Incl. Materials |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication of brakeband brackets for anchor winch. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total price for 4 pcs: | VOR 9 | 1 | 34880 | 0 | 34880 | 0 | 0 | 34880
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Material, welding and plasmacutting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Paitning. To be done by crew. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication of gaskets or top cover. Owner delivered cork plate |  | 1 | 7800 | 0 | 0 | 7800 | 0 | 7800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication of flange for anchor winch |  | 1 | 22840 | 0 | 0 | 27840 | -5000 | 22840
1086 | 1302.02 | Mooring winches aft
|  | Work order Mooring Winches aft |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1. Gasket on the top cover to be replaced, each | QUOTED | 2 | 8500 | 17000 | 0 | 0 | 0 | 17000
|  | Possible drilling out broken bolts, each | CANCELLED | 0 | 200 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2. Oil leakage in the electrical box to be investigated |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3. Replacement of shaft seals (3 pcs. in total) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dis-mounting of 2 pcs. drums,1 pcs. Warping |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | head + Support bearing for replacement of 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pcs. Shaft seals. Per winch | QUOTED | 2 | 53280 | 106560 | 0 | 0 | 0 | 106560
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of shaft seals after dismantling |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | drum and Cabilar, per seal | QUOTED | 12 | 8160 | 97920 | 0 | 0 | 0 | 97920
|  | Counted 6 pcs seals per winch |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible dis- and remounting of shaft from |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | gearbox, each | CANCELLED | 0 | 23760 | 47520 | -47520 | 0 | 0 | 0
|  | Excl. Chok fast |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Posible necessary installation of padeys for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | lifting, priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Beamclamp to be used/install where possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4. Replacement of worn bushes in the drums |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | After dismantling, each | QUOTED | 30 | 3625 | 29000 | 79750 | 0 | 0 | 108750
|  | Counted 4 pcs bush bearings, 6 pcs slides bushed and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 5 pcs bearings per winch |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 5. Machining of the brake surface on the drums |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (3 pcs. in total), each surface | CANCELLED | 0 | 10000 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible mechanical cleaning of braking |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | surface, each | BY CREW | 0 | 3200 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 6. Replacement of shaft if found needed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Posible dis-mounting/replacement of shaft for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cabilar in gearbox, each | CANCELLED | 0 | 35760 | 35760 | -35760 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mooring brake: Dis-mounting, dis-assembling, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cleaning, replacement of brakeband with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | submerged brass bolts, each | BY CREW | 0 | 12960 | 25920 | -25920 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dis-mounting of electrical motor, each | QUOTED | 2 | 11800 | 23600 | 0 | 0 | 0 | 23600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All prices is excluded electrical work & bolts repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Draining of oil incl. sludge truck and disposal | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery of 4 pcs bearings | QUOTED | 1 | 16600 | 0 | 20000 | -3400 | 0 | 16600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assistance for installation of brake bands | QUOTED | 4 | 8500 | 0 | 0 | 34000 | 0 | 34000
1091 | 1317.04 | Repair of cracks in ramps
|  | Repair of cracks in the stern ramp per running |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | meter |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repairs Price case by case | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1092 | 1317.05 | Ramp protection
|  | Work order Ramp protection |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Per additional fishbone: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ramp to lower hold, 38 pcs. , each | QUOTED | 36 | 1040 | 39520 | 0 | 0 | -2080 | 37440
|  | Main deck at hoistable ramp, 60 pcs., each | QUOTED | 48 | 1040 | 62400 | 0 | 0 | -12480 | 49920
|  | Main deck internal ramp, 60 pcs., each | QUOTED | 58 | 1040 | 62400 | 0 | 0 | -2080 | 60320
|  | Upper deck ramp to weather deck, 60 pcs., each | QUOTED | 26 | 1040 | 62400 | 0 | 0 | -35360 | 27040
|  | Based Bimagrip removed for access, and excl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of new and touched. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment Bimagrip, incl.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each m² | JOB 1068 | 0 | 575 | 28750 | 0 | -28750 | 0 | 0
|  | Owner supplies Acraprime SP, Bimagrip LS and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | aggregate |  | 0 |  | 0 | 0 | 0 | 0 | 0
1093 | 1317.06 | Center ramp steel renewal
|  | Work order Center ramp steel renewal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cracked and buckeled areas on center ramp |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from main deck to upper deck to be replaced |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with new steel: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for replacement 5 m². |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Plate thinkness 10mm, steel A36TM. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Below area is cofferdam 1 or water ballast tank |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 22, access via manholes. | CANCELLED | 0 | 176000 | 176000 | -176000 | 0 | 0 | 0
|  | Included staging, based on all area is ready for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hot work, excl. painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | & 4xTu with roller and brush. | CANCELLED | 0 | 10700 | 10700 | -10700 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment Bimagrip, incl.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each m² - based 5 m² | CANCELLED | 0 | 520 | 2600 | -2600 | 0 | 0 | 0
|  | Excl. Treatment of steel below ramp |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | CANCELLED | 0 | 12500 | 12500 | -12500 | 0 | 0 | 0
1094 | 1317.07 | Hoistable ramp steel renewal
|  | Work order Hoistable ramp steel renewal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repair of cracks in the hoistable ramp by steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | renewal. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for 4 pcs. inserts of 1500x2500x10mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36TM | QUOTED | 4 | 132000 | 528000 | 0 | 0 | 0 | 528000
|  | SOW to be discussed, planned & agreed ref.to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | item 1317.08 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on all area is ready for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | & 4xTu with roller and brush. | CREW | 0 | 78000 | 78000 | 0 | -78000 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment Bimagrip, incl.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each m² - based 15 m² | INCL 1068 | 0 | 520 | 7800 | -7800 | 0 | 0 | 0
|  | Excl. Treatment of steel below ramp |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1095 | 1317.08 | Hoistable ramp u-beam
|  | 1. Bimagrip to be removel on Hoistable ramp |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | deck 2 tracks sizes 1mtr x 54 mtr |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment Bimagrip, incl.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each m² | INCL 1068 | 0 | 520 | 56160 | -56160 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each | JOB 1068 | 0 | 35 | 0 | 0 | 0 | 0 | 0
|  | Lashing pots protection and painting of deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | part of lashing pot, each | JOB 1068 | 0 | 22 | 0 | 0 | 0 | 0 | 0
|  | Lashing pots cleaning, blasting and painting, each | JOB 1068 | 0 | 440 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2. Ubeam below hoistable deck to be removed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | between Web. frames in sections of approx. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2250mm and install new Ubeam size 430x150x8mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ubeam sections with hydrulic cylinder reinforcement |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | NOT to be replaced |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each | QUOTED | 108 | 11000 | 1188000 | 0 | 0 | 0 | 1188000
|  | Based on free access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Full staging below Hoistable deck for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and covering/lifts | QUOTED | 1 | 110500 | 110500 | 0 | 0 | 0 | 110500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering of cables, hoses & equipment below |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | deck, included fire blanket on staging top platform | QUOTED | 1 | 80000 | 80000 | 0 | 0 | 0 | 80000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Removal of electrical cables etc if necessary for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | access: Estimate cost. | QUOTED | 1 | 150000 | 150000 | 0 | 0 | 0 | 150000
|  | SOW to be agreed and priced before start-up |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hydraulic Cylinder: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Draining, removal and plugging of hydraulic |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hoses for 12 pcs. Cylinders |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Removing 1 pcs. Pinbolt from each cylinder |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation in reverse order after hotwork and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | painting is completed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Testrun and de-aeration with vessel crew | QUOTED | 1 | 79040 | 79040 | 0 | 0 | 0 | 79040
|  | Excl. All painting and materials, installation of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | fire protection blanket done by firewatch. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assuming fittings can be reused |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hydraulic pipes: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Draining, disconnection and removal of 3 pcs. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hydraulic pipelines each 54 meters |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Plugging pipes and connections |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation of pipelines after hotwork and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | painting is completed. | QUOTED | 1 | 82290 | 82290 | 0 | 0 | 0 | 82290
|  | Excl. All painting and materials, installation of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | fire protection blanket done by firewatch. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assuming fittings and pipe holders can be reused |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal of hydraulic oil, per m³ | QUOTED | 1 | 1200 | 1200 | 0 | 0 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3. External U-beam and new and touch below |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hoistable deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechcanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4 x Tu coat with brush and ruller | CANCELLED | 0 | 78000 | 78000 | 0 | -78000 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Support beam as agreed |  | 1 | 32500 | 32500 | 0 | 0 | 0 | 32500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional: New scope for securing of cheats. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Hydraulic cylinders to be removed 4 pcs. at the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | time and delivery of ball valves and fittings | QUOTED | 1 | 100000 | 100000 | 0 | 0 | 0 | 100000
1096 | 1317.09 | Stern ramp steel renewal
|  | Work order Stern ramp steel renewal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cracked and buckled areas on the stern ramp |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | top plate to be replaced with new steel: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for 30 m² in 2 places. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Plate thickness: 12mm, steel AH36. | QUOTED | 1 | 345600 | 345600 | 0 | 0 | 0 | 345600
|  | Based on all area is ready for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional stiffeners in size 600x250x12mm, each | QUOTED | 60 | 2200 | 132000 | 0 | 0 | 0 | 132000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | & 4xTu with roller and brush. | QUOTED | 1 | 10700 | 10700 | 0 | 0 | 0 | 10700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1097 | 1321.01 | Drains on main deck
|  | Dis-mounting of pipes for cleaning | QUOTED | 1 | 21175 | 21175 | 0 | 0 | 0 | 21175
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP wash cleaning of pipes each day | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access to pipes from ballast water tank 22. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for 20 m3 scaffolding installed in the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ballast tank | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | & 4xTu with roller and brush. | CANCELLED | 0 | 8000 | 8000 | -8000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The vessel'screw will open and close manholes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to the ballast water tank. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1098 | 1321.02 | Bilge valve overhaul
|  | Work order Valve overhaul |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dis-mounting DN250 valve overhaul in yard |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | work shope (per pcs.) | QUOTED | 1 | 15840 | 15840 | 0 | 0 | 0 | 15840
|  | Included rigging/transportation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on free access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transport to/from pipe tunnel | CANCELLED | 0 | 2860 | 2860 | -2860 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The vessel's electrician will disconnect and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | reconnect the hydraulic actuator for the valve. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1099 | 1401.01 | Freefall lifeboat (FFB)
|  | Freefall lifeboat to be taken ashore and return |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | after painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Included removal of old markings and installation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of new owner supplied markings | QUOTED | 1 | 12000 | 12000 | 0 | 0 | 0 | 12000
|  | Boat to be cleaned, covered off for painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and painted. | QUOTED | 1 | 55500 | 55500 | 0 | 0 | 0 | 55500
|  | David to be chemical cleaned, covered off for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | painting, mechanical cleaned on rusti spods, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | washed down with FW, Tu coated 2 times with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | roller and brush on spods and Fc with with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | roller and brush 1 time, lift for access included |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | in price. | QUOTED | 1 | 38840 | 38840 | 0 | 0 | 0 | 38840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible further assistance to owners specialists: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | CANCELLED | 0 | 8500 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Possible fiberglass repairs |  | 0 |  | 0 | 0 | 0 | 0 | 0
1100 | 2701.01 | Ventilation duct cleaning
|  | Work order Ventilation duct cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Accomodation exhaust: 345m, dust in duct | QUOTED | 1 | 105760 | 105760 | 0 | 0 | 0 | 105760
|  | Sanitary exhaust: 170 m, dust in duct | QUOTED | 1 | 51160 | 51160 | 0 | 0 | 0 | 51160
|  | Laundry exhaust: 40 m, dust in duct | QUOTED | 1 | 39400 | 39400 | 0 | 0 | 0 | 39400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Galley canal 50m | CANCELLED | 0 | 91840 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In general: Subject to free access and based pallet |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | tank placed under ventilator for collecting wast |  | 0 |  | 0 | 0 | 0 | 0 | 0
1101 | 3123.01 | Tank top cleaning separator room
|  | Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1103 | 3128.01 | ME Charge air cooler
|  | Cleaning / Grinding |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 x TU Primer |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 x Rughnes all over with sandpaper |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 x FC Topcoat |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Preparing vent etc. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ship delivers paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total | VOR 2 | 1 | 61863 | 61863 | 0 | 0 | 0 | 61863
1104 | 3138.01 | Lining on ME exhaust pipe
|  | Work order Lining on ME exhaust pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Repair cladding on one joint elbow segment. | QUOTED | 1 | 18500 | 18500 | 0 | 0 | 0 | 18500
|  | Included staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
1105 | 3138.02 | Funnel top
|  | Work order Funnel top |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Corrosion on funnel top to be repaired. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for 12 m² to be treated and painted |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | & 4xTu with roller and brush. | CANCELLED | 0 | 28600 | 28600 | -28600 | 0 | 0 | 0
|  | Excl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
1106 | 3149.05 | A60 insulation above main engine
|  | Work order A60 insulation above main engine |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Demount existing insulation, delivery and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | installation of new A-60 insulation, made with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Searox FB6040 with aluminum foil. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total of 25 m². | QUOTED | 1 | 74100 | 74100 | 0 | 0 | 0 | 74100
|  | Incl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for approximately 100 m³ scaffolding to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | installed on top of the main engine for access. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The vessels electrician will remove and disconnect |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | the light fixture. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for washdown of the area with water and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | soap and 1 coat of paint for 100 m². | BY CREW | 0 | 151320 | 151320 | -151320 | 0 | 0 | 0
1108 | 3301.01 | Scrubber SW pumps overhaul
|  | The electrical motors will be disconnected by |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | the vessel's electrician and reconnected again |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | after the overhaul. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scrubber pumps overhaul, 2 pcs., each | QUOTED | 2 | 43200 | 86400 | 0 | 0 | 0 | 86400
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Overhaul of electrical motor 2 pcs., each | QUOTED | 2 | 43700 | 87400 | 0 | 0 | 0 | 87400
|  | Alignment of electrical motor and pump: Incl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of scrupper pump housings with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | owners supplied Wencon, each | CANCELLED | 0 | 12250 | 24500 | 0 | -24500 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery of 2 pcs. bearings 6319C3 isolated for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | FC use |  | 1 | 36960 | 36960 | 0 | 0 | 0 | 36960
|  | Repair of junction box |  | 1 | 4800 | 4800 | 0 | 0 | 0 | 4800
1109 | 3301.02 | Emergency fire pump
|  | The electrical motor to be disconnected by the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | vessel's electrician and reconnected again |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | after the overhaul. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fire pump replacement , 1 pcs. | QUOTED | 1 | 22800 | 22800 | 0 | 0 | 0 | 22800
|  | Overhaul of electrical motor | QUOTED | 1 | 42000 | 42000 | 0 | 0 | 0 | 42000
|  | Alignment of electrical motor and pump: Incl. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1110 | 3301.03 | Ballast tank 7 elbow
|  | Work order Ballast tank 7 elbow |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | DN250 elbow for ballast tank no. 7 to be replaced |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with new. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Location: Near valve 8120-1028 in pipe tunnel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | at frame 168. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipe dimension: 273x12,5mm, material St37-0, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | galvanized. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Maximum working pressure: 10 bar. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The new pipe is to be hot dip galvanized | QUOTED | 1 | 28500 | 28500 | 0 | 0 | 0 | 28500
1112 | 3302.02 | Cooler maintenance
|  | Work order Cooler maintenance - start day 1 - |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | plates to be ready for pickup the 20/7 PM |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Job 1 Scrubber cooler 455 plates: | CANCELLED | 0 | 148785 | 0 | 0 | 0 | 0 | 0
|  | Possible change of owners supplied gaskets, each | CANCELLED | 0 | 186 | 0 | 0 | 0 | 0 | 0
|  | Alternatively: Replacing of plates with new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | overhauled plates of owners supply | QUOTED | 1 | 56320 | 40000 | 16320 | 0 | 0 | 56320
|  | Anchor plate inspection, grinding, and coating: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Job 2 LT FW cooler 2x250 plates: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dismantling, cleaning and reassembling with |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | old gaskets | QUOTED | 2 | 81750 | 163500 | 0 | 0 | 0 | 163500
|  | Possible change of owners supplied gaskets, each | QUOTED | 4 | 186 | 0 | 744 | 0 | 0 | 744
|  | Alternatively: Replacing of plates with new |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | overhauled plates of owners supply | CANCELLED | 0 | 40000 | 40000 | -40000 | 0 | 0 | 0
|  | Anchor plate inspection, grinding, and coating: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Priced after inspection | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1113 | 3302.04 | Scrubber fresh water tanks cleaning
|  | Cleaning of 2 pcs. Scrubber tanks according to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | inspection, total price for 2 pcs. Tanks | VOR 1 | 1 | 77960 | 77960 | 0 | 0 | 0 | 77960
|  | Incl. Washing equipment, sludge truck and ventilation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal of sludge, each m³ | QUOTED | 3 | 1200 | 6000 | 0 | -2400 | 0 | 3600
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal of scrubber solid waste, each ton | CANCELLED | 0 | 15300 | 15300 | 0 | -15300 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. possible scaffolding |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Opening and closing of tanks. To be done |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | by crew. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1114 | 3306.01 | Scrubber uptake & bypass valves overhaul
|  | Possible installation of new manholes to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | installed in the Main engine exhaust gas pipe |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for access to damper valves for scrubber system |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each new manhole | CANCELLED | 0 | 35920 | 0 | 0 | 0 | 0 | 0
|  | Based on free acces for placing the manholes. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Standard overhaul in situ. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bypass valve - Tag: A1010. Maker: VVC, model |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | type DSK-D (double disc), DN1600, Location: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Top of casing (outside): |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Leaf Springs, gland packings and bearings to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be replaced. | QUOTED | 1 | 48350 | 48350 | 0 | 0 | 0 | 48350
|  | Included Staging for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Standard overhaul in situ. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Uptake valve - Tag: A1030 Maker: VVC, model |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | type DSK (single disc), DN1600, Location: Top |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of casing (inside) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gland packing, bearings to be replaced. | QUOTED | 1 | 48150 | 48150 | 0 | 0 | 0 | 48150
|  | Included Staging for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible dis-mounting of valve for access, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each valve | CANCELLED | 0 | 55350 | 0 | 0 | 0 | 0 | 0
|  | Possible dis-mounting of exhaust pipe for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | access, each | CANCELLED | 0 | 29380 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Both actuators is to be dimounted, overhauled |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and mounted again, 2 pcs. |  | 1 | 33280 | 33280 | 0 | 0 | 0 | 33280
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible drilling of holes for adjustment: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Remounting of man hole cover and deliver paint |  | 1 | 4400 | 0 | 0 | 4400 | 0 | 4400
1115 | 3306.02 | Seawater pipe before cooler to be replaced
|  | to GRE |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Main seawater pipe from manifold to the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | non-return valves at the seawater pumps to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | replaced with new CuNife pipes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of existing CuNIFe piping according |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to received specification with new CuniFe piping | QUOTED | 1 | 172500 | 172500 | 0 | 0 | 0 | 172500
|  | Based on reuse of existing supports, all area is |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ready for hot work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Replacement of exixting pipng to GRE type: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | There is not enough space to install this type of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | material. New routing of piping is necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | SOW to be discussed and agreed | CANCELLED | 0 |  | 0 | 0 | 0 | 0 | 0
1116 | 3314.01 | Main Engine Lubricating oil Pumps
|  | 2 pcs. ME lub oil Pumps overhauled in workshop | QUOTED | 2 | 30800 | 61600 | 0 | 0 | 0 | 61600
|  | 2 pcs bearings |  | 1 | 2224 | 0 | 2224 | 0 | 0 | 2224
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Standard overhaul of el-motor, 2 pcs. | QUOTED | 2 | 34500 | 69000 | 0 | 0 | 0 | 69000
|  | Subject to free access for rigging/transportation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | out/in of vessel |  | 0 |  | 0 | 0 | 0 | 0 | 0
1117 | 3314.02 | Replacement of lubrication oil valves
|  | Replacement of lubrication oil valves (per pcs.) | QUOTED | 5 | 10680 | 53400 | 0 | 0 | 0 | 53400
|  | Based on plug and play |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Small mobile drip tray will be used below valves |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to minimize oil spill |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mud truck, per normal working hours | QUOTED | 4 | 1150 | 0 | 0 | 4600 | 0 | 4600
|  | Disposal of oil per m³ | QUOTED | 1 | 1200 | 0 | 0 | 1200 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The crew will drain the systems to minimize |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | the clean up after the repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Clean up afterwards of any oil spill done by crew |  | 0 |  | 0 | 0 | 0 | 0 | 0
1119 | 3336.01 | Installation of new oily water separator
|  | Work order Installation of new oily water separator |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Old type: RWO SKIT S 5.0m3 per h |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New type: OWS-COM 5.0m3 per h |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scope of work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Dismantle old oily water separator (OWS) for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | removal and transport to the main deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Open the bulkhead and remove pipes to gain |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | access for OWS removal and new unit installation. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Dismantle the new OWS for transport to the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | engine room. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Remove handrails located next to the main engine. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Install the new OWS on the existing foundation. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - The vessel's electrician will disconnect all electrical |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | equipment, which will be reconnected later |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Restore pipes, pipe insulation, handrails, and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | the bulkhead after OWS installation. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Allow for modification of below pipes: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 4: Oil discharge, DN25, old connection “4” |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 5: Backflush discharge DN20, old connection “5” |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 6: Control air supply, DN8, old connection “6”. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 15: Backflush water inlet, DN20, old connection “15” |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 22: Bilge water inlet, DN50, Old connection “22” |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 25: OMD 15 ppm cell to be moved |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 23B & 55B: Water recirculation, old connection “23B” |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 27: Drain OWS, DN25, old connection “27” |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tip 55A: Water overboard, DN40, old connection “23A” | QUOTED | 1 | 244900 | 244900 | 0 | 0 | 0 | 244900
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Drity oil tank 85 cleaning for hot work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: Included |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | local cleaning for installation of reinforcement |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | below tanktop deck - Incl job 1026 | INCL 1026 | 0 | 19000 | 19000 | -19000 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation of up to 8 pcs. anglebars legs height |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 500mm on the new foundation height 500mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | included 8 pcs. doubling on tank top deck. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation of up to 4 pcs. Reinforcement bulb |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | profile size 120x8x500mm below tanktop deck. | QUOTED | 1 | 49500 | 49500 | 0 | 0 | 0 | 49500
|  | Excl. Staging and painting and electrical |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Modification of oily water separator skid and installation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of additional filter unit incl. additional piping |  | 1 | 37400 | 0 | 0 | 37400 | 0 | 37400
1120 | 3338.01 | Ship side valves
|  | Shipside valves 30 pcs. according to attached |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | list valves to be opened/closed and overhauled |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and approved by Lloyds surveyor. | QUOTED | 1 | 73990 | 73990 | 0 | 0 | 0 | 73990
|  | Broken studs to be drilled out, re-tapped and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | studs replaced: As per account |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipes between all sea valves and ship's side to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be proven clear | QUOTED | 1 | 6800 | 6800 | 0 | 0 | 0 | 6800
|  | Cleaning of pipes, each | QUOTED | 1 | 500 | 500 | 0 | 0 | 0 | 500
|  | Overhaul of speed log valve | QUOTED | 1 | 3950 | 3950 | 0 | 0 | 0 | 3950
|  | Subject to free access. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (Removal pipes, walkway etc. For access to valves) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. possible remote controls and actuators |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cone valves overhauled without dismounting of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | valve housing. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Butterfly valves cleaned "in-situ" without dismounting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. DN 25 valve off/on for access/repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. DN 100 butterfly valves off/on for access/repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. DN 125 butterfly valves off/on for access/repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. DN 150 butterfly valves off/on for access/repair |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. DN 100 pipes off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. DN 125 pipes off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs. DN 150 pipes off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. DN 200 pipe off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 pcs. DN 350 pipes off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. DN 400 pipe off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4 pcs. actuators and remote controls off/on for access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total: |  | 1 | 57005 | 57005 | 0 | 0 | 0 | 57005
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible machining |  | 0 |  | 0 | 0 | 0 | 0 | 0
1123 | 3341.01 | ME fans
|  | Work order Overhaul of ME fans |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Standard overhaul of electrical motors 30Kw, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3 pcs., each | QUOTED | 3 | 24380 | 73140 | 0 | 0 | 0 | 73140
|  | Excl. Possible access/staging and paint treatment |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible duct repair: Priced after inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Remove/disconnect fire flab if necessary |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Supply of bearings |  | 1 | 4500 | 0 | 0 | 4500 | 0 | 4500
1124 | 3341.02 | AE fans
|  | Work order Overhaul of AE fans |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Standard overhaul of electrical motors 37Kw, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs., each | QUOTED | 2 | 29500 | 59000 | 0 | 0 | 0 | 59000
|  | Excl. Possible access/staging and paint treatment |  | 0 |  | 0 | 0 | 0 | 0 | 0
1131 | 3801.02 | Ropeguard
|  | A: Fabrication of missing rope guard knives, each | CANCELLED | 0 | 3570 | 0 | 0 | 0 | 0 | 0
|  | Option: Installation of new owner supplied |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | rope guard knives, each | CANCELLED | 0 | 1800 | 10800 | -10800 | 0 | 0 | 0
|  | B: Fabrication of new rope guard | CANCELLED | 0 | 50300 | 0 | 0 | 0 | 0 | 0
|  | Based on straight cylindric rope guards |  | 0 |  | 0 | 0 | 0 | 0 | 0
1132 | 3802.01 | Stern Tube Seal
|  | Work order Stern Tube Seal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Aft seal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AEGIR Marine type Prime-Secure 710 with APS. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Staging for dismantling ropeguard | QUOTED | 1 | 13200 | 13200 | 0 | 0 | 0 | 13200
|  | Dismantling and refit ropeguard | QUOTED | 1 | 34200 | 34200 | 0 | 0 | 0 | 34200
|  | Measuring of tail shaft wear down | QUOTED | 1 | 3420 | 3420 | 3420 | -3420 | 0 | 3420
|  | Draining of propeller and stern tupe oil (approx. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3500 l) by yard and new oil refilled by crew | QUOTED | 1 | 16100 | 16100 | 0 | 0 | 0 | 16100
|  | Disposal of oil. Each m³ / 3,5 m³ | QUOTED | 4 | 1200 | 4200 | 0 | 0 | 0 | 4200
|  | Assistance to owners specialist with installation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of new liner. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour shift, estimated 5 shifts | TIMESHEET | 0 | 8500 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Forward stern tube seal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AEGIR PRIME 630 Viton. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | AEGIR Marine will change the forward seals. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Forward seal system to be opened, cleaned and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | inspected by service engineer from AEGIR Marine. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The centre of the forward seal housing is to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | checked by the service engineer. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Yard to assist the service engineer from AEGIR |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Marine as found necessary. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Assistance to owners specialist with installation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of new liner. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour shift, estimated 4 shifts | TIMESHEET | 0 | 8500 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rough estimate timesheets remaining |  | 0 |  | 100000 | -55000 | -45000 | 0 | 0
|  | According to timesheet per 17/7-24 | QUOTED | 1 | 17850 | 17850 | 0 | 0 | 0 | 17850
|  | According to timesheet per 18/7-24 | QUOTED | 1 | 8750 | 8750 | 0 | 0 | 0 | 8750
|  | According to timesheet per 19/7-24 | QUOTED | 1 | 17600 | 0 | 17600 | 0 | 0 | 17600
|  | According to timesheet per 20/7-24 | QUOTED | 1 | 15350 | 0 | 15350 | 0 | 0 | 15350
|  | According to timesheet per 21/7-24 | QUOTED | 1 | 12350 | 0 | 12350 | 0 | 0 | 12350
|  | According to timesheet per 22/7-24 | QUOTED | 1 | 9700 | 0 | 9700 | 0 | 0 | 9700
1134 | 3811.01 | Bow Thruster no. 1 (forward) and 2 (aft)
|  | Bow Thruster No. 1 (forward) and 2 (aft) to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | dismantled for replacement of the propeller |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | shaft seal and blade seals. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | On-site work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Grid removal/reinstall, based on welded type, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per unit | QUOTED | 2 | 12000 | 24000 | 0 | 0 | 0 | 24000
|  | Oil drained and refilled by crew incl. Staging, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per unit | QUOTED | 2 | 20000 | 40000 | 0 | 0 | 0 | 40000
|  | Removal/reinstall of propeller blade, per blade | CANCELLED | 0 | 6000 | 0 | 0 | 0 | 0 | 0
|  | Possible installation of padeys, each | QUOTED | 6 | 10000 | 60000 | 0 | 0 | 0 | 60000
|  | Excl. possible internal painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | TIMESHEET | 0 | 8500 | 0 | 0 | 0 | 0 | 0
|  | Disposal of oil, each m³ | QUOTED | 1 | 1200 | 3600 | 0 | -2400 | 0 | 1200
|  | Possible machining of propeller blade foot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each foot | CANCELLED | 0 | 7500 | 0 | 0 | 0 | 0 | 0
|  | Estimate timesheets remaining |  | 0 |  | 200000 | -100000 | -100000 | 0 | 0
|  | According to timesheet per 17/7-24 | QUOTED | 1 | 20130 | 20130 | 0 | 0 | 0 | 20130
|  | According to timesheet per 18/7-24 | QUOTED | 1 | 26650 | 26650 | 0 | 0 | 0 | 26650
|  | According to timesheet per 19/7-24 | QUOTED | 1 | 19800 | 0 | 19800 | 0 | 0 | 19800
|  | According to timesheet per 20/7-24 | QUOTED | 1 | 22450 | 0 | 22450 | 0 | 0 | 22450
|  | According to timesheet per 21/7-24 | QUOTED | 1 | 19400 | 0 | 19400 | 0 | 0 | 19400
|  | According to timesheet per 22/7-24 | QUOTED | 1 | 20225 | 0 | 20225 | 0 | 0 | 20225
|  | According to timesheet per 23/7-24 | QUOTED | 1 | 21440 | 0 | 21440 | 0 | 0 | 21440
|  | According to timesheet per 24/7-24 | QUOTED | 1 | 14380 | 0 | 0 | 14380 | 0 | 14380
|  | According to timesheet per 25/7-24 | QUOTED | 1 | 15990 | 0 | 0 | 15990 | 0 | 15990
|  | According to timesheet per 26/7-24 | QUOTED | 1 | 8500 | 0 | 0 | 8500 | 0 | 8500
1135 | 3811.02 | Stern Thruster no. 1 (forward) and 2 (aft)
|  | Stern Thruster No. 1 (forward) and 2 (aft) to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | dismantled for replacement of the propeller |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | shaft seal and blade seals. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | On-site work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Grid removal/reinstall, based on welded type, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per unit | QUOTED | 2 | 12000 | 24000 | 0 | 0 | 0 | 24000
|  | Oil drained and refilled by crew incl. Staging, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per unit | QUOTED | 2 | 20000 | 40000 | 0 | 0 | 0 | 40000
|  | Removal/reinstall of propeller blade, per blade | CANCELLED | 0 | 6000 | 0 | 0 | 0 | 0 | 0
|  | Possible installation of padeys, each | QUOTED | 6 | 10000 | 60000 | 0 | 0 | 0 | 60000
|  | Excl. possible internal painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | TIMESHEET | 0 | 8500 | 0 | 0 | 0 | 0 | 0
|  | Disposal of oil, each m³ | QUOTED | 1 | 1200 | 3600 | 0 | -2400 | 0 | 1200
|  | Possible machining of propeller blade foot, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | each foot | CANCELLED | 0 | 7500 | 0 | 0 | 0 | 0 | 0
|  | Estimate timesheets remaining |  | 0 |  | 200000 | -125000 | -75000 | 0 | 0
|  | According to timesheet per 17/7-24 | QUOTED | 1 | 20020 | 20020 | 0 | 0 | 0 | 20020
|  | According to timesheet per 18/7-24 | QUOTED | 1 | 26650 | 26650 | 0 | 0 | 0 | 26650
|  | According to timesheet per 19/7-24 | QUOTED | 1 | 23080 | 0 | 23080 | 0 | 0 | 23080
|  | According to timesheet per 20/7-24 | QUOTED | 1 | 22450 | 0 | 22450 | 0 | 0 | 22450
|  | According to timesheet per 21/7-24 | QUOTED | 1 | 21100 | 0 | 21100 | 0 | 0 | 21100
|  | According to timesheet per 22/7-24 | QUOTED | 1 | 19250 | 0 | 19250 | 0 | 0 | 19250
|  | According to timesheet per 23/7-24 | QUOTED | 1 | 32650 | 0 | 32650 | 0 | 0 | 32650
|  | According to timesheet per 24/7-24 | QUOTED | 1 | 16275 | 0 | 0 | 16275 | 0 | 16275
|  | According to timesheet per 25/7-24 | QUOTED | 1 | 4500 | 0 | 0 | 4500 | 0 | 4500
1136 | 3811.03 | Bow or stern thruster replacement
|  | Workorder Bow or stern thuster replacement |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Grid removal/reinstall, based on welded type, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per unit | CANCELLED | 0 | 12000 | 0 | 0 | 0 | 0 | 0
|  | Oil drained and refilled by crew incl. Staging, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | per unit | CANCELLED | 0 | 20000 | 0 | 0 | 0 | 0 | 0
|  | Removal/reinstall of propeller blade, per blade | CANCELLED | 0 | 6000 | 0 | 0 | 0 | 0 | 0
|  | Demount/refit of underwater part, included |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | transport to workshop for overhaul or shifting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to replacement unit: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on only access from outside, per unit | CANCELLED | 0 | 60000 | 0 | 0 | 0 | 0 | 0
|  | Possible installation of padeys, each | CANCELLED | 0 | 10000 | 0 | 0 | 0 | 0 | 0
|  | Excl. possible internal painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Further yard assistance to service engineers: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each person per 12 hour day shift | CANCELLED | 0 | 8500 | 0 | 0 | 0 | 0 | 0
|  | Disposal of oil, each m³ | CANCELLED | 0 | 1200 | 0 | 0 | 0 | 0 | 0
1138 | 10010.01 | Ballast Water Treatment Plant
|  | Platform and ladders ME room FWD |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel platform to be made in front of main engine. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Platform to be done in angle iron and standard |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel pipes. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel gratings to be used on platform. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ladders to be made in order to grant safe access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to the platform. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Attached pictures from Ficaria, to show how |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | plateu should be made. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | It should be possible to acces pipes from coming |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | BWTS system as well as, floodlights, alarm panels |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and crane. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All new and touched steel to be painted | QUOTED | 1 | 136200 | 136200 | 0 | 0 | 0 | 136200
|  | The Owner supplies all paint. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ballast Water Treatment Plant |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Work order Ballast Water Treatment Plant: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1. Mechanical works |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1.1 Transport and mounting of Owner supplied |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | equipment Installation of: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Main control panel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Backflush pump |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - CIP Unit |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - DESMI BWTS Unit | QUOTED | 1 | 44710 | 44710 | 0 | 0 | 0 | 44710
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2. Pipe & Valve works |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2.1 Fabrication and mounting of pipes |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | according to Isometric Catalogue |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication and Installation of: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Ballast water diagram for BWTS - ISO catalog |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | REV.0 | QUOTED | 1 | 1261616 | 1261616 | 0 | 0 | 0 | 1261616
|  | - Tech. Water supply |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Drain pipe in BWTS room |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2.2 Fabrication and mounting of pipe supports |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication and installation of New steel: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Beams and lifting device, 154 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastening of main panel, 69 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastning of BWTS CIP backflush |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pump, 67 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastening of BWTS CIP dosing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | unit, 32 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Foundation and fastning of BWTS skid 102 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Gratings in Technical compartment modification, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 436 kg. | QUOTED | 1 | 52359 | 52359 | 0 | 0 | 0 | 52359
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2.4 Mounting of Owner supplied valves |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation of owner delivered new valves: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE BFV LUG 350 NEX EAN |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | OOF 26 230 PN10 WITH EL.ACTUATOR 230V |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1ph.PN10 HQ060 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE LUG WITH HANDLEVER |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | DN80 PN10 GGG40 MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE LUG WITH GEARBOX |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | DN250 PN10 GGG40 MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - BUTTERFLY VALVE LUG WITH GEARBOX |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | DN250 PN10 GGG40 MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - NON RETURN VALVE WAFER PN10 DN 80 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - NON RETURN VALVE WAFER PN10 DN 50 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | MARS VALVE EUROPE |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - NON RETURN VALVE WAFER PN10 DN 100 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | MARS VALVE EUROPE | QUOTED | 1 | 42985 | 42985 | 0 | 0 | 0 | 42985
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2.5 Modifications of ballast piping system |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Modification to ballast pipes. | QUOTED | 1 | 91596 | 91596 | 0 | 0 | 0 | 91596
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2.6 Dismantling and removal of non-reusable |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | parts of Ballast system |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Modifications: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Sheet 31/44: Existing ballast pipe to be modified |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | (The change included in 3897-8.1-WD_801-002). |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Sheet 38/44 : Heater to be removed. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Sheet 39/44 : Platform to be modified. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Sheet 42/44 : Cylinder oil tank to be removed. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Sheet 43/44 : Hydraulic pipes to WT door to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be modified | QUOTED | 1 | 181931 | 181931 | 0 | 0 | 0 | 181931
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Subjects in difference report |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All subjects of mechanical works in the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | difference report. | QUOTED | 1 | 171882 | 171882 | 0 | 0 | 0 | 171882
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 3. Electrical works: updated price to owner 04.03-22 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Price on electrical works include: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Delivery and installation of cables according |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | cable list. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Added extra cable Main panel to BWTS PDB |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | -Termination of fiber optic cable+ Fiber optic |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | converters |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - New breakers in MSB |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Fabricate and install new PDB |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Inst. Of lights, fire detectionand PAGA. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Equipment not included. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Modifications in bridge panel. (FWD Bridge Consol) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Inst. Remote Panel in CCR |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Modification in fire damper panel in BWTS room |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and Valve mimic panel in safety control room |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Neccessary cabletrays and brackets included |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - 2 pcs of Roxtec penetrations included |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Modifications in Bridge Panel for GPS |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Lamps to be relocated on platform deck |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | - Delivery and installation of ventilation and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | fire damper. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Price on electrical works is exclusive: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Light fixtures, PAGA, Smoke detector, Call |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Point, Participation on seatrial | QUOTED | 1 | 755562 | 755562 | 0 | 0 | 0 | 755562
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Power supply cable for BWTS valves W3-RM2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and W4-RM1: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivering and installation of 75 meterpower |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | supply cable |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The valves is moved from BWTS room to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | engine room | QUOTED | 1 | 15372 | 15372 | 0 | 0 | 0 | 15372
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4. Steel works |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fabrication and installation of New steel: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Beams and lifting device, 154 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastening of main panel, 69 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastning of BWTS CIP backflush |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pump, 67 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastening of BWTS CIP dosing |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | unit, 32 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Foundation and fastning of BWTS skid 102 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gratings in Technical compartment |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | modification, 436 kg. | QUOTED | 1 | 267450 | 267450 | 0 | 0 | 0 | 267450
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 4.1 Fabrication of new BWTS room including |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | access way | QUOTED | 1 | 242946 | 242946 | 0 | 0 | 0 | 242946
|  | Installation of protection barrier | QUOTED | 1 | 26500 | 26500 | 0 | 0 | 0 | 26500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additionals: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to received collision report: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Existing small electrical cabinet to be relocated in ER. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Existing light column to be relocated. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Existing cable tray and ducting to modification. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Lamp to relocation. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Fastening of the pumps start/stop buttons to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | modified | QUOTED | 1 | 32500 | 32500 | 0 | 0 | 0 | 32500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additionals based on work done on |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Freesia Seaways: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible delivery of 6 pcs. valves | QUOTED | 1 | 37350 | 37350 | 0 | 0 | 0 | 37350
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery and installation of cabinet for HMI |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | panel in BWTS room. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery of power supply 24 VDC. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Delivery of circuit breaker. | QUOTED | 1 | 7770 | 7770 | 0 | 0 | 0 | 7770
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional new 2 x DN 250 counber valves | QUOTED | 1 | 9700 | 9700 | 0 | 0 | 0 | 9700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Extra Cat 7 Cable from Main Panel - BWTS Room |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to agreement with Bo Grønkjær Petersen |  | 1 | 7000 | 7000 | 0 | 0 | 0 | 7000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Remove and install 2 pcs. cabinet in staircase |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for welding of BWTS Room |  | 1 | 3730 | 3730 | 0 | 0 | 0 | 3730
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Modification of prefabricated pipes according to inspection 29/7 |  | 1 | 6650 | 0 | 0 | 13300 | -6650 | 6650
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Modification of electrical cabinet |  | 1 | 7650 | 0 | 0 | 14300 | -6650 | 7650
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Test and certification of lifting points |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Test and certification of of lifting points performed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | using calibrated loadcell and a chainblock. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Report according to ILO152 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Note. Pulling point must be available. Price will be adjusted if test |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | must be done using weights. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total price for load test of 5 lifting points according to inspection 30/7 | CANCELLED | 0 | 26720 | 0 | 0 | 26720 | -26720 | 0
1139 | 1102.06A | Steel Renewal: BW TK 16
|  | Steel renewal in ballast water tank 16 in longitudinal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and transverse bulkhead according to attached sketch. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steel to be renewed: 4 pieces, 124 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access via manholes from lower hold |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | CANCELLED | 0 | 141384 | 141384 | -141384 | 0 | 0 | 0
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New scope only welding |  | 1 | 95700 | 0 | 95700 | 0 | 0 | 95700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for cleaning of HFO storage tank 34 for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hot work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Open/cloose manholes including protection of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | manhole, each place | CANCELLED | 0 | 2450 | 2450 | 0 | -2450 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Storage tank 34 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 8840
|  | Possible ventilation and gasfreeing of tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account. | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  | Possible additional cleaning for Hot work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be agreed upon |  | 1 | 84500 | 57000 | 27500 | 0 | 0 | 84500
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | sludge, per m³ | QUOTED | 11 | 1200 | 18000 | -4800 | 0 | 0 | 13200
|  | Mudtruck, each normal hour | QUOTED | 18 | 1150 | 35650 | -14950 | 0 | 0 | 20700
|  | Cleaning around manholes and walkways: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gas free certificate. See item 520.16 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for cleaning of over flow tank 43 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Open/cloose manholes including protection of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | manhole, each place | CREW | 0 | 2450 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: |  | 0 | 8840 | 0 | 8840 | 0 | -8840 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible ventilation and gasfreeing of tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account. |  | 0 | 10000 | 0 | 10000 | 0 | -10000 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additional cleaning for Hot work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be agreed upon |  | 0 | 36200 | 0 | 36200 | 0 | -36200 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | sludge per m³ |  | 0 | 1200 | 0 | 6000 | 0 | -6000 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mudtruck, each normal hour |  | 0 | 1500 | 0 | 12000 | 0 | -12000 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning around manholes and walkways: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gas free certificate. See item 520.16 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pressure test after the repair: 333,1 m³, frame |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 97 - 109, PS |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pressure test of tanks by air maximum 0,2 bar. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each tank. | QUOTED | 1 | 5000 | 5000 | 0 | 0 | 0 | 5000
|  | Pressurre test of tanks by sea water, based use |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of vessel system. Each tank | CANCELLED | 0 | 5000 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for removal and reinstallation of insulation. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | More specified information is necessary, or to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be priced after joint inspection |  | 1 | 3850 | 0 | 0 | 3850 | 0 | 3850
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 15000 | 15000 | 0 | 0 | 0 | 15000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner supplied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. heating and curring time |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1140 | 1102.07A | Steel Renewal: BW TK 17
|  | Steel renewal in ballast water tank 17 according |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to attached sketch: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Longitudinal and transverse bulkhead: 3 pieces, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 183,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Inner bottom, fixed ramp: 4 pieces, 379,8 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transverse web, frame 101: 1 piece, 69,9 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transverse web, frame 105: 1 piece, 58,5 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Transverse web, frame 109: 2 pieces, 38,6 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total: 730 kg | QUOTED | 1 | 557880 | 557880 | 0 | 0 | 0 | 557880
|  | Access via manholes from lower hold |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for cleaning of HFO storage tank 33 for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hot work |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Open/cloose manholes including protection of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | manhole, each place. | BY CREW | 0 | 2450 | 2450 | -2450 | 0 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Storage tank 33 | QUOTED | 1 | 8840 | 8840 | 0 | 0 | 0 | 8840
|  | Possible ventilation and gasfreeing of tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account. | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  | Possible additional cleaning for Hot work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be agreed upon, done in T&M |  | 1 | 64000 | 64000 | 0 | 0 | 0 | 64000
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | sludge, per m³ | QUOTED | 9 | 1200 | 10800 | 0 | 0 | 0 | 10800
|  | Mudtruck, each normal hour | QUOTED | 24 | 1150 | 27600 | 0 | 0 | 0 | 27600
|  | Cleaning around manholes and walkways: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account | BY CREW | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gas free certificate. See item 520.16 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pressure test after the repair: 333,1 m³, frame |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 97 - 109, PS |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pressure test of tanks by air maximum 0,2 bar. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each tank. | QUOTED | 1 | 5000 | 5000 | 0 | 0 | 0 | 5000
|  | Pressurre test of tanks by sea water, based use |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of vessel system. Each tank | CANCELLED | 0 | 5000 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for removal and reinstallation of insulation. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | More specified information is necessary, or to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be priced after joint inspection |  | 1 | 2800 | 0 | 0 | 2800 | 0 | 2800
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 38500 | 38500 | 0 | 0 | 0 | 38500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. heating and curring time |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel tk 17 additional to job no 1140 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | scope as agreed with steelforeman and superintendent | VOR 12 | 1 | 68375 | 0 | 0 | 68375 | 0 | 68375
|  | incl materials and fireguard |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crew to take care of extra access |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | excl paint and NDT |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for installation of 10 m³ staging | QUOTED | 1 | 11500 | 0 | 0 | 11500 | 0 | 11500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & 4x |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tu with roller and brush. Of above steel repair | QUOTED | 1 | 6000 | 0 | 0 | 6000 | 0 | 6000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for cleaning of over flow tank 43 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Open/cloose manholes including protection of |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | manhole, each place | CREW | 0 | 2450 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Suction of tankbottom incl. removal and disposal |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of max 2 m³ of pumpable oily waste: | QUOTED | 1 | 8840 | 0 | 0 | 8840 | 0 | 8840
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible ventilation and gasfreeing of tanks: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | As per account. | QUOTED | 1 | 10000 | 0 | 0 | 10000 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible additional cleaning for Hot work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | To be agreed upon |  | 1 | 36200 | 0 | 0 | 36200 | 0 | 36200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposing of additional removed pumpable |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | sludge, per m³ | QUOTED | 1 | 1200 | 0 | 0 | 1200 | 0 | 1200
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mudtruck, each normal hour | QUOTED | 8 | 1500 | 0 | 0 | 12000 | 0 | 12000
1141 | 1102.08A | Steel Renewal: BW TK 18
|  | Steel renewal in ballast water tank 18 according |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to attached sketch: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 10: 2 pieces, 32,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 11: 1 piece, 43,7 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 12: 2 pieces, 32,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 15: 1 piece, 43,7 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 16: 2 pieces, 32,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 17: 3 pieces, 72,7 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 18: 2 pieces, 32,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 19: 2 pieces, 32,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 20: 2 pieces, 32,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 25: 2 pieces, 190,8 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 29: 2 pieces, 112,3 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 32: 2 pieces, 32,2 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 33: 3 pieces, 140,4 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total: 28 pieces, 829 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access via manholes from main deck. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | CANCELLED | 0 | 577524 | 0 | 0 | 0 | 0 | 0
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New price due to reduction in scope | QUOTED | 1 | 390000 | 390000 | 0 | 0 | 0 | 390000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 41000 | 41000 | 0 | 0 | 0 | 41000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. heating and curring time |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1142 | 1102.09A | Steel Renewal: BW TK 19
|  | Steel renewal in ballast water tank 19 according |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to attached sketch: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 25: Insert 1700x400mm, thickness 10mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36TM, 53 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 29: Insert 1700x400mm, thickness 10mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36TM, 53 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 29: Weld up 200x100mm, thickness 10mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36TM, 1,6 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total: 3 pieces, 107,6 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access via manholes from main deck. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | CANCELLED | 0 | 89640 | 89640 | -89640 | 0 | 0 | 0
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New scope: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gauging and welding of 7 pcs cracks |  | 1 | 66500 | 0 | 66500 | 0 | 0 | 66500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 16500 | 16500 | 0 | 0 | 0 | 16500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Staging, heating and curring time |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1143 | 1102.10A | Steel Renewal: BW TK 20
|  | Steel renewal in ballast water tank 20 according |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to attached sketch: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 19: Insert 800x400mm, thickness 11mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel A36, 27,5 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 29: Insert 800x400mm, thickness 10mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel AH36TM, 25 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total: 2 pieces, 52,5 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access via manholes from main deck. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | CANCELLED | 0 | 59970 | 0 | 0 | 0 | 0 | 0
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New price due to reduction in scope | QUOTED | 1 | 30000 | 30000 | 0 | 0 | 0 | 30000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 12500 | 12500 | 0 | 0 | 0 | 12500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Staging, heating and curring time |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1144 | 1102.11A | Steel Renewal: BW TK 22
|  | Steel renewal in ballast water tank 22 according |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to attached sketch: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 19: Insert 800x400mm, thickness 11mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel AH36, 27,5 kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | In total: 1 piece, 27,5 kg. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access via manholes from main deck. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | CANCELLED | 0 | 54870 | 0 | 0 | 0 | 0 | 0
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New price due to reduction in scope | QUOTED | 1 | 30000 | 30000 | 0 | 0 | 0 | 30000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 9000 | 9000 | 0 | 0 | 0 | 9000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Staging, heating and curring time |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1145 | 1102.12A | Steel Renewal: Transverse bulkhead main deck
|  | Steel repair on main deck according to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | attached sketch: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 238: Crack to be repaired by gouging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and welding. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | QUOTED | 1 | 20300 | 20300 | 0 | 0 | 0 | 20300
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | CANCELLED | 0 | 8500 | 8500 | -8500 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Staging. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crack masimum lenght 200mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1146 | 1108.04A | Damaged web frame main deck
|  | Damaged web frame at main deck at port side |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ar frame 69 to be repaired: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Face plate to be replaced. Approximately size |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 500x250mm, thickness 12mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine Gas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | QUOTED | 1 | 17500 | 17500 | 0 | 0 | 0 | 17500
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 5500 | 5500 | 0 | 0 | 0 | 5500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. Staging |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1147 |  | Assistance to Owner arranged Lotek
|  | Assistance to Owner arranged Lotek | CANCELLED | 0 | 10000 | 10000 | -10000 | 0 | 0 | 0
1148 | 1016.02 | Sea Chest cleaning
|  | Sea chests cleaned and painted, minimum 1 m³/ |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | seachest: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Silicone treatment of sea chests grid and edge |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | around sea chests hole | QUOTED | 1 | 35000 | 35000 | 0 | 0 | 0 | 35000
|  | Work order Sea chests cleaning and painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Lower seachest PS, frame 89 - 97, volume 41,1 m³, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | total area 200 m² | QUOTED | 41 | 765 | 31442 | 0 | 0 | 0 | 31442
|  | Upper seachest PS, frame 91 - 97, volume 48,2 m³, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | total area 143 m² | QUOTED | 48 | 765 | 36873 | 0 | 0 | 0 | 36873
|  | Forward seachest SB, frame 249 - 250, volume |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1,6 m³, total area 5 m² | QUOTED | 2 | 2134 | 3414 | 0 | 0 | 0 | 3414
|  | Based on max 1 m³ disposal per sea chest |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Open/close of sea chests, welded type, each | QUOTED | 3 | 2000 | 6000 | 0 | 0 | 0 | 6000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal of additional mud per m³ | QUOTED | 2 | 2500 | 12500 | 0 | -7500 | 0 | 5000
1149 | 3801.04A | Propeller Coating
|  | Propeller blades & hub blasting and painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | in-situ without removal. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment of 4 pcs. propeller blades and 1 hub: | QUOTED | 1 | 133690 | 133690 | 0 | 0 | 0 | 133690
|  | Cleaning with chemicals, included hosed down |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 x HP wash with 500 bar |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Grit blasting, included cleaning for painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting with owner supplied XGIT paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Included supply of grit (Owner spcified grit to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | be Garnet 30/60 mesh in size 0,15-0,60mm) |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Tent 6m x 3m x 8m for blasting and painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of Hub & blades in-situ | QUOTED | 1 | 32500 | 32500 | 0 | 0 | 0 | 32500
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Installation of ventilation and heating |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | equipment in tent, based on 3x9kwh blowers | QUOTED | 1 | 25000 | 25000 | 0 | 0 | 0 | 25000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Covering before blasting | QUOTED | 1 | 100000 | 50000 | 50000 | 0 | 0 | 100000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | According to received GRAPHITE guideline |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | document No. 6.1.3 item 1b & 3 Required |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | protection for preparation and coating to be |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | done by owner arrange coating advisor. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Disposal of grit, each ton | QUOTED | 9 | 2350 | 21150 | 0 | 0 | 0 | 21150
|  | Forklift and crane assistance | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The yard can not be held responsible, either in terms |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | of liability or financially, for any damage or defects |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | to parts and/or equipment resulting from the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | execution of this job. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | De- and remount of locks on propeller bolts | QUOTED | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional washing due to salt from pittings | QUOTED | 1 | 30000 | 0 | 30000 | 0 | 0 | 30000
1150 | 1001.11A | VS6a Port side damage
|  | Steel damage in void space 6a port side to be repaired. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for following steel job: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Frame 116.09 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs. insert 900x600mm, thickness 10mm, steel |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | A36 43,2kg |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for installation of scaffolding for access. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Access via manholes from main deck or lower hold. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machine |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Gas/oxygen, Crane, Forklift, fire guard | QUOTED | 1 | 67770 | 67770 | 0 | 0 | 0 | 67770
|  | Based on cleaned & empty area/tanks ready for |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional to come after inspection |  | 1 | 35000 | 0 | 35000 | 0 | 0 | 35000
|  | 1 pc 2400 x 120, 3 pcs 200 x 120 x 10 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 11000 | 11000 | 0 | 0 | 0 | 11000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Based on owner suppied paint |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Excl. heating and curring time |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1151 | 3149.07A | Scrubber upper jet pipe
|  | Repair the crack in the upper jet pipe. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Renew the pipe piece from the welding to the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | collar ring, including the collar ring itself. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Pipe: DN150, Ø168, 28mm, thickness 3,4mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | material SMO254 (1.4547), length approximately 200mm |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Collar ring: Ø212 x Ø168, thickness 3mm, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | material SMO254 (1.4547). |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Existing flange to be reused. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | All materials to be delivered by the yard. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for removal of the butterfly valve and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | the actuator. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | GRE pipes near the pipe to be protected to |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | prevent damages. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Allow for post-treatment to remove any residual |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | contaminants or corrosive elements from the |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | repaired area. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Ensure proper passivation of SMO254 stainless |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | steel surfaces after welding to restore corrosion |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | resistance. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dye penetrant inspection (DPI) to be performed |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | on welds to ensure integrity. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | The crew will test the tightness at first opportunity |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | using the scrubber pumps. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | See attached drawing and pictures |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dis-mounting of valve and actuator. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Existing jet pipe to be cut at welding joint. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | New jet pipe with collar ring to be fabricated and |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | installed with existing flange |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Welding to be done with process 141& Butt welding |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | done with shieding gas in-situ | QUOTED | 1 | 37440 | 37440 | 0 | 0 | 0 | 37440
|  | Based on free access. |  | 0 |  | 0 | 0 | 0 | 0 | 0
1152 | 1102.13A | Steel renewal ramp to lower hold
|  | Corroded and cracked deck plating on the ramp |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | from main deck to lower hold to be repaired |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | with insert at frame 69-70. Below is tank 87: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Dirty oil settling tank 87: 11,3 m³, frame 69 - 71, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | tank top, SB |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Approximately size of insert: 1000 x 500 mm. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Plate thickness: 10,5mm, steel A36TM. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Preparation for scope, Power supply, light, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | ventilation, Fresh air, welding machineGas/oxygen, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Crane, Forklift, fire guard | QUOTED | 1 | 41000 | 41000 | 0 | 0 | 0 | 41000
|  | Based on cleaned & empty area/tanks ready |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | for hot work. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional acces engine room: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint/insulation/cleaning | QUOTED | 1 | 150000 | 150000 | 0 | 0 | 0 | 150000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Paint work: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning with chemicals, mechnical cleaning & |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2xTu with roller and brush. Of above steel repair | QUOTED | 1 | 6000 | 6000 | 0 | 0 | 0 | 6000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Treatment Bimagrip, incl.: |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | not possible. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Each m² | JOB 1068 | 0 | 575 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Steelwork: Based Bimagrip removed for access, |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | and excl. Painting of new and touched. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional insert 28/7 |  | 1 | 30000 | 0 | 0 | 30000 | 0 | 30000
1153 |  | Crack in rudder repair
|  | 2 pcs Cracks in rudder repair + insert | QUOTED | 1 | 105000 | 128000 | -23000 | 0 | 0 | 105000
|  | Possible NDT, each time | INCL 1161 | 0 | 12500 | 12500 | 0 | -12500 | 0 | 0
1155 |  | Welding of broken anchor chain stud PS
|  | Welding of broken anchor chain stud PS, T&M | QUOTED | 1 | 10000 | 10000 | 0 | 0 | 0 | 10000
1156 | VOR 3 | FFB fiber glass repair
|  | FFB fiber glass reapir AFT, according to inspection 20/7. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Incl. Installation of fender list AFT. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total price: | VOR 3 | 1 | 12800 | 0 | 12800 | 0 | 0 | 12800
|  | Excl. Painting |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Additional repair of silicone on sliding plate |  | 1 | 7000 | 0 | 7000 | 0 | 0 | 7000
1157 |  | Boiler inspection
|  | Boiler inspection |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Rent of cutting gas | QUOTED | 1 | 20000 | 0 | 0 | 20000 | 0 | 20000
1158 |  | Test of steampipe, class
|  | Disconnect - connect |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | transport to and from workshop |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | pressure test |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | total | VOR 7 | 1 | 17720 | 0 | 17720 | 0 | 0 | 17720
|  | excl possible repair, paint and NDT |  | 0 |  | 0 | 0 | 0 | 0 | 0
1159 |  | Heeling tank 11 steel
|  | scope as agreed with steelforeman and superintendent | VOR 13 | 1 | 216032 | 0 | 0 | 216032 | 0 | 216032
|  | inkl additional work inspected, longitudual stifners etc. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Scaffolding | VOR 13 | 1 | 41250 | 0 | 0 | 41250 | 0 | 41250
|  | incl materials and fireguard |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Work may affect silicone paint on shell |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | excl paint and NDT |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Painting of new steel in tank 11 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Mechanical cleaning |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2x TU |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total price | VOR 16 | 1 | 119625 | 0 | 0 | 119625 | 0 | 119625
1160 | VOR 8 | Fabrication of new pipe fireline
|  | pipe to be fabricated |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 2 pcs DN100 flanges |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 1 pcs DN50 flange |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | incl galvanization and transport |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total | VOR 8 | 1 | 20960 | 0 | 20960 | 0 | 0 | 20960
|  | excl installation, paint and NDT |  | 0 |  | 0 | 0 | 0 | 0 | 0
1161 |  | Non destructive testing
|  | Non destructive testing, each hour | QUOTED | 50 | 1095 | 0 | 0 | 54750 | 0 | 54750
1162 | VOR 14 | Repair of sprinkler pipes under bridgewings
|  | repair of pipes before installation of insulation |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | incl materials and lift |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | total | VOR 14 | 1 | 34700 | 0 | 0 | 34700 | 0 | 34700
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | excl paint and ndt (and insulation/sheetmetal (other job)) |  | 0 |  | 0 | 0 | 0 | 0 | 0
1164 |  | Covering off for paint spray | QUOTED | 130 | 3.5 | 0 | 0 | 0 | 455 | 455
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation |  | 1 | 20000 | 20000 | 0 | 0 | 0 | 20000
9993 |  | Discount according to agreement
|  | Reduction for less scope on steel jobs according to agreement 29/7. |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Prices for all steel jobs closed |  | 1 | -250000 | 0 | 0 | -250000 | 0 | -250000
|  | Discount according to agreement | 15% | 1 | -2866432.177 | -3145325 | 185804 | 65426 | 27662 | -2866432
9995 |  | Prepayment received in advance |  | 1 | -11770619 | 0 | 0 | -11770619 | 0 | -11770619
|  |  | DKK |  |  | 17813515 | -1042892 | -12141368 | -159320 | 4469932 | 0