## Chapter 0
Ship name: |  | HUMBRIA SEAWAYS
Case No.: |  | 241149
Currency: | DKK | Chapter 0 |  |  |  | Estimate | New/changes | New/changes | Total cost
Job No.: | Item No. | Job description |  | Quantity | Unit Price | 2024-08-07 | 2024-08-14 | 2025-05-06 | Total
1001 | 1 | Docking period: 12/8 - 18/8-2024
|  | Dock/undock and dockdues, lumpsum | QUOTED | 1 | 350000 | 350000 | 0 | 0 | 350000
1002 | 2 | Earth connection
|  | Earth connection | INCL | 0 |  | 0 | 0 | 0 | 0
1003 | 3 | Fire Line Connection
|  | A. Temporary fire connections, per connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 7 | 1500 | 10500 | 0 | 0 | 10500
1004 | 4 | Garbage
|  | Garbage containers (4 m3), each | QUOTED | 2 | 5000 | 10000 | 0 | 0 | 10000
1005 | 5 | Cleaning of dock before departure
|  | Cleaning of dock before departure | INCL | 0 |  | 0 | 0 | 0 | 0
1006 | 6 | Gangway
|  | A. Per installation/removal | QUOTED | 2 | 4000 | 4000 | 4000 | 0 | 8000
1007 | 7 | Cooling water connection
|  | Cooling water connection, per connection | QUOTED | 1 | 3000 | 3000 | 0 | 0 | 3000
|  | Maintenance per day | QUOTED | 7 | 1500 | 10500 | 0 | 0 | 10500
1008 | 8 | Change wires for FFB and MOB. Wir es located on deck 7.
|  | Replacement of FFB davit wire delivered by vessel |  | 0 |  | 0 | 0 | 0 | 0
|  | Per wire | CANCELLED | 0 | 10522.5 | 10523 | -10523 | 0 | 0
|  | Manual spooling and application of grease if applicable |  | 0 |  | 0 | 0 | 0 | 0
|  | "Note: If wire pin/lock are stuck, removal done in t&m. |  | 0 |  | 0 | 0 | 0 | 0
|  | Assuming single sheave crane/block" |  | 0 |  | 0 | 0 | 0 | 0
|  | Scaffolding | CANCELLED | 0 | 45000 | 45000 | -45000 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Replacement of FRB/MOB davit wire delivered by vessel |  | 0 |  | 0 | 0 | 0 | 0
|  | Per wire | CANCELLED | 0 | 7320 | 7320 | -7320 | 0 | 0
|  | Manual spooling and application of grease if applicable |  | 0 |  | 0 | 0 | 0 | 0
|  | "Note: If wire pin/lock are stuck, removal done in t&m. |  | 0 |  | 0 | 0 | 0 | 0
|  | Assuming single sheave crane/block" |  | 0 |  | 0 | 0 | 0 | 0
|  | Scaffolding | CANCELLED | 0 | 5000 | 5000 | -5000 | 0 | 0
1009 | 9 | Change hydraulic hoses to FFB davit. Hoses located on
|  | deck 7 together with wires. |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Replacement of hydraulic hoses delivered by vessel. |  | 0 |  | 0 | 0 | 0 | 0
|  | Max. Ø1" and/or length 3.000 mm. |  | 0 |  | 0 | 0 | 0 | 0
|  | Hose fittings wrapped with Denso-tape after installation. |  | 0 |  | 0 | 0 | 0 | 0
|  | Hoses must be marked sufficiently |  | 0 |  | 0 | 0 | 0 | 0
|  | Per hose | CANCELLED | 0 | 900 | 9000 | -9000 | 0 | 0
|  | Based on minimum 10 pieces and free access |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Note: If hoses are not freely accessible (inside crane column |  | 0 |  | 0 | 0 | 0 | 0
|  | , in energy chain etc.), access charged seperately on t&m basis |  | 0 |  | 0 | 0 | 0 | 0
|  | Scaffolding included in job 1008 | INCL 1008 | 0 |  | 0 | 0 | 0 | 0
1010 | 10 | Check and overhaul broken scupper valves (total 5 pcs).
|  | Overhaul of scupper/storm valves fromdeck without |  | 0 |  | 0 | 0 | 0 | 0
|  | dismounting of valve housing |  | 0 |  | 0 | 0 | 0 | 0
|  | Each valve | QUOTED | 5 | 5700 | 28500 | 0 | 0 | 28500
|  | Possible access i tank, each valve | QUOTED | 5 | 1650 | 8250 | 0 | 0 | 8250
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Possible dis-mounting, transportation of valve, based |  | 0 |  | 0 | 0 | 0 | 0
|  | on free access for transportation |  | 0 |  | 0 | 0 | 0 | 0
|  | Each valve | CANCELLED | 0 | 5980 | 29900 | 0 | -29900 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Possible repair remote control, based on free access |  | 0 |  | 0 | 0 | 0 | 0
|  | Each | QUOTED | 5 | 4150 | 20750 | 0 | 0 | 20750
1011 | 11 | Safegrips in Ramps, basis 210m2
|  | HP-cleaning with soap. |  | 0 |  | 0 | 0 | 0 | 0
|  | Cyclon cleaning. |  | 0 |  | 0 | 0 | 0 | 0
|  | Mechanical cleaning where cyclon cleaning not possible. |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning before painting. |  | 0 |  | 0 | 0 | 0 | 0
|  | Painting primer before Bimagrip |  | 0 |  | 0 | 0 | 0 | 0
|  | Bimagrip compound application |  | 0 |  | 0 | 0 | 0 | 0
|  | Per m2 | QUOTED | 210 | 520 | 88400 | 20800 | 0 | 109200
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Cleaning of lashing pots, each. | QUOTED | 10 | 35 | 0 | 350 | 0 | 350
|  | Lashing pots protection and painting of deck part of |  | 0 |  | 0 | 0 | 0 | 0
|  | lashing pot, each. | CANCELLED | 0 | 22 | 0 | 0 | 0 | 0
|  | Lashing pots cleaning, blasting and painting, each. | CANCELLED | 0 | 440 | 0 | 0 | 0 | 0
1012 | 12 | Welding of crack PS ramps, frame 70, DK3-5. Crack leads
|  | into engine room |  | 0 |  | 0 | 0 | 0 | 0
|  | Priced after joint inspection upon vessel arrival |  | 0 |  | 0 | 0 | 0 | 0
|  | to agree work scope |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Welding Incert PS ramp frame 70 Deck 3 - 5 |  | 0 |  | 0 | 0 | 0 | 0
|  | Steel work | VOR 3 | 1 | 28000 | 0 | 28000 | 0 | 28000
|  | Scaffolding | VOR 3 | 1 | 13050 | 0 | 13050 | 0 | 13050
|  | Fire watch | VOR 3 | 1 | 7250 | 0 | 7250 | 0 | 7250
|  | Material. | VOR 3 | 1 | 7500 | 0 | 7500 | 0 | 7500
|  | Insulation | VOR 3 | 1 | 14500 | 0 | 14500 | 0 | 14500
|  | Paint | VOR 3 | 1 | 7250 | 0 | 7250 | 0 | 7250
|  | SOW | VOR 3 | 1 | 8500 | 0 | 8500 | 0 | 8500
1013 | 13 | Welding of cracks PS ramp, frame 203, DK7-8. Crack leads
|  | into void space. |  | 0 |  | 0 | 0 | 0 | 0
|  | Priced after joint inspection upon vessel arrival to |  | 0 |  | 0 | 0 | 0 | 0
|  | agree work scope |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Repair of cracks deck 5-7 7-8 |  | 0 |  | 0 | 0 | 0 | 0
|  | Steelwork | VOR 4 | 1 | 34000 | 0 | 34000 | 0 | 34000
|  | Sow | VOR 4 | 1 | 8500 | 0 | 8500 | 0 | 8500
|  | Ex Paint and NDT |  | 0 |  | 0 | 0 | 0 | 0
1014 | 14 | Crack in frame WD ramp + Stern ramp Flap + FFB
|  | (top platform) |  | 0 |  | 0 | 0 | 0 | 0
|  | Priced after joint inspection upon vessel arrival to |  | 0 |  | 0 | 0 | 0 | 0
|  | agree work scope |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Repair of crack on stern ramp. |  | 0 |  | 0 | 0 | 0 | 0
|  | Steel work | VOR 5 | 1 | 10200 | 0 | 10200 | 0 | 10200
|  | Sow | VOR 5 | 1 | 4500 | 0 | 4500 | 0 | 4500
|  | Ex Paint and NDT |  | 0 |  | 0 | 0 | 0 | 0
1015 | 15 | Cargo fan Aft. Dis-mounting of damage fan for overhauling
|  | Norm. Elmotor overhaul in workshop. Disconnect/ |  | 0 |  | 0 | 0 | 0 | 0
|  | connect onboard & rigging incl grids on dampers |  | 0 |  | 0 | 0 | 0 | 0
|  | 2 pcs off - 1 pc on(Vessel supply) | QUOTED | 1 | 52662 | 0 | 52662 | 0 | 52662
|  | Balancing wings | QUOTED | 2 | 4300 | 0 | 8600 | 0 | 8600
|  |  |  | 0 |  | 0 | 0 | 0 | 0
1016 | 16 | Clogged drain pipes from ME Safety filter. PS + SB
|  | Clogged drain pipes from ME Safety filter. |  | 0 |  | 0 | 0 | 0 | 0
|  | Priced after joint inspection and agreed work scope |  | 0 |  | 0 | 0 | 0 | 0
|  | Possible insulation |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Timesheets: |  | 0 |  | 0 | 0 | 0 | 0
|  | According to timesheet 13-08-2024 |  | 1 | 19950 | 0 | 19950 | 0 | 19950
|  | According to timesheet 14-08-2024 |  | 1 | 19900 | 0 | 0 | 19900 | 19900
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Remaining work incl cleaning | QUOTED | 1 | 34000 | 0 | 0 | 34000 | 34000
|  | Insulation renewed | QUOTED | 1 | 21000 | 0 | 0 | 21000 | 21000
1017 | 17 | Steering gear electrical motor bearing replacement
|  | Norm. Elmotor overhaul in workshop. Disconnect/ |  | 0 |  | 0 | 0 | 0 | 0
|  | connect onboard & rigging |  | 0 |  | 0 | 0 | 0 | 0
|  | Disassemble. Wash & drying. Assemble with new owner |  | 0 |  | 0 | 0 | 0 | 0
|  | supplied bearings. Testrun & report |  | 0 |  | 0 | 0 | 0 | 0
|  | Per unit, based on size 45 kw | CANCELLED | 0 | 20700 | 0 | 0 | 0 | 0
|  | Price based on free access onboard. |  | 0 |  | 0 | 0 | 0 | 0
|  | Excl access cover on deck |  | 0 |  | 0 | 0 | 0 | 0
1018 | 18 | Steering gear oil leak
|  | Steering gear oil leak |  | 0 |  | 0 | 0 | 0 | 0
|  | Priced after joint inspection and agreed work scope |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | leaks inspected with engineer and scope agreed |  | 0 |  | 0 | 0 | 0 | 0
|  | misc. Leaks to be repaired |  | 0 |  | 0 | 0 | 0 | 0
|  | estimated work | VOR 8 | 1 | 50750 | 0 | 50750 | 0 | 50750
|  | excl materials and possible other repairs |  | 0 |  | 0 | 0 | 0 | 0
|  | Hydraulic hose repair - Oliver | QUOTED | 1 | 1300 | 0 | 0 | 1300 | 1300
1019 | 19 | Cable pull to Sensor in high tank and Evaporator tank.
|  | Cable pull to Sensor in high tank and Evaporator tank. |  | 0 |  | 0 | 0 | 0 | 0
|  | Priced after joint inspection and agreed work scope |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | cable pulls |  | 0 |  | 0 | 0 | 0 | 0
|  | lt tank, ht tank, fbd-cylinder tank deck 3 sb +ps, ht tank, |  | 0 |  | 0 | 0 | 0 | 0
|  | evap tank |  | 0 |  | 0 | 0 | 0 | 0
|  | 6 different cables |  | 0 |  | 0 | 0 | 0 | 0
|  | app |  | 0 |  | 0 | 0 | 0 | 0
|  | Ca 70 m 4x2x0,75 |  | 0 |  | 0 | 0 | 0 | 0
|  | Ca 140 m 2x2x0,75 |  | 0 |  | 0 | 0 | 0 | 0
|  | Ca 80 m 10x2x0,75 |  | 0 |  | 0 | 0 | 0 | 0
|  | incl cable and strips | VOR 9 | 1 | 147100 | 0 | 147100 | 0 | 147100
|  | excl paint and electrical installation |  | 0 |  | 0 | 0 | 0 | 0
1020 | 20 | Inspection of Anti fouling
|  | Inspection of Anti fouling |  | 0 |  | 0 | 0 | 0 | 0
|  | Joint inspection when vessel is high and dry | INFO | 0 |  | 0 | 0 | 0 | 0
1021 | 21 | Inspection of cross over line
|  | Inspection and cleaning of cross over based on same SOW |  | 0 |  | 0 | 0 | 0 | 0
|  | af on Flandria Seaways project No. 231121 | CANCELLED | 0 | 210350 | 210350 | -210350 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Disposal of scallops 25 ton | CANCELLED | 0 | 7500 | 187500 | -187500 | 0 | 0
|  | Bottom plugs in/out | QUOTED | 1 | 500 | 0 | 500 | 0 | 500
1022 | 22 | Strut crack inspection SB & PS
|  | Strut crack inspection SB & PS |  | 0 |  | 0 | 0 | 0 | 0
|  | Joint inspection to agree work scope |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Repair crack in struts SB and PS by welding. |  | 0 |  | 0 | 0 | 0 | 0
|  | Manpower | VOR 1 | 1 | 24650 | 0 | 24650 | 0 | 24650
|  | Cherry picker | VOR 1 | 1 | 7000 | 0 | 7000 | 0 | 7000
|  | SOW | VOR 1 | 1 | 11040 | 0 | 11040 | 0 | 11040
|  | Paint | VOR 1 | 1 | 8625 | 0 | 8625 | 0 | 8625
|  | Force | VOR 1 | 1 | 25000 | 0 | 25000 | 0 | 25000
1023 | 23 | Bilge keel crack inspection SB & PS
|  | Bilge keel crack inspection SB & PS |  | 0 |  | 0 | 0 | 0 | 0
|  | Joint inspection to agree work scope |  | 0 |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0
|  | Repair of crack and modification on bilge keel |  | 0 |  | 0 | 0 | 0 | 0
|  | Repair of crack | VOR 2 | 1 | 19575 | 0 | 19575 | 0 | 19575
|  | Modification bilge keel | VOR 2 | 1 | 163200 | 0 | 163200 | 0 | 163200
|  | Cherry picker | VOR 2 | 1 | 21000 | 0 | 21000 | 0 | 21000
|  | Scaffolding 3 pcs | VOR 2 | 1 | 24000 | 0 | 24000 | 0 | 24000
|  | Paint | VOR 2 | 1 | 23200 | 0 | 23200 | 0 | 23200
|  | ect. NDT. |  | 0 |  | 0 | 0 | 0 | 0
1024 |  | Repair of brackets for scrubber
|  | SB + PS | QUOTED | 1 | 70200 | 70200 | 0 | 0 | 70200
|  | Staging | QUOTED | 2 | 8000 | 16000 | 0 | 0 | 16000
1025 |  | Crane assistance
|  | Crane assistance |  | 0 |  | 0 | 0 | 0 | 0
|  | Timesheet: |  | 0 |  | 0 | 0 | 0 | 0
|  | According to timesheet 13-08-2024 |  | 1 | 7700 | 0 | 7700 | 0 | 7700
|  | According to timesheet 14-08-2024 |  | 1 | 2000 | 0 | 0 | 2000 | 2000
1026 |  | Change seals in ME 1 and 2 LDCL pumps
|  | Change seals in ME 1 and 2 LDCL pumps | QUOTED | 1 | 23200 | 46400 | 0 | -23200 | 23200
|  | One seal replaced - one pump replaced | QUOTED | 1 | 25900 | 0 | 25900 | 0 | 25900
1027 |  | Change HT pump AE2, sparepump onboard
|  | Change HT pump AE2, sparepump onboard | QUOTED | 1 | 12320 | 12320 | 0 | 0 | 12320
|  | Change LT pump AE2 |  | 1 | 6200 | 0 | 0 | 6200 | 6200
1028 |  | Change prelube pump AE1, sparepump onboard
|  | Change prelube pump AE1, sparepump onboard | QUOTED | 1 | 12320 | 12320 | 0 | 0 | 12320
1030 |  | Flex hoses AE water connections
|  | Flex hoses AE water connections | CANCELLED | 0 |  | 0 | 0 | 0 | 0
1031 |  | Stocksupply
|  | Stocksupply | QUOTED | 1 | 15100 | 30000 | 0 | -14900 | 15100
1032 |  | Scaffolding for TC
|  | Scaffolding for TC | QUOTED | 1 | 9850 | 0 | 9850 | 0 | 9850
1033 |  | Removal of cablepipes
|  | Cut down cabel pipes on transom |  | 0 |  | 0 | 0 | 0 | 0
|  | Steelwork | VOR 6 | 1 | 19550 | 0 | 19550 | 0 | 19550
|  | Cherry picker | VOR 6 | 1 | 7500 | 0 | 7500 | 0 | 7500
|  | Sow | VOR 6 | 1 | 6500 | 0 | 6500 | 0 | 6500
|  | Paint. | VOR 6 | 1 | 10500 | 0 | 10500 | 0 | 10500
1034 |  | Valves for LDCL 4 pcs
|  | Delivery of Valves for MELDCL 4 pcs |  | 0 |  | 0 | 0 | 0 | 0
|  | DN 100 incl gear box 150 degreas |  | 0 |  | 0 | 0 | 0 | 0
|  | Incl. Manpower for demounting - mounting of 2 valves | VOR 7 | 1 | 19500 | 0 | 19500 | 0 | 19500
1035 |  | HP wash (low pressure on silicone) 1200 m2 app. Vertical sides
|  | (green belt) | QUOTED | 1200 | 24 | 0 | 28800 | 0 | 28800
1036 |  | Sterntube temp. sensors PS aft replacement
|  | Sterntube temp. sensors PS aft replacement | INFO | 0 |  | 0 | 0 | 0 | 0
|  | Only if possible, to replace, yard deliver sensor |  | 0 |  | 0 | 0 | 0 | 0
|  | (possible next docking scope) |  | 0 |  | 0 | 0 | 0 | 0
1037 |  | MGO service tank pipe clogged
|  | Disconnect and clean pipes | INFO | 0 |  | 0 | 0 | 0 | 0
|  | Ask crew |  | 0 |  | 0 | 0 | 0 | 0
|  | (possible next docking scope) |  | 0 |  | 0 | 0 | 0 | 0
1038 |  | New sewage discharge pump installation
|  | New pump to be installed vessel supply | INFO | 0 |  | 0 | 0 | 0 | 0
|  | Foundation for pump to be manufactured |  | 0 |  | 0 | 0 | 0 | 0
|  | Pipes for pump to be manufactured and galvanized |  | 0 |  | 0 | 0 | 0 | 0
|  | Excl electrical connections |  | 0 |  | 0 | 0 | 0 | 0
|  | Ask crew |  | 0 |  | 0 | 0 | 0 | 0
|  | (possible next docking scope) |  | 0 |  | 0 | 0 | 0 | 0
1039 |  | Grids/mudbox for evap tank drain
|  | Grid for drain inside evap tank to be manufactured | QUOTED | 1 | 10700 | 0 | 0 | 10700 | 10700
|  | Crew to open and clean tank |  | 0 |  | 0 | 0 | 0 | 0
|  | Ask crew |  | 0 |  | 0 | 0 | 0 | 0
|  | (possible next docking scope) |  | 0 |  | 0 | 0 | 0 | 0
1040 |  | Pipe for swimmingpool
|  | Ask CHO | INFO | 0 |  | 0 | 0 | 0 | 0
|  | possible next docking scope) |  | 0 |  | 0 | 0 | 0 | 0
1041 |  | Scaffolding in NaoH room ps aft
|  | Scaffolding in NaoH room ps aft | QUOTED | 1 | 15400 | 0 | 30000 | -14600 | 15400
1042 |  | Valve replacement on closed loop cooler
|  | Valve replacement on closed loop cooler | QUOTED | 1 | 14950 | 0 | 25000 | -10050 | 14950
|  | Valve and actuator vessel supply |  | 0 |  | 0 | 0 | 0 | 0
1043 |  | Sludge discharge / Bilge dischare
|  | Connection | QUOTED | 1 | 4000 | 0 | 4000 | 0 | 4000
|  | Mud truck | QUOTED | 30 | 1150 | 0 | 23000 | 11500 | 34500
|  | Disposal | QUOTED | 90 | 1200 | 0 | 72000 | 36000 | 108000
1044 |  | Delivery an installation of level control in sewage tk.
|  | Delivery an installation of level control in sewage tk. | INCL | 0 |  | 0 | 20000 | -20000 | 0
1045 |  | Gaskets for TC 4 pcs
|  | Gaskets for TC 4 pcs | QUOTED | 1 | 5875 | 0 | 0 | 5875 | 5875
1046 |  | Valve adapter
|  | Valve adapter | QUOTED | 1 | 5015 | 0 | 0 | 5015 | 5015
1047 |  | Bus for crew
|  | Bus for crew | QUOTED | 1 | 3000 | 0 | 0 | 3000 | 3000
9010 |  | Assistance S.A.E.
|  | Assistance S.A.E. |  | 0 |  | 0 | 0 | 0 | 0
9990 |  | Freight/Customs/Documentation
|  | Freight/Customs/Documentation |  | 1 | 20000 | 20000 | 0 | 0 | 20000
9993 |  | Discount according to agreement
|  | Discount according to agreement | 15% | 1 | -285439.8 | -201282 | -77581 | -6576 | -285440
|  |  | DKK |  |  | 1047451 | 532778 | 37264 | 1617492 | 0